## Bookings - AI Training
Booking_ID | Request_Date | Booking_Date | Rescheduled_To | Lead_Time_Days | Equipment_Category | Equipment_Type | Equipment_ID | Ton_Capacity | Load_Weight_T | Location | Project | Project_Phase | Lift_Item | Duration | Shift | Operator_Team | Operator_Certification | Priority | Status | Status_Reason | Weather_Condition | Wind_Speed_Knots | Service_Conflict | Crane_Utilization_Pct | Duration_Variance | Priority_Score | Has_Conflict | Conflict_With | Conflict_Resolution | Wins_Equipment
BK-0001 | 2026-01-04 | 2026-01-05 |  | 1 | Crane | Goliath Gantry Crane | GC-19 | 240 | 79.7 | YST 19 | E | Planning | Engine Module | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Low | Completed |  | Overcast | 15 | FALSE | 91 | Early | 1 | No |  | No Conflict | Yes
BK-0002 | 2026-01-25 | 2026-02-04 |  | 10 | Cometto | SPMT 16 Axle Lines | COM-04 |  |  | YST 05 | C | Testing | Hull Block Section | 10 Days | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Completed |  | Clear | 3 | FALSE | 74 | On Time | 2 | No |  | No Conflict | Yes
BK-0003 | 2026-01-30 | 2026-02-04 | 2026-02-10 | 5 | MEWP | Articulating Boom Lift 26m | MEWP-23 |  |  | YST 07 | A | Outfitting | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | Basic Operator | Urgent | Rescheduled | Equipment breakdown | Clear | 13 | TRUE | 37 |  | 4 | No |  | No Conflict | Yes
BK-0004 | 2026-01-30 | 2026-02-07 |  | 8 | Crane | Workshop Crane | WOR-15 | 10 | 6.8 | YST 11 | C | Planning | Structural Steel Module | 2 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Crane Operator | High | Completed |  | Clear | 3 | FALSE | 44 | On Time | 3 | No |  | No Conflict | Yes
BK-0005 | 2026-01-31 | 2026-02-07 |  | 7 | Cometto | Cometto Eco500 12 Axle Lines | COM-07 |  |  | YST 18 | E | Testing | Offshore Platform Topside | 7 Days | Day Shift (0700-1900) | Team Beta | MEWP Operator | Medium | Completed |  | Clear | 15 | FALSE | 65 | On Time | 2 | No |  | No Conflict | Yes
BK-0006 | 2026-01-05 | 2026-01-11 |  | 6 | Crane | Level Luffing Crane | LLC 06 | 30 | 18.2 | YST 05 | D | Testing | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Pending |  | Clear | 2 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0007 | 2026-01-25 | 2026-01-29 |  | 4 | MEWP | Scissor Lift 10m | MEWP-14 |  |  | YST 10 | E | Fabrication | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Urgent | Completed |  | Partly Cloudy | 5 | FALSE | 59 | Delayed | 4 | No |  | No Conflict | Yes
BK-0008 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 7 | Crane | Goliath Gantry Crane | GC-01 | 600 | 150.8 | YST 19 | C | Fabrication | Riser Assembly | 3 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Urgent | Rescheduled | Weather delay | Clear | 4 | FALSE | 54 |  | 4 | No |  | No Conflict | Yes
BK-0009 | 2026-01-05 | 2026-01-07 |  | 2 | MEWP | Boom Lift 20m | MEWP-17 |  |  | YST 09 | F | Fabrication | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Beta | MEWP Operator | Urgent | Rejected | Load exceeds crane capacity | Overcast | 14 | FALSE | 53 |  | 4 | No |  | No Conflict | Yes
BK-0010 | 2026-01-15 | 2026-01-17 |  | 2 | Crane | Crawler Crane | CRA-08 | 50 | 18.4 | YST D2 | A | Assembly | Transformer Unit | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | High | Completed |  | Clear | 9 | FALSE | 74 | On Time | 3 | No |  | No Conflict | Yes
BK-0011 | 2026-01-30 | 2026-02-10 |  | 11 | MEWP | Boom Lift 20m | MEWP-26 |  |  | YST D4 | D | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Completed |  | Clear | 5 | FALSE | 86 | On Time | 2 | No |  | No Conflict | Yes
BK-0012 | 2026-01-28 | 2026-01-30 | 2026-02-03 | 2 | Crane | Tower Crane | TOW-06 | 40 | 31.3 | YST 12 | E | Planning | Anchor Chain | Full Day | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Medium | Rescheduled | Operator reassigned | Clear | 2 | TRUE | 51 |  | 2 | No |  | No Conflict | Yes
BK-0013 | 2026-01-07 | 2026-01-18 | 2026-01-19 | 11 | Forklift | Heavy Duty Forklift | FLT-17 | 25 | 10.3 | YST 01 | E | Commissioning | Consumables Pallet | 7 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | Medium | Rescheduled | Original date conflicts with maintenance | Overcast | 6 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0014 | 2026-01-24 | 2026-01-28 |  | 4 | Crane | Mobile Crane | MOB-03 | 50 | 28.6 | YST 01 | A | Testing | Transformer Unit | 7 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | High | Completed |  | Clear | 3 | FALSE | 77 | Delayed | 3 | No |  | No Conflict | Yes
BK-0015 | 2026-01-11 | 2026-01-23 |  | 12 | Crane | Workshop Crane | WOR-13 | 20 | 4.9 | YST 11 | A | Planning | Accommodation Module | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Rejected | Operator not available | Partly Cloudy | 5 | TRUE | 42 |  | 2 | No |  | No Conflict | Yes
BK-0016 | 2026-01-29 | 2026-01-31 |  | 2 | Crane | Crawler Crane | CRA-18 | 100 | 76.3 | YST 08 | E | Assembly | Flare Tower Section | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | Medium | Cancelled | Client cancelled | High Wind | 28 | FALSE | 26 |  | 2 | No |  | No Conflict | Yes
BK-0017 | 2026-01-24 | 2026-01-31 |  | 7 | Crane | Tower Crane | TOW-09 | 15 | 8.7 | YST 17 | C | Planning | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Low | Completed |  | Clear | 6 | FALSE | 87 | On Time | 1 | No |  | No Conflict | Yes
BK-0018 | 2026-01-23 | 2026-01-28 |  | 5 | Crane | Level Luffing Crane | LLC 12 | 40 | 24 | YST D2 | A | Assembly | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Beta | Advanced Crane Operator | Low | Completed |  | Clear | 9 | FALSE | 75 | Early | 1 | No |  | No Conflict | Yes
BK-0019 | 2026-01-14 | 2026-01-27 |  | 13 | Cometto | Cometto Eco500 12 Axle Lines | COM-07 |  |  | YST 03 | F | Commissioning | Hull Block Section | Half Day (AM) | Night Shift (1900-0700) | Team Gamma | Basic Operator | High | Completed |  | Light Rain | 10 | FALSE | 84 | On Time | 3 | No |  | No Conflict | Yes
BK-0020 | 2026-01-28 | 2026-01-29 |  | 1 | MEWP | Boom Lift 20m | MEWP-12 |  |  | YST D3 | D | Assembly | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Beta | MEWP Operator | Medium | Cancelled | Duplicate booking | Clear | 4 | FALSE | 42 |  | 2 | No |  | No Conflict | Yes
BK-0021 | 2026-01-21 | 2026-01-27 |  | 6 | Cometto | SPMT 16 Axle Lines | COM-05 |  |  | YST 01 | C | Commissioning | Engine Module | Full Day | Night Shift (1900-0700) | Team Gamma | Forklift Operator | Low | Pending |  | Light Rain | 15 | FALSE | 52 |  | 1 | No |  | No Conflict | Yes
BK-0022 | 2026-01-04 | 2026-01-09 | 2026-01-16 | 5 | MEWP | Articulating Boom Lift 26m | MEWP-23 |  |  | YST 02 | F | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Rescheduled | Equipment breakdown | Clear | 15 | FALSE | 62 |  | 3 | No |  | No Conflict | Yes
BK-0023 | 2026-01-04 | 2026-01-12 |  | 8 | Crane | Crawler Crane | CRA-10 | 250 | 132.2 | YST 06 | B | Testing | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | Urgent | Cancelled | Duplicate booking | Overcast | 14 | FALSE | 33 |  | 4 | No |  | No Conflict | Yes
BK-0024 | 2026-01-14 | 2026-01-23 | 2026-01-25 | 9 | MEWP | Articulating Boom Lift 26m | MEWP-15 |  |  | YST D3 | F | Fabrication | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Rescheduled | Permit delay | Overcast | 11 | FALSE | 68 |  | 3 | No |  | No Conflict | Yes
BK-0025 | 2026-01-22 | 2026-01-26 |  | 4 | Forklift | Heavy Duty Forklift | FLT-31 | 10 | 5.4 | YST 02 | B | Commissioning | Valve Crates | 3 Days | Night Shift (1900-0700) | Team Delta | Basic Operator | Medium | Cancelled | Client cancelled | Overcast | 17 | FALSE | 68 |  | 2 | No |  | No Conflict | Yes
BK-0026 | 2026-01-28 | 2026-02-06 |  | 9 | Crane | Mobile Crane | MOB-17 | 50 | 19.5 | YST 03 | F | Testing | Helideck Module | 3 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Medium | Rejected | Permit not approved | High Wind | 44 | FALSE | 66 |  | 2 | No |  | No Conflict | Yes
BK-0027 | 2026-01-29 | 2026-02-04 |  | 6 | Forklift | Reach Forklift | FLT-29 | 2 | 0.7 | YST D4 | D | Commissioning | Small Fittings Pallet | Full Day | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Rejected | Operator not available | Clear | 16 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0028 | 2026-01-03 | 2026-01-06 |  | 3 | Crane | Workshop Crane | WOR-14 | 10 | 7.1 | YST 10 | D | Testing | Engine Module | 2 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Low | Rejected | Location conflict with another operation | High Wind | 25 | FALSE | 42 |  | 1 | No |  | No Conflict | Yes
BK-0029 | 2026-01-10 | 2026-01-19 |  | 9 | Forklift | Reach Forklift | FLT-18 | 2 | 1.8 | YST 16 | F | Fabrication | Valve Crates | 2 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | High | Rejected | Location conflict with another operation | Light Rain | 6 | FALSE | 62 |  | 3 | No |  | No Conflict | Yes
BK-0030 | 2026-01-01 | 2026-01-03 |  | 2 | Crane | Mobile Crane | MOB-13 | 50 | 10.6 | YST 01 | D | Assembly | Accommodation Module | 2 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Completed |  | Light Rain | 17 | FALSE | 62 | On Time | 3 | No |  | No Conflict | Yes
BK-0031 | 2026-01-03 | 2026-01-12 |  | 9 | Cometto | Cometto MSPE 8 Axle Lines | COM-01 |  |  | YST 04 | B | Outfitting | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | High | Pending |  | Overcast | 13 | FALSE | 58 |  | 3 | No |  | No Conflict | Yes
BK-0032 | 2026-01-31 | 2026-02-09 |  | 9 | Crane | Goliath Gantry Crane | GC-01 | 300 | 78.3 | YST 01 | A | Testing | Construction Materials | 7 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Cancelled | Budget constraint | Overcast | 9 | FALSE | 27 |  | 2 | No |  | No Conflict | Yes
BK-0033 | 2026-01-26 | 2026-02-09 |  | 14 | Forklift | Telehandler Forklift | FLT-05 | 7 | 5.1 | YST D2 | C | Commissioning | Bolt Pallets | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | High | Confirmed |  | Heavy Rain | 24 | FALSE | 86 |  | 3 | No |  | No Conflict | Yes
BK-0034 | 2026-01-17 | 2026-01-30 |  | 13 | Crane | Tower Crane | TOW-19 | 40 | 16.1 | YST D3 | D | Testing | Anchor Chain | Full Day | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | Medium | Completed |  | Overcast | 14 | FALSE | 60 | On Time | 2 | No |  | No Conflict | Yes
BK-0035 | 2026-01-07 | 2026-01-12 |  | 5 | Crane | Crawler Crane | CRA-17 | 150 | 70.3 | YST D1 | B | Commissioning | Hull Block Section | 10 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | Medium | Pending |  | Partly Cloudy | 17 | FALSE | 38 |  | 2 | No |  | No Conflict | Yes
BK-0036 | 2026-01-08 | 2026-01-13 |  | 5 | Crane | Workshop Crane | WOR-17 | 20 | 12.7 | YST D6 | C | Assembly | Transformer Unit | 2 Days | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Medium | Cancelled | Budget constraint | Clear | 5 | FALSE | 68 |  | 2 | No |  | No Conflict | Yes
BK-0037 | 2026-01-23 | 2026-01-26 |  | 3 | Crane | Mobile Crane | MOB-17 | 75 | 27.3 | YST D7 | C | Planning | Helideck Module | 3 Days | Night Shift (1900-0700) | Team Beta | Lifting Supervisor | Medium | Completed |  | Overcast | 6 | FALSE | 75 | On Time | 2 | No |  | No Conflict | Yes
BK-0038 | 2026-01-31 | 2026-02-02 |  | 2 | Forklift | Reach Forklift | FLT-37 | 1.5 | 0.9 | YST D8 | D | Planning | Steel Plates | Full Day | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Confirmed |  | Light Rain | 14 | FALSE | 83 |  | 2 | No |  | No Conflict | Yes
BK-0039 | 2026-01-02 | 2026-01-05 |  | 3 | Forklift | Telehandler Forklift | FLT-36 | 3 | 1.4 | YST 08 | D | Outfitting | Insulation Materials | 5 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Pending |  | Clear | 15 | FALSE | 59 |  | 2 | No |  | No Conflict | Yes
BK-0040 | 2026-01-31 | 2026-02-09 |  | 9 | Forklift | Heavy Duty Forklift | FLT-11 | 15 | 7.1 | YST 09 | E | Outfitting | Safety Equipment | Full Day | Day Shift (0700-1900) | Team Beta | Basic Operator | Low | Completed |  | Clear | 9 | FALSE | 95 | On Time | 1 | No |  | No Conflict | Yes
BK-0041 | 2026-01-22 | 2026-01-25 |  | 3 | Crane | Workshop Crane | WOR-18 | 10 | 4.6 | YST D3 | B | Assembly | Engine Module | Full Day | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Confirmed |  | Overcast | 11 | FALSE | 59 |  | 3 | No |  | No Conflict | Yes
BK-0042 | 2026-01-23 | 2026-01-28 |  | 5 | Crane | Tower Crane | TOW-20 | 40 | 32 | YST D3 | B | Commissioning | Engine Module | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | High | Confirmed |  | Light Rain | 2 | FALSE | 57 |  | 3 | No |  | No Conflict | Yes
BK-0043 | 2026-01-19 | 2026-01-20 |  | 1 | Forklift | Reach Forklift | FLT-38 | 3 | 1.5 | YST 09 | C | Commissioning | PPE Supplies | 2 Days | Night Shift (1900-0700) | Team Alpha | Forklift Operator | Medium | Completed |  | Clear | 7 | FALSE | 58 | Delayed | 2 | No |  | No Conflict | Yes
BK-0044 | 2026-01-13 | 2026-01-23 |  | 10 | MEWP | Telescopic Boom Lift 30m | MEWP-11 |  |  | YST 03 | A | Commissioning | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Delta | Advanced Operator | Urgent | Rejected | Weather conditions unsafe | Heavy Rain | 24 | FALSE | 59 |  | 4 | No |  | No Conflict | Yes
BK-0045 | 2026-01-25 | 2026-01-31 |  | 6 | Crane | Level Luffing Crane | LLC 05 | 40 | 15.5 | YST 09 | F | Testing | Transformer Unit | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | Medium | Confirmed |  | Light Rain | 7 | FALSE | 66 |  | 2 | Yes | BK-0065 | First-Come-First-Served | Yes
BK-0046 | 2026-01-03 | 2026-01-06 |  | 3 | Forklift | Counterbalance Forklift | FLT-32 | 7 | 3.7 | YST 04 | D | Fabrication | Welding Materials | 7 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Rejected | Project schedule changed | Partly Cloudy | 6 | FALSE | 28 |  | 2 | No |  | No Conflict | Yes
BK-0047 | 2026-01-28 | 2026-01-30 |  | 2 | Forklift | Reach Forklift | FLT-01 | 2.5 | 1.2 | YST D6 | B | Outfitting | Gasket Boxes | Full Day | Day Shift (0700-1900) | Team Echo | Forklift Operator | High | Cancelled | Material not ready | Partly Cloudy | 13 | FALSE | 49 |  | 3 | No |  | No Conflict | Yes
BK-0048 | 2026-01-30 | 2026-02-03 |  | 4 | Crane | Workshop Crane | WOR-14 | 10 | 7.8 | YST D2 | F | Commissioning | Mega Block Section | Half Day (AM) | Night Shift (1900-0700) | Team Foxtrot | Basic Crane Operator | Urgent | Completed |  | High Wind | 40 | FALSE | 77 | On Time | 4 | No |  | No Conflict | Yes
BK-0049 | 2026-01-04 | 2026-01-15 |  | 11 | Crane | Tower Crane | TOW-05 | 40 | 23.6 | YST 09 | C | Assembly | Turret Assembly | 2 Days | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Low | Rejected | Project schedule changed | Overcast | 14 | FALSE | 40 |  | 1 | No |  | No Conflict | Yes
BK-0050 | 2026-01-21 | 2026-01-29 |  | 8 | Forklift | Counterbalance Forklift | FLT-15 | 2.5 | 2.1 | YST 08 | A | Outfitting | Electrical Cables | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | High | Cancelled | Client cancelled | Clear | 11 | FALSE | 38 |  | 3 | No |  | No Conflict | Yes
BK-0051 | 2026-01-12 | 2026-01-17 |  | 5 | Crane | Tower Crane | TOW-06 | 40 | 19 | YST D8 | E | Fabrication | Workshop Equipment | Full Day | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | High | Completed |  | Clear | 10 | FALSE | 97 | Delayed | 3 | No |  | No Conflict | Yes
BK-0052 | 2026-01-29 | 2026-02-02 |  | 4 | MEWP | Scissor Lift 10m | MEWP-12 |  |  | YST D3 | C | Fabrication | Personnel Access Work | 14 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | High | Completed |  | High Wind | 40 | FALSE | 64 | Delayed | 3 | No |  | No Conflict | Yes
BK-0053 | 2026-01-19 | 2026-01-23 | 2026-01-25 | 4 | Cometto | Cometto MSPE 8 Axle Lines | COM-05 |  |  | YST 18 | F | Outfitting | Offshore Platform Topside | Half Day (AM) | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Urgent | Rescheduled | Operator reassigned | Light Rain | 11 | FALSE | 42 |  | 4 | No |  | No Conflict | Yes
BK-0054 | 2026-01-21 | 2026-01-24 |  | 3 | Crane | Workshop Crane | WOR-02 | 10 | 3.2 | YST 07 | C | Assembly | Riser Assembly | Full Day | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Medium | Confirmed |  | Overcast | 7 | FALSE | 96 |  | 2 | No |  | No Conflict | Yes
BK-0055 | 2026-01-12 | 2026-01-19 |  | 7 | Forklift | Heavy Duty Forklift | FLT-19 | 20 | 17.6 | YST D7 | B | Commissioning | Small Fittings Pallet | 5 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Confirmed |  | Overcast | 14 | FALSE | 63 |  | 2 | No |  | No Conflict | Yes
BK-0056 | 2026-01-03 | 2026-01-12 |  | 9 | Crane | Tower Crane | TOW-09 | 10 | 7.5 | YST D3 | A | Testing | Pipe Spool | 3 Days | Night Shift (1900-0700) | Team Gamma | Advanced Crane Operator | Medium | Completed |  | Heavy Rain | 20 | FALSE | 44 | Delayed | 2 | No |  | No Conflict | Yes
BK-0057 | 2026-01-15 | 2026-01-26 |  | 11 | Crane | Mobile Crane | MOB-02 | 25 | 13.8 | YST 03 | D | Outfitting | Hull Block Section | Full Day | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Medium | Pending |  | Partly Cloudy | 15 | FALSE | 46 |  | 2 | No |  | No Conflict | Yes
BK-0058 | 2026-01-21 | 2026-01-23 | 2026-01-30 | 2 | MEWP | Telescopic Boom Lift 30m | MEWP-02 |  |  | YST 09 | A | Commissioning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Urgent | Rescheduled | Higher priority job took precedence | Partly Cloudy | 13 | TRUE | 27 |  | 4 | No |  | No Conflict | Yes
BK-0059 | 2026-01-27 | 2026-02-02 |  | 6 | Cometto | Cometto MSPE 8 Axle Lines | COM-04 |  |  | YST 01 | B | Testing | Mega Block Section | 14 Days | Night Shift (1900-0700) | Team Beta | Advanced Operator | Low | Rejected | Insufficient lead time | Clear | 9 | FALSE | 58 |  | 1 | No |  | No Conflict | Yes
BK-0060 | 2026-01-01 | 2026-01-05 |  | 4 | Forklift | Heavy Duty Forklift | FLT-08 | 20 | 6.6 | YST D6 | E | Assembly | PPE Supplies | 5 Days | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Rejected | Project schedule changed | Clear | 10 | TRUE | 24 |  | 2 | No |  | No Conflict | Yes
BK-0061 | 2026-01-16 | 2026-01-21 |  | 5 | Crane | Tower Crane | TOW-08 | 10 | 4.6 | YST D3 | A | Planning | Transformer Unit | 10 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | Medium | Completed |  | High Wind | 37 | FALSE | 85 | Early | 2 | No |  | No Conflict | Yes
BK-0062 | 2026-01-03 | 2026-01-14 |  | 11 | Crane | Goliath Gantry Crane | GC-20 | 200 | 51.9 | YST 01 | C | Outfitting | Accommodation Module | 3 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | Medium | Pending |  | Partly Cloudy | 15 | FALSE | 61 |  | 2 | No |  | No Conflict | Yes
BK-0063 | 2026-01-21 | 2026-02-01 |  | 11 | MEWP | Boom Lift 20m | MEWP-15 |  |  | YST D2 | C | Outfitting | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Cancelled | Project postponed | Partly Cloudy | 10 | FALSE | 63 |  | 2 | No |  | No Conflict | Yes
BK-0064 | 2026-01-30 | 2026-02-05 | 2026-02-06 | 6 | Crane | Level Luffing Crane | LLC 15A | 30 | 12.4 | YST 15 | E | Assembly | Engine Module | 5 Days | Night Shift (1900-0700) | Team Echo | Heavy Lift Specialist | Low | Rescheduled | Material delivery delayed | Overcast | 15 | FALSE | 66 |  | 1 | No |  | No Conflict | Yes
BK-0065 | 2026-01-31 | 2026-02-04 |  | 4 | Crane | Level Luffing Crane | LLC 05 | 300 | 212.1 | YST D1 | A | Assembly | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Medium | Pending |  | Overcast | 15 | FALSE | 59 |  | 2 | Yes | BK-0045 | Later Request - Reassigned | No
BK-0066 | 2026-01-20 | 2026-01-28 |  | 8 | MEWP | Articulating Boom Lift 26m | MEWP-06 |  |  | YST 01 | B | Testing | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Gamma | Basic Operator | Medium | Confirmed |  | Overcast | 4 | FALSE | 80 |  | 2 | No |  | No Conflict | Yes
BK-0067 | 2026-01-01 | 2026-01-03 | 2026-01-06 | 2 | MEWP | Telescopic Boom Lift 30m | MEWP-15 |  |  | YST D2 | E | Planning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Rescheduled | Permit delay | Heavy Rain | 14 | TRUE | 25 |  | 2 | No |  | No Conflict | Yes
BK-0068 | 2026-01-15 | 2026-01-23 |  | 8 | MEWP | Telescopic Boom Lift 30m | MEWP-09 |  |  | YST D2 | F | Testing | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Completed |  | Partly Cloudy | 11 | FALSE | 65 | Early | 2 | No |  | No Conflict | Yes
BK-0069 | 2026-01-02 | 2026-01-03 |  | 1 | Crane | Goliath Gantry Crane | GC-16 | 240 | 58.4 | YST 04 | F | Fabrication | Accommodation Module | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | Medium | Completed |  | Partly Cloudy | 13 | FALSE | 42 | On Time | 2 | No |  | No Conflict | Yes
BK-0070 | 2026-01-15 | 2026-01-27 | 2026-01-28 | 12 | Forklift | Reach Forklift | FLT-19 | 3 | 1.7 | YST D3 | D | Commissioning | Scaffolding Materials | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Rescheduled | Material delivery delayed | Thunderstorm | 22 | FALSE | 53 |  | 2 | No |  | No Conflict | Yes
BK-0071 | 2026-01-13 | 2026-01-24 |  | 11 | Cometto | Cometto Eco500 12 Axle Lines | COM-02 |  |  | YST 13 | C | Commissioning | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Rejected | Weather conditions unsafe | High Wind | 45 | TRUE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0072 | 2026-01-07 | 2026-01-10 | 2026-01-14 | 3 | Crane | Workshop Crane | WOR-16 | 10 | 7.2 | YST 09 | E | Commissioning | Helideck Module | 3 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Medium | Rescheduled | Project timeline shifted | Overcast | 12 | FALSE | 50 |  | 2 | No |  | No Conflict | Yes
BK-0073 | 2026-01-21 | 2026-01-25 |  | 4 | Crane | Level Luffing Crane | LLC 10 | 50 | 23.9 | YST D1 | A | Testing | Engine Module | 3 Days | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | High | Confirmed |  | Overcast | 14 | FALSE | 90 |  | 3 | No |  | No Conflict | Yes
BK-0074 | 2026-01-24 | 2026-02-04 | 2026-02-06 | 11 | Crane | Tower Crane | TOW-16 | 15 | 3.4 | YST 17 | C | Commissioning | Construction Materials | 3 Days | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | Medium | Rescheduled | Safety stand-down | Clear | 7 | FALSE | 59 |  | 2 | No |  | No Conflict | Yes
BK-0075 | 2026-01-12 | 2026-01-17 |  | 5 | Crane | Mobile Crane | MOB-02 | 75 | 30 | YST D8 | D | Assembly | Construction Materials | 5 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Medium | Pending |  | Clear | 6 | FALSE | 29 |  | 2 | No |  | No Conflict | Yes
BK-0076 | 2026-01-30 | 2026-02-03 |  | 4 | Forklift | Reach Forklift | FLT-20 | 2 | 1.4 | YST 20 | F | Commissioning | Safety Equipment | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | High | Cancelled | Duplicate booking | Thunderstorm | 22 | FALSE | 21 |  | 3 | No |  | No Conflict | Yes
BK-0077 | 2026-01-12 | 2026-01-16 |  | 4 | Forklift | Telehandler Forklift | FLT-09 | 7 | 5.8 | YST 07 | F | Testing | Valve Crates | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Pending |  | Clear | 12 | FALSE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0078 | 2026-01-13 | 2026-01-16 |  | 3 | Crane | Workshop Crane | WOR-14 | 10 | 7.8 | YST D5 | D | Fabrication | Hull Block Section | 2 Days | Night Shift (1900-0700) | Team Delta | Rigging Supervisor | High | Rejected | Weather conditions unsafe | Partly Cloudy | 11 | FALSE | 56 |  | 3 | No |  | No Conflict | Yes
BK-0079 | 2026-01-15 | 2026-01-21 |  | 6 | Crane | Mobile Crane | MOB-07 | 100 | 71.1 | YST 03 | C | Testing | Flare Tower Section | 5 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Low | Completed |  | High Wind | 41 | FALSE | 88 | On Time | 1 | No |  | No Conflict | Yes
BK-0080 | 2026-01-15 | 2026-01-26 |  | 11 | Crane | Mobile Crane | MOB-15 | 25 | 8.4 | YST 04 | B | Outfitting | Flare Tower Section | 7 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Low | Pending |  | High Wind | 36 | FALSE | 26 |  | 1 | No |  | No Conflict | Yes
BK-0081 | 2026-01-27 | 2026-02-04 |  | 8 | Crane | Goliath Gantry Crane | GC-18 | 240 | 127 | YST 01 | A | Planning | Accommodation Module | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Rigging Supervisor | Medium | Cancelled | Budget constraint | Clear | 6 | FALSE | 47 |  | 2 | No |  | No Conflict | Yes
BK-0082 | 2026-01-04 | 2026-01-13 |  | 9 | Crane | Level Luffing Crane | LLC 21 | 30 | 18.9 | YST 08 | E | Planning | Anchor Chain | 5 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | High | Completed |  | Overcast | 9 | FALSE | 40 | Delayed | 3 | No |  | No Conflict | Yes
BK-0083 | 2026-01-08 | 2026-01-15 |  | 7 | Crane | Workshop Crane | WOR-17 | 10 | 3.5 | YST 15 | D | Planning | Engine Module | 3 Days | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | High | Completed |  | Overcast | 13 | FALSE | 90 | On Time | 3 | No |  | No Conflict | Yes
BK-0084 | 2026-01-08 | 2026-01-17 |  | 9 | MEWP | Articulating Boom Lift 26m | MEWP-02 |  |  | YST 05 | D | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Rejected | Crane already booked | Partly Cloudy | 7 | FALSE | 49 |  | 2 | No |  | No Conflict | Yes
BK-0085 | 2026-01-02 | 2026-01-06 |  | 4 | Crane | Goliath Gantry Crane | GC-15 | 200 | 143.9 | YST 04 | F | Fabrication | Riser Assembly | 3 Days | Night Shift (1900-0700) | Team Echo | Heavy Lift Specialist | Medium | Confirmed |  | Clear | 3 | FALSE | 47 |  | 2 | No |  | No Conflict | Yes
BK-0086 | 2026-01-26 | 2026-01-31 |  | 5 | Forklift | Reach Forklift | FLT-32 | 3 | 1.9 | YST 11 | D | Planning | PPE Supplies | 5 Days | Day Shift (0700-1900) | Team Echo | Advanced Operator | Medium | Confirmed |  | Partly Cloudy | 7 | FALSE | 45 |  | 2 | No |  | No Conflict | Yes
BK-0087 | 2026-01-11 | 2026-01-19 |  | 8 | Crane | Tower Crane | TOW-15 | 40 | 16.7 | YST 12 | F | Planning | Turret Assembly | 2 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | High | Completed |  | Clear | 14 | FALSE | 83 | On Time | 3 | No |  | No Conflict | Yes
BK-0088 | 2026-01-01 | 2026-01-04 | 2026-01-09 | 3 | MEWP | Telescopic Boom Lift 30m | MEWP-05 |  |  | YST 02 | A | Testing | Personnel Access Work | Half Day (AM) | Night Shift (1900-0700) | Team Gamma | MEWP Operator | Medium | Rescheduled | Equipment breakdown | Clear | 16 | FALSE | 24 |  | 2 | No |  | No Conflict | Yes
BK-0089 | 2026-01-05 | 2026-01-11 |  | 6 | Crane | Workshop Crane | WOR-01 | 20 | 12.3 | YST 11 | C | Commissioning | Engine Module | 5 Days | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | Urgent | Confirmed |  | Partly Cloudy | 11 | FALSE | 52 |  | 4 | No |  | No Conflict | Yes
BK-0090 | 2026-01-04 | 2026-01-07 | 2026-01-09 | 3 | Crane | Goliath Gantry Crane | GC-16 | 400 | 270.5 | YST 01 | B | Commissioning | Helideck Module | 5 Days | Night Shift (1900-0700) | Team Echo | Heavy Lift Specialist | Medium | Rescheduled | Weather delay | Overcast | 7 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0091 | 2026-01-08 | 2026-01-17 | 2026-01-21 | 9 | Crane | Tower Crane | TOW-18 | 25 | 17.4 | YST D3 | F | Outfitting | Helideck Module | Half Day (PM) | Night Shift (1900-0700) | Team Alpha | Basic Crane Operator | Medium | Rescheduled | Equipment breakdown | Partly Cloudy | 15 | FALSE | 48 |  | 2 | No |  | No Conflict | Yes
BK-0092 | 2026-01-22 | 2026-01-28 |  | 6 | Crane | Tower Crane | TOW-17 | 15 | 6.1 | YST 12 | B | Assembly | Anchor Chain | 7 Days | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Medium | Completed |  | High Wind | 32 | FALSE | 97 | On Time | 2 | No |  | No Conflict | Yes
BK-0093 | 2026-01-03 | 2026-01-07 |  | 4 | MEWP | Articulating Boom Lift 26m | MEWP-21 |  |  | YST 05 | E | Fabrication | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Pending |  | Clear | 12 | FALSE | 56 |  | 3 | No |  | No Conflict | Yes
BK-0094 | 2026-01-02 | 2026-01-12 | 2026-01-18 | 10 | Crane | Level Luffing Crane | LLC 07 | 300 | 146.9 | YST 09 | E | Assembly | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Lifting Supervisor | Low | Rescheduled | Material delivery delayed | Overcast | 11 | TRUE | 24 |  | 1 | No |  | No Conflict | Yes
BK-0095 | 2026-01-02 | 2026-01-05 |  | 3 | Crane | Mobile Crane | MOB-05 | 50 | 26.8 | YST 06 | D | Fabrication | Construction Materials | 2 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Crane Operator | Urgent | Completed |  | Light Rain | 18 | FALSE | 69 | On Time | 4 | No |  | No Conflict | Yes
BK-0096 | 2026-01-15 | 2026-01-18 |  | 3 | Crane | Crawler Crane | CRA-08 | 250 | 120 | YST D2 | B | Fabrication | Anchor Chain | 10 Days | Night Shift (1900-0700) | Team Gamma | Lifting Supervisor | Urgent | Cancelled | Material not ready | Partly Cloudy | 18 | FALSE | 21 |  | 4 | No |  | No Conflict | Yes
BK-0097 | 2026-01-03 | 2026-01-15 |  | 12 | MEWP | Boom Lift 20m | MEWP-19 |  |  | YST 07 | F | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | High | Rejected | Location conflict with another operation | Clear | 2 | TRUE | 36 |  | 3 | No |  | No Conflict | Yes
BK-0098 | 2026-01-24 | 2026-01-29 |  | 5 | Crane | Level Luffing Crane | LLC 18 | 100 | 27.7 | YST 02 | E | Assembly | Construction Materials | Full Day | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Completed |  | Light Rain | 5 | FALSE | 63 | Delayed | 2 | No |  | No Conflict | Yes
BK-0099 | 2026-01-11 | 2026-01-18 |  | 7 | Crane | Goliath Gantry Crane | GC-17 | 240 | 68.1 | YST 19 | E | Outfitting | Transformer Unit | 3 Days | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | High | Rejected | Load exceeds crane capacity | Clear | 18 | TRUE | 59 |  | 3 | No |  | No Conflict | Yes
BK-0100 | 2026-01-24 | 2026-02-03 |  | 10 | MEWP | Telescopic Boom Lift 30m | MEWP-16 |  |  | YST 10 | C | Commissioning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Completed |  | Heavy Rain | 10 | FALSE | 56 | Early | 2 | No |  | No Conflict | Yes
BK-0101 | 2026-02-19 | 2026-02-22 |  | 3 | Crane | Mobile Crane | MOB-20 | 50 | 19.4 | YST D1 | F | Planning | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | Medium | Pending |  | Clear | 16 | FALSE | 64 |  | 2 | No |  | No Conflict | Yes
BK-0102 | 2026-02-07 | 2026-02-12 |  | 5 | Forklift | Reach Forklift | FLT-34 | 1.5 | 0.9 | YST D3 | B | Outfitting | Welding Materials | Full Day | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Completed |  | Thunderstorm | 30 | FALSE | 95 | Delayed | 2 | No |  | No Conflict | Yes
BK-0103 | 2026-02-21 | 2026-03-03 |  | 10 | Crane | Mobile Crane | MOB-18 | 50 | 20.5 | YST 04 | F | Commissioning | Accommodation Module | Full Day | Night Shift (1900-0700) | Team Gamma | Lifting Supervisor | High | Cancelled | Duplicate booking | Partly Cloudy | 17 | FALSE | 38 |  | 3 | No |  | No Conflict | Yes
BK-0104 | 2026-02-04 | 2026-02-11 |  | 7 | MEWP | Telescopic Boom Lift 30m | MEWP-25 |  |  | YST 12 | D | Commissioning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Urgent | Confirmed |  | Clear | 17 | FALSE | 92 |  | 4 | No |  | No Conflict | Yes
BK-0105 | 2026-02-18 | 2026-02-22 | 2026-02-24 | 4 | MEWP | Articulating Boom Lift 26m | MEWP-04 |  |  | YST 05 | B | Commissioning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | Low | Rescheduled | Safety stand-down | Clear | 5 | TRUE | 69 |  | 1 | No |  | No Conflict | Yes
BK-0106 | 2026-02-01 | 2026-02-14 |  | 13 | Forklift | Heavy Duty Forklift | FLT-31 | 25 | 21.2 | YST D1 | A | Commissioning | Small Fittings Pallet | 3 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | Medium | Cancelled | Project postponed | Overcast | 3 | FALSE | 22 |  | 2 | Yes | BK-0152 | Yielded to Higher Priority | No
BK-0107 | 2026-02-27 | 2026-03-04 | 2026-03-07 | 5 | MEWP | Articulating Boom Lift 26m | MEWP-01 |  |  | YST 02 | E | Testing | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Rescheduled | Safety stand-down | Partly Cloudy | 6 | TRUE | 27 |  | 2 | No |  | No Conflict | Yes
BK-0108 | 2026-02-06 | 2026-02-15 |  | 9 | MEWP | Boom Lift 20m | MEWP-24 |  |  | YST 01 | F | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | High | Confirmed |  | Light Rain | 18 | FALSE | 65 |  | 3 | No |  | No Conflict | Yes
BK-0109 | 2026-02-22 | 2026-02-24 |  | 2 | Forklift | Reach Forklift | FLT-17 | 2.5 | 1.8 | YST 08 | F | Testing | Steel Plates | 2 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Urgent | Completed |  | Clear | 13 | FALSE | 47 | On Time | 4 | No |  | No Conflict | Yes
BK-0110 | 2026-02-06 | 2026-02-11 | 2026-02-16 | 5 | MEWP | Articulating Boom Lift 26m | MEWP-21 |  |  | YST 04 | D | Fabrication | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Echo | Advanced Operator | Medium | Rescheduled | Client request | Partly Cloudy | 13 | FALSE | 68 |  | 2 | Yes | BK-0189 | Yielded to Higher Priority | No
BK-0111 | 2026-02-26 | 2026-03-06 |  | 8 | Crane | Goliath Gantry Crane | GC-18 | 600 | 179.2 | YST 01 | E | Fabrication | Transformer Unit | 3 Days | Day Shift (0700-1900) | Team Echo | Lifting Supervisor | Medium | Rejected | Permit not approved | Overcast | 6 | TRUE | 33 |  | 2 | No |  | No Conflict | Yes
BK-0112 | 2026-02-23 | 2026-03-02 |  | 7 | Crane | Tower Crane | TOW-05 | 40 | 27.6 | YST 09 | C | Commissioning | Mooring Winch | 3 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | High | Cancelled | Budget constraint | Clear | 10 | FALSE | 24 |  | 3 | No |  | No Conflict | Yes
BK-0113 | 2026-02-02 | 2026-02-07 | 2026-02-13 | 5 | Cometto | Cometto MSPE 8 Axle Lines | COM-01 |  |  | YST 02 | F | Outfitting | Offshore Platform Topside | Full Day | Day Shift (0700-1900) | Team Beta | Advanced Operator | High | Rescheduled | Material delivery delayed | Partly Cloudy | 14 | FALSE | 63 |  | 3 | No |  | No Conflict | Yes
BK-0114 | 2026-02-28 | 2026-03-07 |  | 7 | Cometto | SPMT 16 Axle Lines | COM-09 |  |  | YST 02 | C | Outfitting | Hull Block Section | 2 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | High | Rejected | Weather conditions unsafe | Overcast | 15 | TRUE | 42 |  | 3 | No |  | No Conflict | Yes
BK-0115 | 2026-02-05 | 2026-02-09 |  | 4 | Forklift | Counterbalance Forklift | FLT-40 | 2.5 | 1.1 | YST D6 | E | Planning | Scaffolding Materials | 5 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Confirmed |  | Partly Cloudy | 3 | FALSE | 68 |  | 2 | No |  | No Conflict | Yes
BK-0116 | 2026-02-08 | 2026-02-15 |  | 7 | Forklift | Counterbalance Forklift | FLT-15 | 3 | 2.7 | YST 17 | C | Fabrication | Electrical Cables | 5 Days | Night Shift (1900-0700) | Team Gamma | Forklift Operator | High | Rejected | Location conflict with another operation | Partly Cloudy | 6 | FALSE | 23 |  | 3 | No |  | No Conflict | Yes
BK-0117 | 2026-02-18 | 2026-03-02 |  | 12 | Forklift | Heavy Duty Forklift | FLT-04 | 25 | 13.1 | YST 18 | F | Outfitting | Small Fittings Pallet | 10 Days | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Medium | Pending |  | Partly Cloudy | 11 | FALSE | 50 |  | 2 | No |  | No Conflict | Yes
BK-0118 | 2026-02-08 | 2026-02-18 |  | 10 | Crane | Workshop Crane | WOR-02 | 10 | 7.5 | YST D5 | C | Fabrication | Riser Assembly | 3 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | Medium | Completed |  | Partly Cloudy | 4 | FALSE | 45 | Delayed | 2 | No |  | No Conflict | Yes
BK-0119 | 2026-02-27 | 2026-03-02 | 2026-03-07 | 3 | Crane | Workshop Crane | WOR-19 | 10 | 7.8 | YST 06 | C | Planning | Mega Block Section | 5 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Medium | Rescheduled | Safety stand-down | Clear | 8 | FALSE | 64 |  | 2 | No |  | No Conflict | Yes
BK-0120 | 2026-02-23 | 2026-02-26 |  | 3 | Forklift | Telehandler Forklift | FLT-35 | 5 | 4.2 | YST 13 | A | Commissioning | Timber Dunnage | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Medium | Completed |  | Partly Cloudy | 12 | FALSE | 66 | On Time | 2 | No |  | No Conflict | Yes
BK-0121 | 2026-02-28 | 2026-03-03 |  | 3 | Crane | Crawler Crane | CRA-07 | 250 | 195 | YST 05 | F | Assembly | Structural Steel Module | 2 Days | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Cancelled | Material not ready | Clear | 17 | FALSE | 49 |  | 2 | No |  | No Conflict | Yes
BK-0122 | 2026-02-06 | 2026-02-15 |  | 9 | Crane | Goliath Gantry Crane | GC-19 | 600 | 169.5 | YST 04 | F | Planning | Structural Steel Module | 14 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | Low | Rejected | Crane already booked | Light Rain | 15 | FALSE | 20 |  | 1 | No |  | No Conflict | Yes
BK-0123 | 2026-02-07 | 2026-02-13 |  | 6 | Crane | Tower Crane | TOW-01 | 40 | 27.3 | YST D3 | C | Planning | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Medium | Completed |  | Partly Cloudy | 15 | FALSE | 46 | Early | 2 | No |  | No Conflict | Yes
BK-0124 | 2026-02-17 | 2026-02-20 | 2026-02-24 | 3 | Crane | Tower Crane | TOW-13 | 25 | 14.8 | YST 17 | B | Assembly | Accommodation Module | Half Day (AM) | Night Shift (1900-0700) | Team Delta | Rigging Supervisor | High | Rescheduled | Original date conflicts with maintenance | Overcast | 4 | TRUE | 44 |  | 3 | No |  | No Conflict | Yes
BK-0125 | 2026-02-18 | 2026-02-24 | 2026-02-25 | 6 | MEWP | Boom Lift 20m | MEWP-16 |  |  | YST 03 | A | Testing | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | High | Rescheduled | Permit delay | Thunderstorm | 27 | FALSE | 22 |  | 3 | No |  | No Conflict | Yes
BK-0126 | 2026-02-22 | 2026-03-06 | 2026-03-13 | 12 | Forklift | Counterbalance Forklift | FLT-02 | 3 | 2.1 | YST D8 | C | Fabrication | Paint Drums | 10 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | High | Rescheduled | Material delivery delayed | Overcast | 14 | FALSE | 28 |  | 3 | No |  | No Conflict | Yes
BK-0127 | 2026-02-23 | 2026-03-03 |  | 8 | MEWP | Articulating Boom Lift 26m | MEWP-04 |  |  | YST 02 | E | Outfitting | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | High | Cancelled | Duplicate booking | High Wind | 35 | FALSE | 70 |  | 3 | No |  | No Conflict | Yes
BK-0128 | 2026-02-15 | 2026-02-21 |  | 6 | Crane | Mobile Crane | MOB-19 | 100 | 62.7 | YST 03 | A | Planning | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Medium | Completed |  | Clear | 14 | FALSE | 87 | On Time | 2 | No |  | No Conflict | Yes
BK-0129 | 2026-02-12 | 2026-02-14 |  | 2 | Crane | Crawler Crane | CRA-09 | 250 | 133.1 | YST 06 | D | Planning | Helideck Module | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Medium | Pending |  | Clear | 13 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0130 | 2026-02-11 | 2026-02-22 |  | 11 | Crane | Mobile Crane | MOB-18 | 100 | 49.6 | YST 02 | B | Fabrication | Turret Assembly | 7 Days | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | Medium | Cancelled | Material not ready | Clear | 10 | FALSE | 37 |  | 2 | No |  | No Conflict | Yes
BK-0131 | 2026-02-14 | 2026-02-18 | 2026-02-23 | 4 | Forklift | Telehandler Forklift | FLT-39 | 5 | 2.8 | YST 08 | C | Testing | Small Fittings Pallet | 3 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | Medium | Rescheduled | Permit delay | Partly Cloudy | 12 | TRUE | 40 |  | 2 | No |  | No Conflict | Yes
BK-0132 | 2026-02-23 | 2026-02-26 |  | 3 | Crane | Mobile Crane | MOB-16 | 75 | 41.7 | YST 05 | D | Assembly | Turret Assembly | 10 Days | Night Shift (1900-0700) | Team Gamma | Advanced Crane Operator | Medium | Rejected | Project schedule changed | Clear | 8 | TRUE | 66 |  | 2 | No |  | No Conflict | Yes
BK-0133 | 2026-02-15 | 2026-02-27 |  | 12 | Crane | Crawler Crane | CRA-16 | 50 | 27.5 | YST 07 | D | Planning | Workshop Equipment | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Cancelled | Material not ready | Partly Cloudy | 17 | FALSE | 54 |  | 3 | No |  | No Conflict | Yes
BK-0134 | 2026-02-02 | 2026-02-11 |  | 9 | Crane | Tower Crane | TOW-08 | 10 | 7.8 | YST 10 | F | Commissioning | Helideck Module | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | High | Pending |  | Overcast | 12 | FALSE | 20 |  | 3 | No |  | No Conflict | Yes
BK-0135 | 2026-02-04 | 2026-02-08 |  | 4 | MEWP | Boom Lift 20m | MEWP-12 |  |  | YST D3 | A | Outfitting | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Echo | MEWP Operator | High | Confirmed |  | Clear | 15 | FALSE | 45 |  | 3 | No |  | No Conflict | Yes
BK-0136 | 2026-02-04 | 2026-02-14 |  | 10 | Cometto | SPMT 16 Axle Lines | COM-08 |  |  | YST 05 | F | Outfitting | Mega Block Section | 5 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Completed |  | Partly Cloudy | 11 | FALSE | 85 | On Time | 2 | No |  | No Conflict | Yes
BK-0137 | 2026-02-28 | 2026-03-04 |  | 4 | Crane | Goliath Gantry Crane | GC-19 | 240 | 105 | YST 19 | B | Fabrication | Structural Steel Module | Full Day | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Completed |  | Overcast | 15 | FALSE | 96 | On Time | 2 | No |  | No Conflict | Yes
BK-0138 | 2026-02-19 | 2026-02-24 |  | 5 | Crane | Goliath Gantry Crane | GC-10 | 240 | 124 | YST 04 | D | Planning | Helideck Module | 3 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | Medium | Completed |  | Clear | 17 | FALSE | 78 | On Time | 2 | Yes | BK-0173 | Later Request - Reassigned | No
BK-0139 | 2026-02-13 | 2026-02-20 |  | 7 | Crane | Mobile Crane | MOB-10 | 50 | 25.3 | YST D8 | C | Planning | Turret Assembly | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Medium | Confirmed |  | Clear | 6 | FALSE | 48 |  | 2 | No |  | No Conflict | Yes
BK-0140 | 2026-02-19 | 2026-02-24 | 2026-02-28 | 5 | Crane | Workshop Crane | WOR-10 | 10 | 7.8 | YST 09 | A | Outfitting | Mooring Winch | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Rescheduled | Safety stand-down | Clear | 14 | FALSE | 51 |  | 3 | No |  | No Conflict | Yes
BK-0141 | 2026-02-23 | 2026-03-05 |  | 10 | MEWP | Scissor Lift 10m | MEWP-26 |  |  | YST 01 | D | Testing | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Completed |  | Overcast | 17 | FALSE | 47 | Delayed | 2 | No |  | No Conflict | Yes
BK-0142 | 2026-02-09 | 2026-02-18 |  | 9 | Forklift | Telehandler Forklift | FLT-35 | 3 | 2.5 | YST D5 | C | Planning | Timber Dunnage | Full Day | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Rejected | Crane already booked | Partly Cloudy | 13 | FALSE | 35 |  | 3 | No |  | No Conflict | Yes
BK-0143 | 2026-02-07 | 2026-02-17 |  | 10 | MEWP | Articulating Boom Lift 26m | MEWP-06 |  |  | YST D2 | E | Assembly | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Beta | Advanced Operator | High | Pending |  | Overcast | 7 | FALSE | 65 |  | 3 | No |  | No Conflict | Yes
BK-0144 | 2026-02-10 | 2026-02-14 | 2026-02-17 | 4 | Crane | Tower Crane | TOW-14 | 10 | 6.6 | YST 12 | B | Fabrication | Helideck Module | 7 Days | Night Shift (1900-0700) | Team Foxtrot | Heavy Lift Specialist | Medium | Rescheduled | Safety stand-down | Overcast | 9 | TRUE | 60 |  | 2 | No |  | No Conflict | Yes
BK-0145 | 2026-02-21 | 2026-02-26 |  | 5 | MEWP | Scissor Lift 10m | MEWP-17 |  |  | YST D1 | E | Planning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Completed |  | Heavy Rain | 12 | FALSE | 69 | Delayed | 2 | No |  | No Conflict | Yes
BK-0146 | 2026-02-23 | 2026-02-28 |  | 5 | Crane | Tower Crane | TOW-07 | 40 | 9.1 | YST 14 | E | Outfitting | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | Medium | Pending |  | Light Rain | 3 | FALSE | 49 |  | 2 | No |  | No Conflict | Yes
BK-0147 | 2026-02-01 | 2026-02-03 | 2026-02-06 | 2 | Forklift | Reach Forklift | FLT-13 | 3 | 1 | YST 01 | C | Planning | Scaffolding Materials | 14 Days | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Medium | Rescheduled | Project timeline shifted | Overcast | 10 | TRUE | 60 |  | 2 | No |  | No Conflict | Yes
BK-0148 | 2026-02-24 | 2026-03-04 |  | 8 | Crane | Workshop Crane | WOR-07 | 10 | 7.9 | YST 07 | A | Commissioning | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Beta | Advanced Crane Operator | Medium | Completed |  | Partly Cloudy | 5 | FALSE | 48 | On Time | 2 | No |  | No Conflict | Yes
BK-0149 | 2026-02-08 | 2026-02-13 |  | 5 | Cometto | Cometto MSPE 8 Axle Lines | COM-06 |  |  | YST 02 | A | Testing | Mega Block Section | 7 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | High | Cancelled | Project postponed | Overcast | 7 | FALSE | 60 |  | 3 | No |  | No Conflict | Yes
BK-0150 | 2026-02-24 | 2026-02-27 | 2026-02-28 | 3 | Crane | Workshop Crane | WOR-04 | 20 | 7 | YST 10 | C | Fabrication | Engine Module | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Rescheduled | Permit delay | Clear | 4 | TRUE | 64 |  | 2 | Yes | BK-0195 | Yielded to Higher Priority | No
BK-0151 | 2026-02-28 | 2026-03-10 |  | 10 | Forklift | Heavy Duty Forklift | FLT-19 | 15 | 12.5 | YST D4 | D | Commissioning | Consumables Pallet | 3 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | Medium | Confirmed |  | Overcast | 18 | FALSE | 63 |  | 2 | No |  | No Conflict | Yes
BK-0152 | 2026-02-11 | 2026-02-14 |  | 3 | Forklift | Reach Forklift | FLT-31 | 2.5 | 1.5 | YST 18 | B | Planning | PPE Supplies | 10 Days | Night Shift (1900-0700) | Team Alpha | Forklift Operator | High | Confirmed |  | Thunderstorm | 32 | FALSE | 72 |  | 3 | Yes | BK-0106 | Priority Override | Yes
BK-0153 | 2026-02-25 | 2026-03-02 | 2026-03-03 | 5 | Cometto | Cometto MSPE 8 Axle Lines | COM-09 |  |  | YST 18 | B | Testing | Jacket Structure | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Low | Rescheduled | Material delivery delayed | Partly Cloudy | 4 | FALSE | 35 |  | 1 | No |  | No Conflict | Yes
BK-0154 | 2026-02-08 | 2026-02-10 |  | 2 | Crane | Mobile Crane | MOB-06 | 25 | 7.5 | YST 05 | C | Testing | Workshop Equipment | Half Day (PM) | Night Shift (1900-0700) | Team Foxtrot | Basic Crane Operator | Low | Completed |  | Partly Cloudy | 10 | FALSE | 89 | Early | 1 | No |  | No Conflict | Yes
BK-0155 | 2026-02-24 | 2026-03-07 |  | 11 | Forklift | Counterbalance Forklift | FLT-18 | 5 | 2.6 | YST D6 | E | Assembly | Scaffolding Materials | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Completed |  | Clear | 7 | FALSE | 46 | Early | 3 | No |  | No Conflict | Yes
BK-0156 | 2026-02-22 | 2026-03-02 |  | 8 | Crane | Tower Crane | TOW-01 | 10 | 3.3 | YST 09 | A | Testing | Flare Tower Section | Full Day | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Urgent | Confirmed |  | Light Rain | 15 | FALSE | 98 |  | 4 | No |  | No Conflict | Yes
BK-0157 | 2026-02-24 | 2026-02-28 |  | 4 | Forklift | Telehandler Forklift | FLT-12 | 3 | 1.5 | YST 17 | D | Assembly | Pipe Bundles | Full Day | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Urgent | Confirmed |  | Light Rain | 11 | FALSE | 40 |  | 4 | No |  | No Conflict | Yes
BK-0158 | 2026-02-12 | 2026-02-15 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-15 |  |  | YST 08 | B | Fabrication | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | High | Pending |  | Clear | 15 | FALSE | 54 |  | 3 | No |  | No Conflict | Yes
BK-0159 | 2026-02-12 | 2026-02-19 |  | 7 | Cometto | Cometto MSPE 8 Axle Lines | COM-11 |  |  | YST 13 | B | Outfitting | Engine Module | 2 Days | Night Shift (1900-0700) | Team Gamma | MEWP Operator | Medium | Pending |  | Partly Cloudy | 3 | FALSE | 29 |  | 2 | No |  | No Conflict | Yes
BK-0160 | 2026-02-23 | 2026-02-27 |  | 4 | Crane | Goliath Gantry Crane | GC-16 | 600 | 276.6 | YST 04 | D | Planning | Turret Assembly | 2 Days | Night Shift (1900-0700) | Team Echo | Lifting Supervisor | Low | Confirmed |  | Overcast | 3 | FALSE | 55 |  | 1 | No |  | No Conflict | Yes
BK-0161 | 2026-02-10 | 2026-02-14 |  | 4 | Crane | Mobile Crane | MOB-09 | 75 | 29.1 | YST 06 | B | Planning | Mooring Winch | Full Day | Night Shift (1900-0700) | Team Beta | Basic Crane Operator | High | Pending |  | Clear | 16 | FALSE | 42 |  | 3 | No |  | No Conflict | Yes
BK-0162 | 2026-02-25 | 2026-02-28 | 2026-03-01 | 3 | Crane | Crawler Crane | CRA-10 | 50 | 21.9 | YST 02 | B | Planning | Structural Steel Module | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Rescheduled | Higher priority job took precedence | Overcast | 13 | TRUE | 31 |  | 2 | No |  | No Conflict | Yes
BK-0163 | 2026-02-13 | 2026-02-23 |  | 10 | MEWP | Boom Lift 20m | MEWP-15 |  |  | YST 04 | B | Fabrication | Personnel Access Work | Half Day (PM) | Night Shift (1900-0700) | Team Alpha | Advanced Operator | Low | Rejected | Crane already booked | Clear | 14 | FALSE | 36 |  | 1 | No |  | No Conflict | Yes
BK-0164 | 2026-02-27 | 2026-03-01 | 2026-03-03 | 2 | Forklift | Heavy Duty Forklift | FLT-06 | 25 | 19.8 | YST D6 | A | Fabrication | Welding Materials | 7 Days | Night Shift (1900-0700) | Team Gamma | Advanced Operator | Medium | Rescheduled | Original date conflicts with maintenance | Thunderstorm | 33 | FALSE | 47 |  | 2 | No |  | No Conflict | Yes
BK-0165 | 2026-02-12 | 2026-02-15 | 2026-02-22 | 3 | Crane | Crawler Crane | CRA-20 | 250 | 70.6 | YST 03 | D | Planning | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Medium | Rescheduled | Client request | Clear | 14 | TRUE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0166 | 2026-02-01 | 2026-02-15 |  | 14 | Forklift | Telehandler Forklift | FLT-23 | 7 | 2.3 | YST 18 | E | Fabrication | Small Fittings Pallet | 7 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Medium | Confirmed |  | Clear | 10 | FALSE | 73 |  | 2 | No |  | No Conflict | Yes
BK-0167 | 2026-02-12 | 2026-02-21 | 2026-02-24 | 9 | Forklift | Heavy Duty Forklift | FLT-18 | 10 | 5.1 | YST 08 | B | Testing | Valve Crates | 3 Days | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Low | Rescheduled | Project timeline shifted | Light Rain | 14 | TRUE | 57 |  | 1 | No |  | No Conflict | Yes
BK-0168 | 2026-02-26 | 2026-03-07 |  | 9 | Crane | Tower Crane | TOW-19 | 10 | 2.1 | YST 17 | A | Planning | Construction Materials | Half Day (PM) | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Medium | Confirmed |  | Clear | 9 | FALSE | 61 |  | 2 | No |  | No Conflict | Yes
BK-0169 | 2026-02-20 | 2026-02-23 |  | 3 | Crane | Workshop Crane | WOR-01 | 10 | 5.5 | YST 14 | C | Planning | Hull Block Section | Half Day (PM) | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | High | Rejected | Load exceeds crane capacity | Partly Cloudy | 14 | TRUE | 30 |  | 3 | No |  | No Conflict | Yes
BK-0170 | 2026-02-24 | 2026-03-08 |  | 12 | Forklift | Reach Forklift | FLT-15 | 2.5 | 2 | YST 06 | B | Fabrication | Bolt Pallets | 5 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | Medium | Cancelled | Budget constraint | Overcast | 14 | FALSE | 22 |  | 2 | No |  | No Conflict | Yes
BK-0171 | 2026-02-06 | 2026-02-13 | 2026-02-16 | 7 | Forklift | Heavy Duty Forklift | FLT-22 | 10 | 5.7 | YST 16 | A | Commissioning | Welding Materials | 5 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Rescheduled | Operator reassigned | Overcast | 12 | FALSE | 42 |  | 2 | No |  | No Conflict | Yes
BK-0172 | 2026-02-26 | 2026-02-28 |  | 2 | Crane | Mobile Crane | MOB-14 | 100 | 29.8 | YST 07 | E | Commissioning | Structural Steel Module | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | Medium | Rejected | Crane under scheduled maintenance | Light Rain | 9 | TRUE | 40 |  | 2 | No |  | No Conflict | Yes
BK-0173 | 2026-02-09 | 2026-02-22 | 2026-02-24 | 13 | Crane | Goliath Gantry Crane | GC-10 | 400 | 225.8 | YST 01 | D | Commissioning | Turret Assembly | 3 Days | Night Shift (1900-0700) | Team Alpha | Heavy Lift Specialist | Medium | Rescheduled | Original date conflicts with maintenance | Clear | 7 | TRUE | 33 |  | 2 | Yes | BK-0138 | First-Come-First-Served | Yes
BK-0174 | 2026-02-14 | 2026-02-22 |  | 8 | Cometto | SPMT 16 Axle Lines | COM-05 |  |  | YST 18 | A | Assembly | Mega Block Section | Full Day | Day Shift (0700-1900) | Team Echo | Basic Operator | Medium | Completed |  | Clear | 4 | FALSE | 82 | Delayed | 2 | No |  | No Conflict | Yes
BK-0175 | 2026-02-16 | 2026-02-19 |  | 3 | Crane | Goliath Gantry Crane | GC-10 | 300 | 219.4 | YST 01 | F | Testing | Mooring Winch | Full Day | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Urgent | Completed |  | Partly Cloudy | 13 | FALSE | 68 | On Time | 4 | No |  | No Conflict | Yes
BK-0176 | 2026-02-15 | 2026-02-21 |  | 6 | Crane | Crawler Crane | CRA-04 | 50 | 34.6 | YST 03 | B | Testing | Helideck Module | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Medium | Rejected | Project schedule changed | Clear | 14 | FALSE | 50 |  | 2 | No |  | No Conflict | Yes
BK-0177 | 2026-02-19 | 2026-03-02 |  | 11 | MEWP | Scissor Lift 10m | MEWP-29 |  |  | YST D1 | F | Testing | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Urgent | Rejected | Insufficient lead time | Clear | 16 | FALSE | 32 |  | 4 | Yes | BK-0190 | Priority Override | Yes
BK-0178 | 2026-02-05 | 2026-02-06 |  | 1 | Crane | Workshop Crane | WOR-05 | 20 | 14.3 | YST 10 | D | Testing | Flare Tower Section | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Urgent | Confirmed |  | Partly Cloudy | 12 | FALSE | 98 |  | 4 | No |  | No Conflict | Yes
BK-0179 | 2026-02-28 | 2026-03-01 |  | 1 | Cometto | SPMT 24 Axle Lines | COM-03 |  |  | YST 02 | A | Assembly | Offshore Platform Topside | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Urgent | Pending |  | Heavy Rain | 21 | FALSE | 36 |  | 4 | No |  | No Conflict | Yes
BK-0180 | 2026-02-13 | 2026-02-21 |  | 8 | MEWP | Telescopic Boom Lift 30m | MEWP-06 |  |  | YST 02 | D | Assembly | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Echo | Forklift Operator | High | Completed |  | Overcast | 3 | FALSE | 98 | On Time | 3 | No |  | No Conflict | Yes
BK-0181 | 2026-02-12 | 2026-02-13 |  | 1 | Forklift | Telehandler Forklift | FLT-07 | 5 | 2.1 | YST 09 | C | Assembly | Small Fittings Pallet | 10 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Urgent | Completed |  | Overcast | 4 | FALSE | 92 | On Time | 4 | No |  | No Conflict | Yes
BK-0182 | 2026-02-16 | 2026-02-25 |  | 9 | Forklift | Counterbalance Forklift | FLT-33 | 3 | 1 | YST 03 | B | Fabrication | Electrical Cables | 2 Days | Night Shift (1900-0700) | Team Echo | Basic Operator | Urgent | Confirmed |  | Light Rain | 9 | FALSE | 63 |  | 4 | No |  | No Conflict | Yes
BK-0183 | 2026-02-23 | 2026-02-26 |  | 3 | Crane | Mobile Crane | MOB-04 | 100 | 29.8 | YST D8 | D | Testing | Riser Assembly | 5 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | High | Confirmed |  | Overcast | 13 | FALSE | 87 |  | 3 | No |  | No Conflict | Yes
BK-0184 | 2026-02-27 | 2026-03-07 |  | 8 | Crane | Mobile Crane | MOB-19 | 25 | 18 | YST 03 | C | Commissioning | Flare Tower Section | 5 Days | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | High | Cancelled | Client cancelled | Partly Cloudy | 2 | FALSE | 50 |  | 3 | No |  | No Conflict | Yes
BK-0185 | 2026-02-05 | 2026-02-12 |  | 7 | MEWP | Scissor Lift 10m | MEWP-09 |  |  | YST 08 | D | Outfitting | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Urgent | Cancelled | Material not ready | Heavy Rain | 24 | FALSE | 39 |  | 4 | No |  | No Conflict | Yes
BK-0186 | 2026-02-22 | 2026-02-28 |  | 6 | MEWP | Scissor Lift 10m | MEWP-17 |  |  | YST 01 | C | Assembly | Personnel Access Work | 14 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | High | Pending |  | Overcast | 17 | FALSE | 37 |  | 3 | No |  | No Conflict | Yes
BK-0187 | 2026-02-21 | 2026-02-25 |  | 4 | Crane | Workshop Crane | WOR-17 | 20 | 16 | YST 10 | B | Commissioning | Structural Steel Module | 5 Days | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Medium | Completed |  | Clear | 17 | FALSE | 66 | On Time | 2 | No |  | No Conflict | Yes
BK-0188 | 2026-02-24 | 2026-02-25 |  | 1 | Cometto | Cometto Eco500 12 Axle Lines | COM-11 |  |  | YST 13 | B | Commissioning | Hull Block Section | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Completed |  | Heavy Rain | 15 | FALSE | 70 | On Time | 2 | No |  | No Conflict | Yes
BK-0189 | 2026-02-09 | 2026-02-17 |  | 8 | MEWP | Boom Lift 20m | MEWP-21 |  |  | YST 11 | C | Assembly | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Urgent | Completed |  | Clear | 11 | FALSE | 47 | On Time | 4 | Yes | BK-0110 | Priority Override | Yes
BK-0190 | 2026-02-28 | 2026-03-07 |  | 7 | MEWP | Scissor Lift 10m | MEWP-29 |  |  | YST D4 | A | Fabrication | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Medium | Completed |  | Clear | 8 | FALSE | 76 | Early | 2 | Yes | BK-0177 | Yielded to Higher Priority | No
BK-0191 | 2026-02-15 | 2026-02-18 |  | 3 | Forklift | Heavy Duty Forklift | FLT-12 | 10 | 7.7 | YST 16 | B | Testing | Paint Drums | 2 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Rejected | Insufficient lead time | Light Rain | 17 | FALSE | 60 |  | 2 | No |  | No Conflict | Yes
BK-0192 | 2026-02-14 | 2026-02-19 |  | 5 | Forklift | Reach Forklift | FLT-24 | 1.5 | 0.7 | YST 02 | F | Commissioning | Tool Containers | 10 Days | Night Shift (1900-0700) | Team Echo | Basic Operator | Medium | Cancelled | Budget constraint | Clear | 13 | FALSE | 57 |  | 2 | No |  | No Conflict | Yes
BK-0193 | 2026-02-10 | 2026-02-13 |  | 3 | Forklift | Telehandler Forklift | FLT-28 | 5 | 1.6 | YST 15 | B | Fabrication | Paint Drums | 7 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | Urgent | Completed |  | High Wind | 37 | FALSE | 48 | On Time | 4 | No |  | No Conflict | Yes
BK-0194 | 2026-02-01 | 2026-02-08 |  | 7 | Crane | Crawler Crane | CRA-09 | 50 | 22.5 | YST 07 | F | Planning | Riser Assembly | 5 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Urgent | Cancelled | Budget constraint | Clear | 5 | FALSE | 36 |  | 4 | No |  | No Conflict | Yes
BK-0195 | 2026-02-16 | 2026-02-24 |  | 8 | Crane | Workshop Crane | WOR-04 | 10 | 3.7 | YST 13 | A | Testing | Anchor Chain | 5 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | High | Completed |  | Overcast | 5 | FALSE | 71 | On Time | 3 | Yes | BK-0150 | Priority Override | Yes
BK-0196 | 2026-02-07 | 2026-02-16 |  | 9 | Forklift | Heavy Duty Forklift | FLT-19 | 20 | 16.9 | YST D3 | B | Planning | Scaffolding Materials | Full Day | Day Shift (0700-1900) | Team Beta | MEWP Operator | High | Completed |  | Clear | 4 | FALSE | 82 | On Time | 3 | No |  | No Conflict | Yes
BK-0197 | 2026-02-03 | 2026-02-12 |  | 9 | Crane | Workshop Crane | WOR-08 | 10 | 6.8 | YST 12 | B | Planning | Workshop Equipment | 2 Days | Night Shift (1900-0700) | Team Gamma | Advanced Crane Operator | Medium | Confirmed |  | Heavy Rain | 21 | FALSE | 87 |  | 2 | No |  | No Conflict | Yes
BK-0198 | 2026-02-04 | 2026-02-06 |  | 2 | Forklift | Counterbalance Forklift | FLT-11 | 2.5 | 1.4 | YST D8 | C | Assembly | Welding Materials | 2 Days | Night Shift (1900-0700) | Team Echo | Advanced Operator | Medium | Cancelled | Material not ready | Clear | 14 | FALSE | 64 |  | 2 | No |  | No Conflict | Yes
BK-0199 | 2026-03-26 | 2026-03-31 |  | 5 | Forklift | Heavy Duty Forklift | FLT-11 | 10 | 6.7 | YST 05 | B | Testing | Pipe Bundles | Half Day (PM) | Night Shift (1900-0700) | Team Delta | MEWP Operator | High | Cancelled | Project postponed | Partly Cloudy | 13 | FALSE | 50 |  | 3 | No |  | No Conflict | Yes
BK-0200 | 2026-03-30 | 2026-04-05 |  | 6 | Forklift | Reach Forklift | FLT-21 | 1.5 | 0.9 | YST 03 | E | Fabrication | Gasket Boxes | Half Day (AM) | Night Shift (1900-0700) | Team Echo | Forklift Operator | High | Pending |  | High Wind | 35 | FALSE | 59 |  | 3 | No |  | No Conflict | Yes
BK-0201 | 2026-03-04 | 2026-03-09 |  | 5 | Cometto | SPMT 24 Axle Lines | COM-03 |  |  | YST 13 | B | Testing | Offshore Platform Topside | 5 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Low | Cancelled | Client cancelled | Light Rain | 17 | FALSE | 68 |  | 1 | No |  | No Conflict | Yes
BK-0202 | 2026-03-16 | 2026-03-20 |  | 4 | Crane | Crawler Crane | CRA-18 | 50 | 23.4 | YST D1 | E | Outfitting | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Low | Completed |  | Clear | 17 | FALSE | 71 | Delayed | 1 | No |  | No Conflict | Yes
BK-0203 | 2026-03-01 | 2026-03-03 |  | 2 | Crane | Tower Crane | TOW-20 | 10 | 6.9 | YST 10 | D | Assembly | Helideck Module | 10 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | High | Cancelled | Duplicate booking | Partly Cloudy | 3 | FALSE | 55 |  | 3 | No |  | No Conflict | Yes
BK-0204 | 2026-03-25 | 2026-04-01 |  | 7 | MEWP | Articulating Boom Lift 26m | MEWP-04 |  |  | YST D3 | C | Testing | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Rejected | Insufficient lead time | Partly Cloudy | 5 | FALSE | 65 |  | 2 | No |  | No Conflict | Yes
BK-0205 | 2026-03-24 | 2026-04-01 |  | 8 | Crane | Tower Crane | TOW-13 | 15 | 9.9 | YST 14 | D | Planning | Engine Module | Full Day | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | High | Confirmed |  | Thunderstorm | 23 | FALSE | 82 |  | 3 | No |  | No Conflict | Yes
BK-0206 | 2026-03-19 | 2026-04-01 |  | 13 | Crane | Mobile Crane | MOB-02 | 25 | 6.6 | YST D1 | B | Commissioning | Turret Assembly | 3 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Medium | Pending |  | Overcast | 6 | FALSE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0207 | 2026-03-29 | 2026-04-02 |  | 4 | Forklift | Reach Forklift | FLT-22 | 2 | 1.5 | YST 09 | F | Testing | Consumables Pallet | 10 Days | Day Shift (0700-1900) | Team Beta | MEWP Operator | Medium | Cancelled | Project postponed | Clear | 12 | FALSE | 32 |  | 2 | No |  | No Conflict | Yes
BK-0208 | 2026-03-07 | 2026-03-14 |  | 7 | Crane | Crawler Crane | CRA-06 | 100 | 60.5 | YST D4 | E | Outfitting | Workshop Equipment | 3 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | High | Rejected | Project schedule changed | Overcast | 15 | TRUE | 47 |  | 3 | No |  | No Conflict | Yes
BK-0209 | 2026-03-26 | 2026-03-27 |  | 1 | Crane | Mobile Crane | MOB-02 | 50 | 16.1 | YST 01 | B | Planning | Workshop Equipment | Full Day | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | Urgent | Cancelled | Duplicate booking | Overcast | 11 | FALSE | 48 |  | 4 | No |  | No Conflict | Yes
BK-0210 | 2026-03-04 | 2026-03-11 |  | 7 | Cometto | Cometto Eco500 12 Axle Lines | COM-07 |  |  | YST 19 | D | Outfitting | Jacket Structure | Full Day | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Medium | Cancelled | Client cancelled | Partly Cloudy | 12 | FALSE | 20 |  | 2 | No |  | No Conflict | Yes
BK-0211 | 2026-03-24 | 2026-03-28 |  | 4 | MEWP | Telescopic Boom Lift 30m | MEWP-30 |  |  | YST 08 | E | Fabrication | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | High | Pending |  | Light Rain | 8 | FALSE | 31 |  | 3 | No |  | No Conflict | Yes
BK-0212 | 2026-03-22 | 2026-03-24 |  | 2 | Forklift | Counterbalance Forklift | FLT-18 | 7 | 2.7 | YST 02 | D | Commissioning | Scaffolding Materials | 3 Days | Day Shift (0700-1900) | Team Echo | Advanced Operator | High | Confirmed |  | High Wind | 26 | FALSE | 43 |  | 3 | No |  | No Conflict | Yes
BK-0213 | 2026-03-25 | 2026-04-06 |  | 12 | MEWP | Articulating Boom Lift 26m | MEWP-26 |  |  | YST D4 | B | Testing | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Completed |  | Clear | 18 | FALSE | 74 | Delayed | 2 | No |  | No Conflict | Yes
BK-0214 | 2026-03-03 | 2026-03-07 |  | 4 | Forklift | Telehandler Forklift | FLT-14 | 5 | 2.8 | YST 12 | F | Planning | Electrical Cables | 10 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Urgent | Rejected | Safety inspection required first | Clear | 13 | FALSE | 35 |  | 4 | No |  | No Conflict | Yes
BK-0215 | 2026-03-31 | 2026-04-01 |  | 1 | Forklift | Reach Forklift | FLT-35 | 1.5 | 1.3 | YST 13 | E | Outfitting | Gasket Boxes | 5 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Completed |  | Partly Cloudy | 11 | FALSE | 72 | On Time | 3 | No |  | No Conflict | Yes
BK-0216 | 2026-03-04 | 2026-03-07 |  | 3 | Forklift | Counterbalance Forklift | FLT-28 | 2.5 | 1.9 | YST 07 | D | Commissioning | Tool Containers | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Urgent | Cancelled | Material not ready | Light Rain | 4 | FALSE | 65 |  | 4 | No |  | No Conflict | Yes
BK-0217 | 2026-03-11 | 2026-03-12 |  | 1 | Crane | Goliath Gantry Crane | GC-20 | 300 | 156.3 | YST 19 | D | Assembly | Engine Module | 5 Days | Night Shift (1900-0700) | Team Delta | Rigging Supervisor | Medium | Cancelled | Budget constraint | Clear | 5 | FALSE | 24 |  | 2 | No |  | No Conflict | Yes
BK-0218 | 2026-03-25 | 2026-04-03 | 2026-04-10 | 9 | Crane | Level Luffing Crane | LLC 10 | 50 | 24.2 | YST D1 | D | Outfitting | Engine Module | 5 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Medium | Rescheduled | Project timeline shifted | Light Rain | 2 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0219 | 2026-03-28 | 2026-04-04 |  | 7 | Forklift | Heavy Duty Forklift | FLT-01 | 20 | 9.7 | YST D2 | D | Testing | Bolt Pallets | 3 Days | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Low | Pending |  | Partly Cloudy | 4 | FALSE | 66 |  | 1 | No |  | No Conflict | Yes
BK-0220 | 2026-03-12 | 2026-03-15 |  | 3 | Forklift | Heavy Duty Forklift | FLT-40 | 15 | 7.1 | YST 06 | A | Testing | Valve Crates | 5 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | High | Pending |  | Partly Cloudy | 4 | FALSE | 26 |  | 3 | Yes | BK-0297 | Priority Override | Yes
BK-0221 | 2026-03-07 | 2026-03-15 | 2026-03-22 | 8 | MEWP | Articulating Boom Lift 26m | MEWP-05 |  |  | YST 12 | C | Outfitting | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | High | Rescheduled | Project timeline shifted | Partly Cloudy | 11 | FALSE | 43 |  | 3 | No |  | No Conflict | Yes
BK-0222 | 2026-03-11 | 2026-03-24 | 2026-03-31 | 13 | Crane | Crawler Crane | CRA-14 | 100 | 49.2 | YST 04 | D | Outfitting | Turret Assembly | Full Day | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | High | Rescheduled | Permit delay | Partly Cloudy | 11 | TRUE | 37 |  | 3 | Yes | BK-0305 | Priority Override | Yes
BK-0223 | 2026-03-27 | 2026-03-30 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-24 |  |  | YST 03 | E | Outfitting | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Rejected | Project schedule changed | Light Rain | 8 | TRUE | 54 |  | 3 | No |  | No Conflict | Yes
BK-0224 | 2026-03-16 | 2026-03-24 |  | 8 | Crane | Mobile Crane | MOB-10 | 50 | 32.7 | YST D7 | F | Fabrication | Turret Assembly | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Pending |  | Light Rain | 7 | FALSE | 30 |  | 2 | Yes | BK-0287 | Yielded to Higher Priority | No
BK-0225 | 2026-03-06 | 2026-03-13 |  | 7 | MEWP | Boom Lift 20m | MEWP-12 |  |  | YST D4 | A | Commissioning | Personnel Access Work | Half Day (AM) | Night Shift (1900-0700) | Team Beta | Advanced Operator | Low | Completed |  | Clear | 13 | FALSE | 98 | On Time | 1 | No |  | No Conflict | Yes
BK-0226 | 2026-03-02 | 2026-03-03 |  | 1 | MEWP | Scissor Lift 10m | MEWP-27 |  |  | YST 09 | C | Testing | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Cancelled | Material not ready | Overcast | 4 | FALSE | 34 |  | 2 | No |  | No Conflict | Yes
BK-0227 | 2026-03-17 | 2026-03-22 |  | 5 | Forklift | Telehandler Forklift | FLT-39 | 7 | 2.8 | YST D6 | F | Assembly | Small Fittings Pallet | Half Day (AM) | Night Shift (1900-0700) | Team Delta | Forklift Operator | Medium | Confirmed |  | Clear | 7 | FALSE | 92 |  | 2 | No |  | No Conflict | Yes
BK-0228 | 2026-03-04 | 2026-03-12 |  | 8 | Crane | Crawler Crane | CRA-16 | 50 | 14 | YST 08 | A | Fabrication | Workshop Equipment | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | High | Confirmed |  | Overcast | 7 | FALSE | 97 |  | 3 | No |  | No Conflict | Yes
BK-0229 | 2026-03-19 | 2026-03-22 |  | 3 | Crane | Goliath Gantry Crane | GC-20 | 600 | 432.2 | YST 04 | A | Fabrication | Construction Materials | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Crane Operator | High | Completed |  | Partly Cloudy | 17 | FALSE | 93 | On Time | 3 | No |  | No Conflict | Yes
BK-0230 | 2026-03-05 | 2026-03-14 |  | 9 | Forklift | Heavy Duty Forklift | FLT-30 | 20 | 15.9 | YST 06 | B | Testing | Paint Drums | 3 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Confirmed |  | Heavy Rain | 23 | FALSE | 51 |  | 2 | No |  | No Conflict | Yes
BK-0231 | 2026-03-16 | 2026-03-27 | 2026-03-29 | 11 | MEWP | Scissor Lift 10m | MEWP-16 |  |  | YST 03 | F | Commissioning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Echo | Advanced Operator | High | Rescheduled | Original date conflicts with maintenance | Partly Cloudy | 15 | FALSE | 47 |  | 3 | No |  | No Conflict | Yes
BK-0232 | 2026-03-31 | 2026-04-10 |  | 10 | Forklift | Reach Forklift | FLT-28 | 2.5 | 0.8 | YST 19 | E | Testing | Insulation Materials | Half Day (PM) | Day Shift (0700-1900) | Team Beta | Forklift Operator | Urgent | Confirmed |  | Partly Cloudy | 8 | FALSE | 40 |  | 4 | No |  | No Conflict | Yes
BK-0233 | 2026-03-19 | 2026-03-25 |  | 6 | MEWP | Telescopic Boom Lift 30m | MEWP-23 |  |  | YST 07 | C | Assembly | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Cancelled | Budget constraint | Heavy Rain | 23 | FALSE | 37 |  | 2 | No |  | No Conflict | Yes
BK-0234 | 2026-03-22 | 2026-03-27 |  | 5 | Crane | Tower Crane | TOW-18 | 40 | 25.9 | YST 12 | D | Commissioning | Pipe Spool | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Rejected | Insufficient lead time | Clear | 5 | TRUE | 52 |  | 3 | Yes | BK-0265 | Priority Override | Yes
BK-0235 | 2026-03-13 | 2026-03-22 |  | 9 | Forklift | Counterbalance Forklift | FLT-06 | 3 | 2.2 | YST 13 | B | Assembly | Steel Plates | 5 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Confirmed |  | Clear | 3 | FALSE | 65 |  | 2 | No |  | No Conflict | Yes
BK-0236 | 2026-03-20 | 2026-03-28 |  | 8 | Crane | Tower Crane | TOW-16 | 10 | 5.1 | YST 12 | B | Planning | Workshop Equipment | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Urgent | Pending |  | Light Rain | 18 | FALSE | 30 |  | 4 | No |  | No Conflict | Yes
BK-0237 | 2026-03-22 | 2026-03-23 |  | 1 | Crane | Level Luffing Crane | LLC 16A | 40 | 21.2 | YST 03 | F | Commissioning | Accommodation Module | 2 Days | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | High | Pending |  | Clear | 4 | FALSE | 55 |  | 3 | No |  | No Conflict | Yes
BK-0238 | 2026-03-30 | 2026-04-06 |  | 7 | Crane | Crawler Crane | CRA-15 | 100 | 76.8 | YST D2 | E | Planning | Mega Block Section | 7 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | Medium | Pending |  | Partly Cloudy | 12 | FALSE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0239 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 7 | Forklift | Telehandler Forklift | FLT-16 | 7 | 3.7 | YST 13 | A | Outfitting | Small Fittings Pallet | 5 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | High | Rescheduled | Operator reassigned | Clear | 4 | FALSE | 34 |  | 3 | No |  | No Conflict | Yes
BK-0240 | 2026-03-11 | 2026-03-16 | 2026-03-18 | 5 | Crane | Tower Crane | TOW-10 | 10 | 3.1 | YST 16 | D | Assembly | Mega Block Section | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | Low | Rescheduled | Operator reassigned | Partly Cloudy | 10 | FALSE | 32 |  | 1 | No |  | No Conflict | Yes
BK-0241 | 2026-03-24 | 2026-03-27 |  | 3 | Forklift | Telehandler Forklift | FLT-08 | 4 | 2.7 | YST D5 | E | Planning | Insulation Materials | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Medium | Confirmed |  | Light Rain | 13 | FALSE | 96 |  | 2 | No |  | No Conflict | Yes
BK-0242 | 2026-03-29 | 2026-04-05 |  | 7 | Crane | Goliath Gantry Crane | GC-14 | 600 | 429.7 | YST 04 | E | Planning | Anchor Chain | 5 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | High | Completed |  | Partly Cloudy | 14 | FALSE | 69 | Early | 3 | No |  | No Conflict | Yes
BK-0243 | 2026-03-23 | 2026-03-29 |  | 6 | Crane | Level Luffing Crane | LLC 19 | 30 | 12.6 | YST 07 | C | Outfitting | Anchor Chain | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Medium | Completed |  | High Wind | 35 | FALSE | 53 | On Time | 2 | No |  | No Conflict | Yes
BK-0244 | 2026-03-25 | 2026-03-30 |  | 5 | Forklift | Telehandler Forklift | FLT-37 | 7 | 4.1 | YST 06 | D | Outfitting | Welding Materials | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Completed |  | Clear | 6 | FALSE | 66 | On Time | 2 | No |  | No Conflict | Yes
BK-0245 | 2026-03-29 | 2026-04-08 |  | 10 | MEWP | Articulating Boom Lift 26m | MEWP-10 |  |  | YST D4 | A | Fabrication | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Medium | Cancelled | Client cancelled | Light Rain | 17 | FALSE | 48 |  | 2 | No |  | No Conflict | Yes
BK-0246 | 2026-03-24 | 2026-03-28 |  | 4 | Crane | Tower Crane | TOW-14 | 25 | 10.3 | YST 17 | F | Testing | Hull Block Section | Half Day (PM) | Night Shift (1900-0700) | Team Echo | Heavy Lift Specialist | Medium | Pending |  | Clear | 11 | FALSE | 51 |  | 2 | No |  | No Conflict | Yes
BK-0247 | 2026-03-25 | 2026-04-03 |  | 9 | Forklift | Reach Forklift | FLT-11 | 2.5 | 1.2 | YST 15 | A | Planning | Welding Materials | 3 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | High | Pending |  | Clear | 9 | FALSE | 65 |  | 3 | No |  | No Conflict | Yes
BK-0248 | 2026-03-09 | 2026-03-16 |  | 7 | Crane | Mobile Crane | MOB-15 | 75 | 24.5 | YST D7 | C | Commissioning | Transformer Unit | 2 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Medium | Completed |  | Overcast | 4 | FALSE | 46 | On Time | 2 | No |  | No Conflict | Yes
BK-0249 | 2026-03-29 | 2026-04-04 |  | 6 | Crane | Mobile Crane | MOB-20 | 25 | 12.9 | YST 02 | C | Outfitting | Accommodation Module | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Medium | Completed |  | Overcast | 6 | FALSE | 42 | Delayed | 2 | No |  | No Conflict | Yes
BK-0250 | 2026-03-28 | 2026-04-09 |  | 12 | Forklift | Reach Forklift | FLT-09 | 2.5 | 1.5 | YST 18 | F | Commissioning | Timber Dunnage | 10 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | High | Completed |  | Heavy Rain | 23 | FALSE | 59 | Early | 3 | No |  | No Conflict | Yes
BK-0251 | 2026-03-16 | 2026-03-23 |  | 7 | Forklift | Reach Forklift | FLT-17 | 2.5 | 1.8 | YST 12 | C | Assembly | Scaffolding Materials | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Advanced Operator | High | Rejected | Permit not approved | Partly Cloudy | 2 | TRUE | 69 |  | 3 | No |  | No Conflict | Yes
BK-0252 | 2026-03-14 | 2026-03-23 |  | 9 | MEWP | Scissor Lift 10m | MEWP-07 |  |  | YST 12 | F | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Medium | Cancelled | Material not ready | Light Rain | 9 | FALSE | 60 |  | 2 | Yes | BK-0301 | Yielded to Higher Priority | No
BK-0253 | 2026-03-08 | 2026-03-14 |  | 6 | Forklift | Telehandler Forklift | FLT-27 | 5 | 2.1 | YST D1 | E | Outfitting | Gasket Boxes | Full Day | Day Shift (0700-1900) | Team Beta | Basic Operator | Medium | Cancelled | Client cancelled | Clear | 17 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0254 | 2026-03-01 | 2026-03-04 |  | 3 | Crane | Crawler Crane | CRA-01 | 100 | 39.8 | YST D4 | D | Assembly | Mooring Winch | Full Day | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Completed |  | Partly Cloudy | 3 | FALSE | 49 | On Time | 2 | No |  | No Conflict | Yes
BK-0255 | 2026-03-25 | 2026-03-30 |  | 5 | MEWP | Boom Lift 20m | MEWP-29 |  |  | YST 07 | B | Outfitting | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Rejected | Crane under scheduled maintenance | Light Rain | 16 | TRUE | 67 |  | 2 | No |  | No Conflict | Yes
BK-0256 | 2026-03-25 | 2026-03-27 |  | 2 | Cometto | Cometto Eco500 12 Axle Lines | COM-11 |  |  | YST 15 | E | Testing | Offshore Platform Topside | 10 Days | Night Shift (1900-0700) | Team Beta | Forklift Operator | High | Confirmed |  | Clear | 17 | FALSE | 52 |  | 3 | No |  | No Conflict | Yes
BK-0257 | 2026-03-12 | 2026-03-23 |  | 11 | Forklift | Heavy Duty Forklift | FLT-21 | 10 | 7.1 | YST 08 | A | Planning | Scaffolding Materials | Half Day (AM) | Night Shift (1900-0700) | Team Echo | Basic Operator | Medium | Rejected | Crane already booked | Overcast | 17 | TRUE | 51 |  | 2 | No |  | No Conflict | Yes
BK-0258 | 2026-03-03 | 2026-03-11 |  | 8 | Crane | Workshop Crane | WOR-05 | 10 | 6.4 | YST 02 | E | Commissioning | Pipe Spool | 5 Days | Night Shift (1900-0700) | Team Beta | Basic Crane Operator | Medium | Completed |  | Light Rain | 16 | FALSE | 64 | On Time | 2 | No |  | No Conflict | Yes
BK-0259 | 2026-03-05 | 2026-03-09 |  | 4 | Crane | Workshop Crane | WOR-16 | 20 | 5.9 | YST 13 | E | Testing | Transformer Unit | Full Day | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Medium | Completed |  | Clear | 18 | FALSE | 56 | Delayed | 2 | No |  | No Conflict | Yes
BK-0260 | 2026-03-15 | 2026-03-16 |  | 1 | MEWP | Telescopic Boom Lift 30m | MEWP-29 |  |  | YST 06 | F | Testing | Personnel Access Work | Half Day (AM) | Night Shift (1900-0700) | Team Echo | Forklift Operator | Medium | Cancelled | Material not ready | Light Rain | 8 | FALSE | 69 |  | 2 | No |  | No Conflict | Yes
BK-0261 | 2026-03-18 | 2026-03-21 |  | 3 | Crane | Mobile Crane | MOB-17 | 75 | 40.7 | YST 02 | A | Outfitting | Engine Module | 3 Days | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Confirmed |  | Clear | 3 | FALSE | 82 |  | 2 | No |  | No Conflict | Yes
BK-0262 | 2026-03-16 | 2026-03-22 | 2026-03-28 | 6 | Cometto | SPMT 16 Axle Lines | COM-04 |  |  | YST 01 | A | Outfitting | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | High | Rescheduled | Material delivery delayed | Light Rain | 3 | FALSE | 70 |  | 3 | No |  | No Conflict | Yes
BK-0263 | 2026-03-02 | 2026-03-12 |  | 10 | Crane | Level Luffing Crane | LLC 07 | 30 | 16.1 | YST 10 | B | Testing | Engine Module | 10 Days | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Completed |  | Overcast | 7 | FALSE | 87 | On Time | 2 | No |  | No Conflict | Yes
BK-0264 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 7 | Cometto | SPMT 24 Axle Lines | COM-03 |  |  | YST 02 | D | Assembly | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Rescheduled | Material delivery delayed | Thunderstorm | 30 | FALSE | 47 |  | 2 | No |  | No Conflict | Yes
BK-0265 | 2026-03-24 | 2026-03-28 |  | 4 | Crane | Tower Crane | TOW-18 | 15 | 3.1 | YST D2 | F | Planning | Helideck Module | 7 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Medium | Completed |  | High Wind | 44 | FALSE | 96 | On Time | 2 | Yes | BK-0234 | Yielded to Higher Priority | No
BK-0266 | 2026-03-10 | 2026-03-24 |  | 14 | Crane | Crawler Crane | CRA-09 | 50 | 17.9 | YST D4 | A | Outfitting | Flare Tower Section | 7 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Urgent | Confirmed |  | Partly Cloudy | 6 | FALSE | 55 |  | 4 | No |  | No Conflict | Yes
BK-0267 | 2026-03-08 | 2026-03-12 |  | 4 | Crane | Tower Crane | TOW-07 | 40 | 22.3 | YST D8 | F | Commissioning | Riser Assembly | 5 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Medium | Rejected | Safety inspection required first | Overcast | 5 | FALSE | 69 |  | 2 | No |  | No Conflict | Yes
BK-0268 | 2026-03-02 | 2026-03-14 |  | 12 | Crane | Mobile Crane | MOB-08 | 100 | 52.4 | YST 02 | A | Assembly | Flare Tower Section | 5 Days | Night Shift (1900-0700) | Team Alpha | Basic Crane Operator | High | Cancelled | Budget constraint | Partly Cloudy | 12 | FALSE | 64 |  | 3 | No |  | No Conflict | Yes
BK-0269 | 2026-03-08 | 2026-03-11 |  | 3 | Cometto | SPMT 24 Axle Lines | COM-10 |  |  | YST 15 | C | Planning | Jacket Structure | 3 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | High | Confirmed |  | Partly Cloudy | 3 | FALSE | 56 |  | 3 | No |  | No Conflict | Yes
BK-0270 | 2026-03-03 | 2026-03-08 |  | 5 | Crane | Workshop Crane | WOR-18 | 10 | 3.6 | YST 08 | F | Testing | Mooring Winch | Full Day | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Medium | Cancelled | Budget constraint | Clear | 4 | FALSE | 25 |  | 2 | No |  | No Conflict | Yes
BK-0271 | 2026-03-04 | 2026-03-12 |  | 8 | Crane | Crawler Crane | CRA-20 | 100 | 75.5 | YST 06 | D | Testing | Pipe Spool | 3 Days | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | Urgent | Cancelled | Duplicate booking | Clear | 3 | FALSE | 29 |  | 4 | No |  | No Conflict | Yes
BK-0272 | 2026-03-25 | 2026-04-02 |  | 8 | Crane | Workshop Crane | WOR-05 | 10 | 3.3 | YST 11 | C | Outfitting | Construction Materials | 7 Days | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | Medium | Rejected | Weather conditions unsafe | Partly Cloudy | 12 | FALSE | 68 |  | 2 | No |  | No Conflict | Yes
BK-0273 | 2026-03-09 | 2026-03-16 |  | 7 | MEWP | Boom Lift 20m | MEWP-13 |  |  | YST 01 | B | Commissioning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Confirmed |  | Overcast | 3 | FALSE | 40 |  | 2 | Yes | BK-0283 | First-Come-First-Served | Yes
BK-0274 | 2026-03-03 | 2026-03-08 |  | 5 | Crane | Workshop Crane | WOR-10 | 20 | 14.4 | YST 07 | F | Planning | Hull Block Section | 7 Days | Day Shift (0700-1900) | Team Beta | Advanced Crane Operator | Urgent | Pending |  | Thunderstorm | 35 | FALSE | 31 |  | 4 | No |  | No Conflict | Yes
BK-0275 | 2026-03-07 | 2026-03-13 |  | 6 | MEWP | Scissor Lift 10m | MEWP-08 |  |  | YST 02 | C | Commissioning | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Medium | Confirmed |  | Partly Cloudy | 11 | FALSE | 72 |  | 2 | No |  | No Conflict | Yes
BK-0276 | 2026-03-09 | 2026-03-19 |  | 10 | MEWP | Telescopic Boom Lift 30m | MEWP-18 |  |  | YST 01 | A | Commissioning | Personnel Access Work | 10 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Urgent | Cancelled | Budget constraint | Partly Cloudy | 9 | FALSE | 29 |  | 4 | No |  | No Conflict | Yes
BK-0277 | 2026-03-14 | 2026-03-27 | 2026-03-29 | 13 | Forklift | Telehandler Forklift | FLT-14 | 7 | 5.9 | YST 18 | C | Commissioning | Welding Materials | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | High | Rescheduled | Project timeline shifted | Overcast | 18 | FALSE | 56 |  | 3 | No |  | No Conflict | Yes
BK-0278 | 2026-03-11 | 2026-03-13 | 2026-03-14 | 2 | MEWP | Scissor Lift 10m | MEWP-11 |  |  | YST 06 | D | Outfitting | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | High | Rescheduled | Operator reassigned | Partly Cloudy | 10 | TRUE | 31 |  | 3 | No |  | No Conflict | Yes
BK-0279 | 2026-03-25 | 2026-04-08 |  | 14 | MEWP | Boom Lift 20m | MEWP-08 |  |  | YST 08 | E | Outfitting | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Confirmed |  | Overcast | 13 | FALSE | 64 |  | 3 | No |  | No Conflict | Yes
BK-0280 | 2026-03-16 | 2026-03-22 | 2026-03-26 | 6 | Crane | Goliath Gantry Crane | GC-01 | 200 | 144.1 | YST 04 | B | Planning | Helideck Module | 7 Days | Night Shift (1900-0700) | Team Beta | Heavy Lift Specialist | High | Rescheduled | Equipment breakdown | Clear | 16 | FALSE | 35 |  | 3 | No |  | No Conflict | Yes
BK-0281 | 2026-03-13 | 2026-03-22 |  | 9 | MEWP | Telescopic Boom Lift 30m | MEWP-13 |  |  | YST 11 | F | Planning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Echo | Advanced Operator | Medium | Cancelled | Client cancelled | Partly Cloudy | 16 | FALSE | 35 |  | 2 | Yes | BK-0300 | Yielded to Higher Priority | No
BK-0282 | 2026-03-17 | 2026-03-24 |  | 7 | Forklift | Counterbalance Forklift | FLT-13 | 7 | 5 | YST 17 | B | Outfitting | Pipe Bundles | Full Day | Day Shift (0700-1900) | Team Gamma | MEWP Operator | High | Completed |  | Clear | 3 | FALSE | 69 | Delayed | 3 | No |  | No Conflict | Yes
BK-0283 | 2026-03-15 | 2026-03-17 | 2026-03-18 | 2 | MEWP | Boom Lift 20m | MEWP-13 |  |  | YST 05 | B | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Rescheduled | Project timeline shifted | Clear | 12 | FALSE | 27 |  | 2 | Yes | BK-0273 | Later Request - Reassigned | No
BK-0284 | 2026-03-04 | 2026-03-12 |  | 8 | MEWP | Scissor Lift 10m | MEWP-24 |  |  | YST D1 | B | Assembly | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | Medium | Completed |  | Overcast | 6 | FALSE | 49 | On Time | 2 | No |  | No Conflict | Yes
BK-0285 | 2026-03-23 | 2026-03-25 |  | 2 | Crane | Workshop Crane | WOR-06 | 20 | 10.5 | YST 13 | A | Outfitting | Workshop Equipment | Half Day (PM) | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Low | Rejected | Permit not approved | Partly Cloudy | 17 | TRUE | 57 |  | 1 | No |  | No Conflict | Yes
BK-0286 | 2026-03-22 | 2026-03-28 |  | 6 | Crane | Level Luffing Crane | LLC 08 | 300 | 66.6 | YST D4 | A | Fabrication | Hull Block Section | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Lifting Supervisor | High | Rejected | Safety inspection required first | Clear | 13 | FALSE | 39 |  | 3 | No |  | No Conflict | Yes
BK-0287 | 2026-03-11 | 2026-03-23 |  | 12 | Crane | Mobile Crane | MOB-10 | 50 | 12.8 | YST 03 | D | Commissioning | Workshop Equipment | 3 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | High | Pending |  | Overcast | 3 | FALSE | 43 |  | 3 | Yes | BK-0224 | Priority Override | Yes
BK-0288 | 2026-03-29 | 2026-04-03 |  | 5 | Crane | Mobile Crane | MOB-05 | 25 | 13.6 | YST 05 | F | Fabrication | Mooring Winch | Half Day (PM) | Night Shift (1900-0700) | Team Gamma | Lifting Supervisor | Medium | Pending |  | Overcast | 5 | FALSE | 53 |  | 2 | No |  | No Conflict | Yes
BK-0289 | 2026-03-03 | 2026-03-09 |  | 6 | Cometto | SPMT 16 Axle Lines | COM-06 |  |  | YST 14 | E | Outfitting | Jacket Structure | Full Day | Day Shift (0700-1900) | Team Echo | Advanced Operator | Medium | Confirmed |  | Partly Cloudy | 17 | FALSE | 51 |  | 2 | No |  | No Conflict | Yes
BK-0290 | 2026-03-29 | 2026-04-05 |  | 7 | Cometto | Cometto Eco500 12 Axle Lines | COM-01 |  |  | YST 01 | D | Outfitting | Engine Module | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | High | Rejected | Weather conditions unsafe | Clear | 13 | TRUE | 32 |  | 3 | No |  | No Conflict | Yes
BK-0291 | 2026-03-23 | 2026-03-27 |  | 4 | Forklift | Telehandler Forklift | FLT-01 | 5 | 4.3 | YST 17 | A | Fabrication | Paint Drums | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Advanced Operator | High | Cancelled | Material not ready | Clear | 12 | FALSE | 22 |  | 3 | No |  | No Conflict | Yes
BK-0292 | 2026-03-21 | 2026-03-24 |  | 3 | Crane | Mobile Crane | MOB-14 | 75 | 41 | YST 08 | C | Testing | Helideck Module | 7 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Medium | Cancelled | Duplicate booking | Partly Cloudy | 8 | FALSE | 24 |  | 2 | No |  | No Conflict | Yes
BK-0293 | 2026-03-05 | 2026-03-09 |  | 4 | Crane | Mobile Crane | MOB-13 | 50 | 36.3 | YST D7 | A | Assembly | Construction Materials | Full Day | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Completed |  | Partly Cloudy | 17 | FALSE | 93 | Early | 3 | No |  | No Conflict | Yes
BK-0294 | 2026-03-07 | 2026-03-13 |  | 6 | Crane | Crawler Crane | CRA-03 | 50 | 19.3 | YST 04 | C | Outfitting | Riser Assembly | 2 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Urgent | Confirmed |  | Overcast | 18 | FALSE | 89 |  | 4 | No |  | No Conflict | Yes
BK-0295 | 2026-03-28 | 2026-03-30 | 2026-04-02 | 2 | Forklift | Heavy Duty Forklift | FLT-30 | 15 | 8.7 | YST D4 | F | Testing | Pipe Bundles | 2 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Low | Rescheduled | Client request | Heavy Rain | 20 | FALSE | 67 |  | 1 | No |  | No Conflict | Yes
BK-0296 | 2026-03-01 | 2026-03-08 |  | 7 | Crane | Goliath Gantry Crane | GC-15 | 300 | 78.4 | YST 01 | B | Assembly | Mega Block Section | Full Day | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | High | Completed |  | Clear | 18 | FALSE | 75 | On Time | 3 | No |  | No Conflict | Yes
BK-0297 | 2026-03-05 | 2026-03-17 |  | 12 | Forklift | Heavy Duty Forklift | FLT-40 | 15 | 5.3 | YST 03 | F | Planning | Electrical Cables | 7 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Completed |  | Clear | 3 | FALSE | 85 | Delayed | 2 | Yes | BK-0220 | Yielded to Higher Priority | No
BK-0298 | 2026-03-19 | 2026-03-26 |  | 7 | Cometto | SPMT 24 Axle Lines | COM-05 |  |  | YST 17 | D | Testing | Mega Block Section | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Confirmed |  | Clear | 16 | FALSE | 59 |  | 3 | No |  | No Conflict | Yes
BK-0299 | 2026-03-22 | 2026-03-29 |  | 7 | Forklift | Reach Forklift | FLT-40 | 2 | 1.2 | YST 08 | C | Outfitting | Welding Materials | Full Day | Day Shift (0700-1900) | Team Beta | Advanced Operator | High | Cancelled | Material not ready | Partly Cloudy | 4 | FALSE | 30 |  | 3 | No |  | No Conflict | Yes
BK-0300 | 2026-03-10 | 2026-03-19 |  | 9 | MEWP | Boom Lift 20m | MEWP-13 |  |  | YST 04 | C | Testing | Personnel Access Work | 5 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | High | Confirmed |  | Partly Cloudy | 15 | FALSE | 55 |  | 3 | Yes | BK-0281 | Priority Override | Yes
BK-0301 | 2026-03-18 | 2026-03-21 |  | 3 | MEWP | Scissor Lift 10m | MEWP-07 |  |  | YST 11 | F | Fabrication | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Completed |  | Clear | 4 | FALSE | 85 | Delayed | 3 | Yes | BK-0252 | Priority Override | Yes
BK-0302 | 2026-03-16 | 2026-03-18 |  | 2 | MEWP | Articulating Boom Lift 26m | MEWP-27 |  |  | YST 04 | E | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Low | Confirmed |  | Partly Cloudy | 3 | FALSE | 92 |  | 1 | No |  | No Conflict | Yes
BK-0303 | 2026-03-05 | 2026-03-16 |  | 11 | Forklift | Counterbalance Forklift | FLT-29 | 3 | 2.6 | YST D2 | C | Assembly | Welding Materials | 3 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Completed |  | Overcast | 11 | FALSE | 85 | Early | 2 | No |  | No Conflict | Yes
BK-0304 | 2026-03-12 | 2026-03-26 |  | 14 | MEWP | Telescopic Boom Lift 30m | MEWP-28 |  |  | YST 05 | E | Assembly | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Echo | MEWP Operator | Urgent | Confirmed |  | Clear | 11 | FALSE | 55 |  | 4 | No |  | No Conflict | Yes
BK-0305 | 2026-03-14 | 2026-03-22 |  | 8 | Crane | Crawler Crane | CRA-14 | 250 | 70.1 | YST 07 | C | Outfitting | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Pending |  | Clear | 6 | FALSE | 21 |  | 2 | Yes | BK-0222 | Yielded to Higher Priority | No
BK-0306 | 2026-03-05 | 2026-03-13 |  | 8 | MEWP | Telescopic Boom Lift 30m | MEWP-03 |  |  | YST 05 | D | Testing | Personnel Access Work | Half Day (PM) | Night Shift (1900-0700) | Team Delta | Advanced Operator | Urgent | Cancelled | Material not ready | Clear | 18 | FALSE | 44 |  | 4 | No |  | No Conflict | Yes
BK-0307 | 2026-03-12 | 2026-03-15 |  | 3 | Crane | Level Luffing Crane | LLC 15A | 300 | 80.4 | YST 17 | A | Planning | Flare Tower Section | Full Day | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Urgent | Pending |  | Overcast | 13 | FALSE | 64 |  | 4 | No |  | No Conflict | Yes
BK-0308 | 2026-03-03 | 2026-03-06 |  | 3 | Cometto | SPMT 16 Axle Lines | COM-02 |  |  | YST 15 | F | Planning | Jacket Structure | 3 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Cancelled | Duplicate booking | Overcast | 11 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0309 | 2026-03-25 | 2026-03-26 |  | 1 | MEWP | Telescopic Boom Lift 30m | MEWP-14 |  |  | YST 11 | E | Commissioning | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | Medium | Confirmed |  | Partly Cloudy | 10 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0310 | 2026-03-19 | 2026-03-22 |  | 3 | Crane | Crawler Crane | CRA-03 | 50 | 28.1 | YST 05 | C | Assembly | Mooring Winch | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Lifting Supervisor | Medium | Cancelled | Project postponed | Clear | 5 | FALSE | 62 |  | 2 | No |  | No Conflict | Yes
BK-0311 | 2026-03-15 | 2026-03-20 |  | 5 | Crane | Workshop Crane | WOR-17 | 10 | 6.6 | YST D6 | B | Outfitting | Structural Steel Module | 7 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Urgent | Pending |  | Light Rain | 15 | FALSE | 48 |  | 4 | No |  | No Conflict | Yes
BK-0312 | 2026-03-24 | 2026-03-31 |  | 7 | Crane | Workshop Crane | WOR-09 | 20 | 6.8 | YST 02 | D | Commissioning | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | Medium | Completed |  | High Wind | 42 | FALSE | 64 | On Time | 2 | No |  | No Conflict | Yes
BK-0313 | 2026-03-05 | 2026-03-12 |  | 7 | Crane | Crawler Crane | CRA-11 | 250 | 100.2 | YST 07 | C | Outfitting | Workshop Equipment | 10 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Low | Pending |  | Overcast | 10 | FALSE | 26 |  | 1 | No |  | No Conflict | Yes
BK-0314 | 2026-04-21 | 2026-04-28 |  | 7 | MEWP | Boom Lift 20m | MEWP-17 |  |  | YST 07 | A | Planning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Confirmed |  | Clear | 5 | FALSE | 83 |  | 2 | No |  | No Conflict | Yes
BK-0315 | 2026-04-15 | 2026-04-20 |  | 5 | Cometto | SPMT 16 Axle Lines | COM-01 |  |  | YST 04 | E | Commissioning | Engine Module | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Rejected | Safety inspection required first | Clear | 5 | TRUE | 62 |  | 3 | No |  | No Conflict | Yes
BK-0316 | 2026-04-25 | 2026-05-06 |  | 11 | MEWP | Boom Lift 20m | MEWP-23 |  |  | YST 04 | C | Outfitting | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Urgent | Cancelled | Client cancelled | Overcast | 12 | FALSE | 37 |  | 4 | No |  | No Conflict | Yes
BK-0317 | 2026-04-25 | 2026-04-27 |  | 2 | Crane | Level Luffing Crane | LLC 15 | 50 | 16.6 | YST 09 | D | Planning | Structural Steel Module | Half Day (AM) | Night Shift (1900-0700) | Team Beta | Heavy Lift Specialist | High | Confirmed |  | Clear | 15 | FALSE | 98 |  | 3 | No |  | No Conflict | Yes
BK-0318 | 2026-04-15 | 2026-04-23 |  | 8 | Crane | Level Luffing Crane | LLC 09 | 30 | 18.6 | YST D3 | A | Commissioning | Turret Assembly | 5 Days | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | Medium | Cancelled | Budget constraint | Partly Cloudy | 6 | FALSE | 20 |  | 2 | No |  | No Conflict | Yes
BK-0319 | 2026-04-17 | 2026-04-25 |  | 8 | Forklift | Reach Forklift | FLT-35 | 3 | 1.5 | YST 13 | E | Testing | Safety Equipment | Full Day | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | High | Completed |  | High Wind | 36 | FALSE | 43 | Delayed | 3 | Yes | BK-0343 | Yielded to Higher Priority | No
BK-0320 | 2026-04-21 | 2026-04-23 |  | 2 | MEWP | Articulating Boom Lift 26m | MEWP-27 |  |  | YST 03 | D | Commissioning | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Medium | Pending |  | Clear | 14 | FALSE | 60 |  | 2 | No |  | No Conflict | Yes
BK-0321 | 2026-04-23 | 2026-04-28 |  | 5 | Crane | Workshop Crane | WOR-02 | 20 | 15.6 | YST 10 | E | Commissioning | Structural Steel Module | Full Day | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | Medium | Completed |  | Partly Cloudy | 16 | FALSE | 61 | On Time | 2 | No |  | No Conflict | Yes
BK-0322 | 2026-04-26 | 2026-05-04 |  | 8 | Crane | Goliath Gantry Crane | GC-19 | 600 | 207.4 | YST 04 | F | Planning | Workshop Equipment | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Low | Confirmed |  | Partly Cloudy | 3 | FALSE | 40 |  | 1 | No |  | No Conflict | Yes
BK-0323 | 2026-04-06 | 2026-04-13 |  | 7 | Forklift | Counterbalance Forklift | FLT-38 | 7 | 3.5 | YST 20 | B | Planning | PPE Supplies | Half Day (AM) | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Medium | Rejected | Location conflict with another operation | Light Rain | 15 | FALSE | 63 |  | 2 | No |  | No Conflict | Yes
BK-0324 | 2026-04-19 | 2026-04-26 |  | 7 | Crane | Goliath Gantry Crane | GC-16 | 200 | 56 | YST 19 | B | Outfitting | Structural Steel Module | Half Day (AM) | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Completed |  | Clear | 3 | FALSE | 80 | Delayed | 2 | No |  | No Conflict | Yes
BK-0325 | 2026-04-25 | 2026-04-28 |  | 3 | Forklift | Counterbalance Forklift | FLT-06 | 2.5 | 1.7 | YST 01 | D | Commissioning | PPE Supplies | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Rejected | Location conflict with another operation | Clear | 6 | TRUE | 31 |  | 2 | No |  | No Conflict | Yes
BK-0326 | 2026-04-20 | 2026-04-28 |  | 8 | MEWP | Telescopic Boom Lift 30m | MEWP-21 |  |  | YST 03 | A | Testing | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Low | Completed |  | High Wind | 44 | FALSE | 88 | Early | 1 | No |  | No Conflict | Yes
BK-0327 | 2026-04-17 | 2026-04-20 |  | 3 | Forklift | Heavy Duty Forklift | FLT-08 | 20 | 8.5 | YST 02 | A | Planning | Tool Containers | 5 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Medium | Confirmed |  | Overcast | 11 | FALSE | 79 |  | 2 | No |  | No Conflict | Yes
BK-0328 | 2026-04-26 | 2026-05-07 |  | 11 | MEWP | Scissor Lift 10m | MEWP-30 |  |  | YST 02 | B | Commissioning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Confirmed |  | Partly Cloudy | 12 | FALSE | 87 |  | 2 | No |  | No Conflict | Yes
BK-0329 | 2026-04-22 | 2026-05-03 |  | 11 | Crane | Level Luffing Crane | LLC 08 | 50 | 14.3 | YST 08 | E | Outfitting | Engine Module | 5 Days | Night Shift (1900-0700) | Team Delta | Lifting Supervisor | Urgent | Confirmed |  | Clear | 15 | FALSE | 69 |  | 4 | No |  | No Conflict | Yes
BK-0330 | 2026-04-06 | 2026-04-11 |  | 5 | Crane | Workshop Crane | WOR-07 | 10 | 3.3 | YST 15 | D | Outfitting | Accommodation Module | 2 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Low | Confirmed |  | Partly Cloudy | 12 | FALSE | 50 |  | 1 | No |  | No Conflict | Yes
BK-0331 | 2026-04-26 | 2026-05-05 |  | 9 | Forklift | Heavy Duty Forklift | FLT-34 | 15 | 6.7 | YST 03 | A | Commissioning | Scaffolding Materials | 3 Days | Night Shift (1900-0700) | Team Echo | Advanced Operator | Medium | Completed |  | Partly Cloudy | 9 | FALSE | 54 | Early | 2 | No |  | No Conflict | Yes
BK-0332 | 2026-04-19 | 2026-05-01 |  | 12 | Forklift | Counterbalance Forklift | FLT-31 | 7 | 2.4 | YST 02 | F | Planning | Pipe Bundles | 5 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Completed |  | Partly Cloudy | 9 | FALSE | 84 | Delayed | 2 | Yes | BK-0342; BK-0345 | Later Request - Reassigned | No
BK-0333 | 2026-04-07 | 2026-04-10 |  | 3 | Crane | Workshop Crane | WOR-10 | 10 | 3.1 | YST 01 | D | Outfitting | Mooring Winch | Full Day | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | High | Confirmed |  | Light Rain | 14 | FALSE | 80 |  | 3 | No |  | No Conflict | Yes
BK-0334 | 2026-04-15 | 2026-04-23 |  | 8 | Crane | Workshop Crane | WOR-11 | 10 | 5.7 | YST D2 | E | Fabrication | Riser Assembly | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Cancelled | Client cancelled | Light Rain | 4 | FALSE | 52 |  | 3 | No |  | No Conflict | Yes
BK-0335 | 2026-04-30 | 2026-05-08 |  | 8 | Forklift | Counterbalance Forklift | FLT-40 | 7 | 3.1 | YST 12 | F | Fabrication | Timber Dunnage | Half Day (AM) | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Confirmed |  | Clear | 12 | FALSE | 70 |  | 3 | No |  | No Conflict | Yes
BK-0336 | 2026-04-24 | 2026-05-06 |  | 12 | MEWP | Boom Lift 20m | MEWP-11 |  |  | YST 08 | C | Assembly | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Confirmed |  | Partly Cloudy | 18 | FALSE | 47 |  | 2 | No |  | No Conflict | Yes
BK-0337 | 2026-04-16 | 2026-04-24 | 2026-04-25 | 8 | Cometto | SPMT 16 Axle Lines | COM-06 |  |  | YST 15 | A | Planning | Jacket Structure | 5 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Rescheduled | Weather delay | Partly Cloudy | 7 | TRUE | 37 |  | 2 | No |  | No Conflict | Yes
BK-0338 | 2026-04-23 | 2026-04-26 |  | 3 | Crane | Goliath Gantry Crane | GC-15 | 600 | 142.7 | YST 19 | F | Commissioning | Hull Block Section | 2 Days | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | Medium | Completed |  | Clear | 8 | FALSE | 54 | Delayed | 2 | No |  | No Conflict | Yes
BK-0339 | 2026-04-17 | 2026-04-24 | 2026-04-28 | 7 | Crane | Crawler Crane | CRA-17 | 150 | 73.6 | YST 08 | C | Fabrication | Construction Materials | 7 Days | Day Shift (0700-1900) | Team Gamma | Lifting Supervisor | High | Rescheduled | Original date conflicts with maintenance | Light Rain | 9 | TRUE | 38 |  | 3 | No |  | No Conflict | Yes
BK-0340 | 2026-04-06 | 2026-04-13 |  | 7 | Crane | Tower Crane | TOW-05 | 25 | 15 | YST 12 | C | Fabrication | Structural Steel Module | Full Day | Day Shift (0700-1900) | Team Gamma | Lifting Supervisor | High | Completed |  | Clear | 3 | FALSE | 49 | On Time | 3 | No |  | No Conflict | Yes
BK-0341 | 2026-04-18 | 2026-05-01 |  | 13 | MEWP | Scissor Lift 10m | MEWP-13 |  |  | YST 01 | F | Testing | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | Urgent | Confirmed |  | High Wind | 35 | FALSE | 58 |  | 4 | No |  | No Conflict | Yes
BK-0342 | 2026-04-16 | 2026-04-27 |  | 11 | Forklift | Heavy Duty Forklift | FLT-31 | 25 | 12.4 | YST 11 | E | Fabrication | Insulation Materials | 7 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Confirmed |  | Partly Cloudy | 4 | FALSE | 52 |  | 2 | Yes | BK-0332 | First-Come-First-Served | Yes
BK-0343 | 2026-04-19 | 2026-04-25 |  | 6 | Forklift | Telehandler Forklift | FLT-35 | 4 | 3.5 | YST 01 | D | Assembly | Safety Equipment | 7 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Urgent | Completed |  | Overcast | 18 | FALSE | 63 | On Time | 4 | Yes | BK-0319 | Priority Override | Yes
BK-0344 | 2026-04-23 | 2026-05-03 |  | 10 | Crane | Crawler Crane | CRA-12 | 50 | 18.7 | YST 05 | D | Commissioning | Pipe Spool | Full Day | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Low | Cancelled | Material not ready | High Wind | 39 | FALSE | 66 |  | 1 | No |  | No Conflict | Yes
BK-0345 | 2026-04-29 | 2026-05-04 | 2026-05-06 | 5 | Forklift | Counterbalance Forklift | FLT-31 | 3 | 1.6 | YST 07 | D | Planning | Electrical Cables | 14 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Low | Rescheduled | Permit delay | Clear | 10 | FALSE | 28 |  | 1 | Yes | BK-0332; BK-0528 | Yielded to Higher Priority | No
BK-0346 | 2026-04-06 | 2026-04-16 |  | 10 | Crane | Mobile Crane | MOB-19 | 25 | 6.9 | YST 05 | B | Assembly | Flare Tower Section | Full Day | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Medium | Rejected | Operator not available | Partly Cloudy | 17 | FALSE | 51 |  | 2 | No |  | No Conflict | Yes
BK-0347 | 2026-04-30 | 2026-05-08 |  | 8 | Crane | Level Luffing Crane | LLC 20 | 50 | 21.2 | YST 17 | F | Outfitting | Engine Module | 5 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Medium | Completed |  | High Wind | 28 | FALSE | 41 | Delayed | 2 | No |  | No Conflict | Yes
BK-0348 | 2026-04-06 | 2026-04-13 |  | 7 | Crane | Mobile Crane | MOB-02 | 50 | 32.9 | YST 06 | F | Planning | Structural Steel Module | Full Day | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | Low | Completed |  | Partly Cloudy | 7 | FALSE | 50 | Delayed | 1 | No |  | No Conflict | Yes
BK-0349 | 2026-04-28 | 2026-05-02 |  | 4 | Forklift | Telehandler Forklift | FLT-07 | 5 | 1.8 | YST D2 | C | Outfitting | Bolt Pallets | 3 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | Low | Pending |  | Partly Cloudy | 7 | FALSE | 34 |  | 1 | No |  | No Conflict | Yes
BK-0350 | 2026-04-27 | 2026-04-30 |  | 3 | Forklift | Counterbalance Forklift | FLT-08 | 7 | 2.8 | YST 15 | B | Outfitting | Safety Equipment | 5 Days | Night Shift (1900-0700) | Team Delta | Advanced Operator | Medium | Cancelled | Client cancelled | Heavy Rain | 20 | FALSE | 34 |  | 2 | No |  | No Conflict | Yes
BK-0351 | 2026-04-05 | 2026-04-15 |  | 10 | Crane | Goliath Gantry Crane | GC-13 | 300 | 202.7 | YST 01 | D | Planning | Mega Block Section | 14 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Low | Rejected | Crane under scheduled maintenance | Clear | 3 | FALSE | 36 |  | 1 | No |  | No Conflict | Yes
BK-0352 | 2026-04-02 | 2026-04-04 |  | 2 | Cometto | Cometto MSPE 8 Axle Lines | COM-10 |  |  | YST 20 | B | Commissioning | Engine Module | Full Day | Night Shift (1900-0700) | Team Beta | Advanced Operator | High | Confirmed |  | High Wind | 43 | FALSE | 50 |  | 3 | No |  | No Conflict | Yes
BK-0353 | 2026-04-28 | 2026-05-04 |  | 6 | Cometto | Cometto Eco500 12 Axle Lines | COM-02 |  |  | YST 16 | C | Fabrication | Jacket Structure | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Cancelled | Client cancelled | Thunderstorm | 20 | FALSE | 33 |  | 2 | No |  | No Conflict | Yes
BK-0354 | 2026-04-30 | 2026-05-06 | 2026-05-11 | 6 | Cometto | SPMT 16 Axle Lines | COM-03 |  |  | YST 19 | D | Fabrication | Jacket Structure | 2 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | High | Rescheduled | Equipment breakdown | Partly Cloudy | 15 | TRUE | 27 |  | 3 | No |  | No Conflict | Yes
BK-0355 | 2026-04-05 | 2026-04-11 |  | 6 | Crane | Crawler Crane | CRA-16 | 50 | 39.5 | YST 02 | D | Fabrication | Pipe Spool | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | High | Cancelled | Client cancelled | Overcast | 11 | FALSE | 50 |  | 3 | No |  | No Conflict | Yes
BK-0356 | 2026-04-22 | 2026-04-27 |  | 5 | Crane | Workshop Crane | WOR-15 | 20 | 4.8 | YST 07 | E | Planning | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Medium | Completed |  | Overcast | 7 | FALSE | 61 | On Time | 2 | No |  | No Conflict | Yes
BK-0357 | 2026-04-28 | 2026-05-12 |  | 14 | Crane | Mobile Crane | MOB-19 | 100 | 50.7 | YST 05 | F | Testing | Helideck Module | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Crane Operator | Urgent | Completed |  | High Wind | 40 | FALSE | 69 | On Time | 4 | No |  | No Conflict | Yes
BK-0358 | 2026-04-09 | 2026-04-15 |  | 6 | Crane | Goliath Gantry Crane | GC-01 | 200 | 131.2 | YST 01 | F | Assembly | Turret Assembly | 5 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Urgent | Completed |  | Clear | 5 | FALSE | 73 | Delayed | 4 | No |  | No Conflict | Yes
BK-0359 | 2026-04-26 | 2026-05-02 |  | 6 | Crane | Mobile Crane | MOB-18 | 100 | 71.2 | YST D1 | D | Planning | Accommodation Module | 2 Days | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Low | Rejected | Crane under scheduled maintenance | Partly Cloudy | 12 | TRUE | 55 |  | 1 | No |  | No Conflict | Yes
BK-0360 | 2026-04-22 | 2026-05-03 |  | 11 | Crane | Workshop Crane | WOR-05 | 10 | 4.9 | YST D6 | E | Commissioning | Anchor Chain | 2 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | High | Completed |  | Partly Cloudy | 17 | FALSE | 72 | On Time | 3 | No |  | No Conflict | Yes
BK-0361 | 2026-04-09 | 2026-04-15 |  | 6 | Forklift | Telehandler Forklift | FLT-02 | 5 | 2.8 | YST 11 | A | Commissioning | Pipe Bundles | 3 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Cancelled | Material not ready | Partly Cloudy | 5 | FALSE | 42 |  | 2 | No |  | No Conflict | Yes
BK-0362 | 2026-04-02 | 2026-04-10 |  | 8 | Crane | Workshop Crane | WOR-03 | 20 | 7.2 | YST 06 | D | Commissioning | Riser Assembly | 7 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | Low | Completed |  | Heavy Rain | 23 | FALSE | 77 | On Time | 1 | No |  | No Conflict | Yes
BK-0363 | 2026-04-11 | 2026-04-16 |  | 5 | Crane | Tower Crane | TOW-07 | 10 | 7 | YST D3 | C | Outfitting | Engine Module | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Medium | Cancelled | Duplicate booking | Clear | 4 | FALSE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0364 | 2026-04-02 | 2026-04-06 |  | 4 | MEWP | Boom Lift 20m | MEWP-23 |  |  | YST 03 | E | Outfitting | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Pending |  | Partly Cloudy | 13 | FALSE | 61 |  | 2 | No |  | No Conflict | Yes
BK-0365 | 2026-04-27 | 2026-05-01 |  | 4 | Forklift | Reach Forklift | FLT-26 | 2.5 | 1.6 | YST 07 | A | Commissioning | Scaffolding Materials | Full Day | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Confirmed |  | Overcast | 7 | FALSE | 92 |  | 3 | No |  | No Conflict | Yes
BK-0366 | 2026-04-24 | 2026-05-06 |  | 12 | Crane | Workshop Crane | WOR-07 | 20 | 11.6 | YST 02 | D | Outfitting | Transformer Unit | 2 Days | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | High | Rejected | Operator not available | Partly Cloudy | 4 | FALSE | 61 |  | 3 | No |  | No Conflict | Yes
BK-0367 | 2026-04-06 | 2026-04-10 |  | 4 | MEWP | Telescopic Boom Lift 30m | MEWP-04 |  |  | YST 08 | D | Outfitting | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Pending |  | Overcast | 3 | FALSE | 37 |  | 2 | No |  | No Conflict | Yes
BK-0368 | 2026-04-05 | 2026-04-06 |  | 1 | Forklift | Telehandler Forklift | FLT-32 | 4 | 2.2 | YST D1 | A | Outfitting | Pipe Bundles | 5 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Completed |  | Heavy Rain | 12 | FALSE | 93 | On Time | 2 | No |  | No Conflict | Yes
BK-0369 | 2026-04-04 | 2026-04-11 |  | 7 | MEWP | Scissor Lift 10m | MEWP-16 |  |  | YST 09 | E | Commissioning | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | High | Completed |  | Partly Cloudy | 9 | FALSE | 53 | On Time | 3 | Yes | BK-0413 | Priority Override | Yes
BK-0370 | 2026-04-06 | 2026-04-09 |  | 3 | Crane | Mobile Crane | MOB-16 | 75 | 31.3 | YST D7 | F | Fabrication | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Medium | Completed |  | High Wind | 29 | FALSE | 92 | On Time | 2 | No |  | No Conflict | Yes
BK-0371 | 2026-04-21 | 2026-05-04 |  | 13 | MEWP | Scissor Lift 10m | MEWP-09 |  |  | YST 08 | A | Testing | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Medium | Rejected | Location conflict with another operation | Heavy Rain | 24 | FALSE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0372 | 2026-04-10 | 2026-04-12 |  | 2 | Forklift | Heavy Duty Forklift | FLT-29 | 20 | 17.1 | YST 07 | A | Outfitting | PPE Supplies | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Operator | Medium | Confirmed |  | Partly Cloudy | 15 | FALSE | 67 |  | 2 | No |  | No Conflict | Yes
BK-0373 | 2026-04-29 | 2026-05-11 |  | 12 | Crane | Goliath Gantry Crane | GC-16 | 300 | 173.4 | YST 19 | A | Planning | Engine Module | 2 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | High | Completed |  | Overcast | 7 | FALSE | 48 | On Time | 3 | No |  | No Conflict | Yes
BK-0374 | 2026-04-07 | 2026-04-14 |  | 7 | Crane | Level Luffing Crane | LLC 17 | 30 | 14.1 | YST 06 | F | Outfitting | Mega Block Section | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Rigging Supervisor | High | Rejected | Insufficient lead time | Light Rain | 12 | TRUE | 63 |  | 3 | No |  | No Conflict | Yes
BK-0375 | 2026-04-19 | 2026-04-29 | 2026-04-30 | 10 | Forklift | Heavy Duty Forklift | FLT-12 | 10 | 8.4 | YST 14 | E | Commissioning | Bolt Pallets | 2 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Rescheduled | Operator reassigned | Overcast | 9 | TRUE | 30 |  | 2 | No |  | No Conflict | Yes
BK-0376 | 2026-04-13 | 2026-04-20 |  | 7 | MEWP | Boom Lift 20m | MEWP-12 |  |  | YST 03 | D | Commissioning | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Alpha | Forklift Operator | High | Completed |  | Partly Cloudy | 9 | FALSE | 52 | Early | 3 | No |  | No Conflict | Yes
BK-0377 | 2026-04-27 | 2026-05-06 |  | 9 | Crane | Mobile Crane | MOB-07 | 100 | 37.4 | YST 03 | B | Outfitting | Anchor Chain | 3 Days | Night Shift (1900-0700) | Team Gamma | Advanced Crane Operator | High | Confirmed |  | Light Rain | 2 | FALSE | 79 |  | 3 | No |  | No Conflict | Yes
BK-0378 | 2026-04-15 | 2026-04-26 |  | 11 | Crane | Workshop Crane | WOR-16 | 20 | 4.9 | YST 06 | D | Commissioning | Hull Block Section | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Completed |  | Partly Cloudy | 10 | FALSE | 43 | On Time | 2 | No |  | No Conflict | Yes
BK-0379 | 2026-04-08 | 2026-04-14 |  | 6 | Crane | Tower Crane | TOW-17 | 10 | 3 | YST 09 | E | Planning | Accommodation Module | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Confirmed |  | Overcast | 10 | FALSE | 61 |  | 3 | No |  | No Conflict | Yes
BK-0380 | 2026-04-29 | 2026-05-05 |  | 6 | Crane | Workshop Crane | WOR-04 | 20 | 14.8 | YST 08 | F | Assembly | Accommodation Module | 2 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Urgent | Rejected | Operator not available | Thunderstorm | 29 | FALSE | 47 |  | 4 | No |  | No Conflict | Yes
BK-0381 | 2026-04-29 | 2026-05-02 |  | 3 | Cometto | SPMT 24 Axle Lines | COM-09 |  |  | YST 20 | B | Fabrication | Hull Block Section | 7 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Low | Confirmed |  | Clear | 10 | FALSE | 69 |  | 1 | No |  | No Conflict | Yes
BK-0382 | 2026-04-14 | 2026-04-16 |  | 2 | Forklift | Reach Forklift | FLT-36 | 1.5 | 1.2 | YST 15 | A | Fabrication | Bolt Pallets | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Urgent | Confirmed |  | Heavy Rain | 15 | FALSE | 92 |  | 4 | No |  | No Conflict | Yes
BK-0383 | 2026-04-09 | 2026-04-16 |  | 7 | Cometto | Cometto Eco500 12 Axle Lines | COM-09 |  |  | YST 17 | A | Assembly | Engine Module | 5 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Completed |  | Clear | 5 | FALSE | 77 | Early | 2 | No |  | No Conflict | Yes
BK-0384 | 2026-04-04 | 2026-04-14 |  | 10 | Crane | Level Luffing Crane | LLC 21 | 100 | 32.7 | YST 17 | E | Outfitting | Mooring Winch | 10 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Confirmed |  | Partly Cloudy | 6 | FALSE | 81 |  | 2 | No |  | No Conflict | Yes
BK-0385 | 2026-04-10 | 2026-04-14 | 2026-04-21 | 4 | Crane | Level Luffing Crane | LLC 03 | 300 | 176.5 | YST D4 | B | Outfitting | Anchor Chain | 2 Days | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | Low | Rescheduled | Project timeline shifted | Light Rain | 11 | TRUE | 51 |  | 1 | No |  | No Conflict | Yes
BK-0386 | 2026-04-14 | 2026-04-23 |  | 9 | Forklift | Heavy Duty Forklift | FLT-24 | 20 | 13.4 | YST D2 | D | Planning | Insulation Materials | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Pending |  | Light Rain | 13 | FALSE | 47 |  | 2 | No |  | No Conflict | Yes
BK-0387 | 2026-04-03 | 2026-04-04 |  | 1 | Crane | Mobile Crane | MOB-05 | 50 | 19 | YST D8 | D | Planning | Workshop Equipment | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Lifting Supervisor | Medium | Completed |  | Thunderstorm | 35 | FALSE | 83 | Early | 2 | No |  | No Conflict | Yes
BK-0388 | 2026-04-27 | 2026-04-30 |  | 3 | Crane | Tower Crane | TOW-02 | 10 | 6.6 | YST D5 | E | Assembly | Engine Module | 3 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Low | Cancelled | Material not ready | Partly Cloudy | 4 | FALSE | 31 |  | 1 | No |  | No Conflict | Yes
BK-0389 | 2026-04-26 | 2026-04-29 |  | 3 | Crane | Level Luffing Crane | LLC 19 | 100 | 72.3 | YST 10 | B | Fabrication | Pipe Spool | 5 Days | Night Shift (1900-0700) | Team Delta | Basic Crane Operator | High | Completed |  | Clear | 10 | FALSE | 74 | On Time | 3 | No |  | No Conflict | Yes
BK-0390 | 2026-04-13 | 2026-04-15 |  | 2 | Crane | Mobile Crane | MOB-20 | 100 | 25.3 | YST 07 | F | Commissioning | Flare Tower Section | 5 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | Medium | Cancelled | Project postponed | Partly Cloudy | 11 | FALSE | 27 |  | 2 | No |  | No Conflict | Yes
BK-0391 | 2026-04-27 | 2026-04-28 |  | 1 | Forklift | Counterbalance Forklift | FLT-16 | 3 | 1.1 | YST 16 | D | Fabrication | Welding Materials | 2 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Completed |  | Partly Cloudy | 2 | FALSE | 87 | Delayed | 2 | No |  | No Conflict | Yes
BK-0392 | 2026-04-16 | 2026-04-22 |  | 6 | Forklift | Heavy Duty Forklift | FLT-04 | 15 | 4.8 | YST 10 | D | Commissioning | Consumables Pallet | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Medium | Completed |  | Overcast | 11 | FALSE | 72 | Delayed | 2 | No |  | No Conflict | Yes
BK-0393 | 2026-04-20 | 2026-05-02 | 2026-05-06 | 12 | Forklift | Reach Forklift | FLT-34 | 2 | 1.1 | YST D3 | D | Outfitting | Pipe Bundles | Half Day (AM) | Day Shift (0700-1900) | Team Echo | Advanced Operator | Low | Rescheduled | Project timeline shifted | Clear | 13 | TRUE | 32 |  | 1 | No |  | No Conflict | Yes
BK-0394 | 2026-04-12 | 2026-04-17 |  | 5 | MEWP | Articulating Boom Lift 26m | MEWP-05 |  |  | YST D3 | F | Commissioning | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | Urgent | Rejected | Insufficient lead time | Overcast | 17 | FALSE | 38 |  | 4 | No |  | No Conflict | Yes
BK-0395 | 2026-04-23 | 2026-05-02 |  | 9 | Cometto | Cometto Eco500 12 Axle Lines | COM-03 |  |  | YST 03 | B | Fabrication | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Urgent | Completed |  | Overcast | 2 | FALSE | 56 | On Time | 4 | No |  | No Conflict | Yes
BK-0396 | 2026-04-06 | 2026-04-09 | 2026-04-15 | 3 | Forklift | Counterbalance Forklift | FLT-08 | 2.5 | 2.1 | YST 11 | C | Planning | Scaffolding Materials | 3 Days | Day Shift (0700-1900) | Team Beta | MEWP Operator | Medium | Rescheduled | Client request | Light Rain | 10 | FALSE | 26 |  | 2 | No |  | No Conflict | Yes
BK-0397 | 2026-04-02 | 2026-04-14 |  | 12 | Crane | Mobile Crane | MOB-20 | 25 | 18.7 | YST 02 | A | Fabrication | Helideck Module | 3 Days | Night Shift (1900-0700) | Team Alpha | Basic Crane Operator | High | Confirmed |  | Overcast | 8 | FALSE | 58 |  | 3 | No |  | No Conflict | Yes
BK-0398 | 2026-04-23 | 2026-04-28 |  | 5 | MEWP | Scissor Lift 10m | MEWP-21 |  |  | YST 05 | D | Planning | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Alpha | Advanced Operator | High | Completed |  | Clear | 17 | FALSE | 72 | On Time | 3 | No |  | No Conflict | Yes
BK-0399 | 2026-04-09 | 2026-04-14 | 2026-04-17 | 5 | Forklift | Telehandler Forklift | FLT-15 | 4 | 2.3 | YST 05 | E | Commissioning | Scaffolding Materials | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Forklift Operator | Urgent | Rescheduled | Client request | Partly Cloudy | 2 | FALSE | 25 |  | 4 | No |  | No Conflict | Yes
BK-0400 | 2026-04-11 | 2026-04-16 |  | 5 | Forklift | Reach Forklift | FLT-10 | 1.5 | 1.1 | YST 13 | E | Assembly | Pipe Bundles | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Urgent | Rejected | Load exceeds crane capacity | Partly Cloudy | 11 | TRUE | 37 |  | 4 | No |  | No Conflict | Yes
BK-0401 | 2026-04-29 | 2026-05-05 | 2026-05-07 | 6 | Forklift | Reach Forklift | FLT-35 | 3 | 1.1 | YST D1 | F | Outfitting | Tool Containers | 3 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Rescheduled | Material delivery delayed | Light Rain | 11 | FALSE | 67 |  | 3 | Yes | BK-0508 | Priority Override | Yes
BK-0402 | 2026-04-17 | 2026-05-01 |  | 14 | Crane | Level Luffing Crane | LLC 17 | 300 | 190.8 | YST D2 | E | Assembly | Accommodation Module | 2 Days | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Low | Rejected | Crane already booked | Clear | 11 | FALSE | 43 |  | 1 | No |  | No Conflict | Yes
BK-0403 | 2026-04-09 | 2026-04-16 | 2026-04-20 | 7 | Crane | Level Luffing Crane | LLC 19 | 30 | 12.3 | YST 16 | E | Commissioning | Accommodation Module | 5 Days | Day Shift (0700-1900) | Team Beta | Advanced Crane Operator | High | Rescheduled | Permit delay | Heavy Rain | 17 | FALSE | 65 |  | 3 | No |  | No Conflict | Yes
BK-0404 | 2026-04-17 | 2026-04-26 |  | 9 | Crane | Tower Crane | TOW-04 | 15 | 6.3 | YST 17 | B | Outfitting | Mooring Winch | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Low | Confirmed |  | Clear | 4 | FALSE | 77 |  | 1 | No |  | No Conflict | Yes
BK-0405 | 2026-04-18 | 2026-04-24 |  | 6 | Crane | Crawler Crane | CRA-15 | 250 | 69.4 | YST D3 | B | Testing | Anchor Chain | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Rigging Supervisor | Urgent | Rejected | Project schedule changed | Clear | 16 | TRUE | 33 |  | 4 | No |  | No Conflict | Yes
BK-0406 | 2026-04-15 | 2026-04-21 |  | 6 | Cometto | SPMT 16 Axle Lines | COM-07 |  |  | YST 02 | C | Assembly | Jacket Structure | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Basic Operator | Low | Confirmed |  | High Wind | 34 | FALSE | 41 |  | 1 | No |  | No Conflict | Yes
BK-0407 | 2026-04-26 | 2026-04-29 |  | 3 | Forklift | Reach Forklift | FLT-14 | 1.5 | 1 | YST 10 | A | Outfitting | Electrical Cables | Full Day | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Medium | Completed |  | Partly Cloudy | 11 | FALSE | 90 | On Time | 2 | No |  | No Conflict | Yes
BK-0408 | 2026-04-27 | 2026-05-05 |  | 8 | MEWP | Boom Lift 20m | MEWP-25 |  |  | YST D3 | F | Testing | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Rejected | Load exceeds crane capacity | Partly Cloudy | 9 | FALSE | 62 |  | 2 | No |  | No Conflict | Yes
BK-0409 | 2026-04-29 | 2026-05-04 |  | 5 | Crane | Level Luffing Crane | LLC 21 | 40 | 21.8 | YST 01 | A | Fabrication | Construction Materials | 5 Days | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | High | Cancelled | Budget constraint | High Wind | 42 | FALSE | 53 |  | 3 | No |  | No Conflict | Yes
BK-0410 | 2026-04-07 | 2026-04-16 |  | 9 | MEWP | Scissor Lift 10m | MEWP-22 |  |  | YST 04 | F | Testing | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Completed |  | Partly Cloudy | 12 | FALSE | 42 | On Time | 2 | No |  | No Conflict | Yes
BK-0411 | 2026-04-30 | 2026-05-01 |  | 1 | Crane | Mobile Crane | MOB-13 | 25 | 9.6 | YST D1 | B | Assembly | Pipe Spool | Full Day | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Medium | Completed |  | Light Rain | 6 | FALSE | 50 | On Time | 2 | No |  | No Conflict | Yes
BK-0412 | 2026-04-11 | 2026-04-14 |  | 3 | Cometto | SPMT 16 Axle Lines | COM-06 |  |  | YST 14 | A | Planning | Engine Module | Half Day (PM) | Night Shift (1900-0700) | Team Gamma | Advanced Operator | Medium | Rejected | Project schedule changed | Clear | 9 | FALSE | 27 |  | 2 | No |  | No Conflict | Yes
BK-0413 | 2026-04-09 | 2026-04-11 | 2026-04-16 | 2 | MEWP | Telescopic Boom Lift 30m | MEWP-16 |  |  | YST 03 | F | Planning | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Rescheduled | Material delivery delayed | Clear | 6 | FALSE | 60 |  | 2 | Yes | BK-0369 | Yielded to Higher Priority | No
BK-0414 | 2026-04-07 | 2026-04-16 |  | 9 | Crane | Tower Crane | TOW-14 | 15 | 3 | YST 14 | E | Assembly | Transformer Unit | 10 Days | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Low | Completed |  | Overcast | 7 | FALSE | 70 | On Time | 1 | No |  | No Conflict | Yes
BK-0415 | 2026-04-09 | 2026-04-19 |  | 10 | Crane | Crawler Crane | CRA-17 | 100 | 63.5 | YST D2 | D | Commissioning | Flare Tower Section | Full Day | Day Shift (0700-1900) | Team Echo | Lifting Supervisor | High | Completed |  | Clear | 6 | FALSE | 96 | On Time | 3 | No |  | No Conflict | Yes
BK-0416 | 2026-04-20 | 2026-04-26 | 2026-05-02 | 6 | Forklift | Telehandler Forklift | FLT-18 | 5 | 3.4 | YST D5 | C | Planning | Timber Dunnage | Full Day | Night Shift (1900-0700) | Team Gamma | Basic Operator | Medium | Rescheduled | Safety stand-down | Thunderstorm | 24 | TRUE | 20 |  | 2 | No |  | No Conflict | Yes
BK-0417 | 2026-04-06 | 2026-04-11 |  | 5 | Forklift | Reach Forklift | FLT-05 | 3 | 2.4 | YST 18 | D | Testing | Safety Equipment | 3 Days | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Medium | Confirmed |  | Partly Cloudy | 7 | FALSE | 40 |  | 2 | No |  | No Conflict | Yes
BK-0418 | 2026-04-04 | 2026-04-10 |  | 6 | Forklift | Reach Forklift | FLT-18 | 1.5 | 1.3 | YST 08 | C | Commissioning | Steel Plates | 5 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | Low | Cancelled | Material not ready | Clear | 17 | FALSE | 65 |  | 1 | No |  | No Conflict | Yes
BK-0419 | 2026-04-23 | 2026-04-30 |  | 7 | Crane | Workshop Crane | WOR-09 | 20 | 4.8 | YST 07 | F | Commissioning | Flare Tower Section | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | Medium | Cancelled | Client cancelled | Overcast | 7 | FALSE | 28 |  | 2 | No |  | No Conflict | Yes
BK-0420 | 2026-04-09 | 2026-04-21 |  | 12 | Forklift | Telehandler Forklift | FLT-35 | 4 | 2.2 | YST D8 | F | Commissioning | Steel Plates | 3 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Low | Completed |  | Clear | 12 | FALSE | 57 | On Time | 1 | No |  | No Conflict | Yes
BK-0421 | 2026-04-17 | 2026-04-23 |  | 6 | Crane | Level Luffing Crane | LLC 14 | 40 | 31.5 | YST 02 | E | Planning | Accommodation Module | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Confirmed |  | High Wind | 32 | FALSE | 44 |  | 2 | No |  | No Conflict | Yes
BK-0422 | 2026-05-07 | 2026-05-10 |  | 3 | Crane | Workshop Crane | WOR-14 | 10 | 7 | YST 01 | B | Planning | Mooring Winch | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Rigging Supervisor | Urgent | Rejected | Project schedule changed | Partly Cloudy | 12 | FALSE | 24 |  | 4 | No |  | No Conflict | Yes
BK-0423 | 2026-05-25 | 2026-06-01 |  | 7 | Crane | Level Luffing Crane | LLC 03 | 100 | 23.3 | YST D3 | A | Fabrication | Engine Module | 10 Days | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | Medium | Rejected | Location conflict with another operation | Clear | 16 | TRUE | 63 |  | 2 | No |  | No Conflict | Yes
BK-0424 | 2026-05-02 | 2026-05-09 |  | 7 | Crane | Mobile Crane | MOB-14 | 100 | 40.4 | YST 02 | D | Outfitting | Construction Materials | Full Day | Day Shift (0700-1900) | Team Foxtrot | Lifting Supervisor | High | Completed |  | Heavy Rain | 13 | FALSE | 90 | On Time | 3 | No |  | No Conflict | Yes
BK-0425 | 2026-05-17 | 2026-05-21 |  | 4 | Crane | Level Luffing Crane | LLC 03 | 30 | 9.3 | YST D4 | C | Outfitting | Turret Assembly | 3 Days | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | Medium | Pending |  | Partly Cloudy | 16 | FALSE | 22 |  | 2 | No |  | No Conflict | Yes
BK-0426 | 2026-05-02 | 2026-05-04 |  | 2 | MEWP | Articulating Boom Lift 26m | MEWP-19 |  |  | YST 10 | C | Assembly | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Beta | Forklift Operator | Medium | Cancelled | Project postponed | High Wind | 41 | FALSE | 23 |  | 2 | No |  | No Conflict | Yes
BK-0427 | 2026-05-08 | 2026-05-14 |  | 6 | Forklift | Counterbalance Forklift | FLT-13 | 7 | 5 | YST 12 | F | Commissioning | Tool Containers | 3 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Cancelled | Budget constraint | High Wind | 44 | FALSE | 41 |  | 2 | No |  | No Conflict | Yes
BK-0428 | 2026-05-20 | 2026-05-24 |  | 4 | Crane | Level Luffing Crane | LLC 08 | 100 | 68.4 | YST 02 | B | Outfitting | Mooring Winch | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Medium | Cancelled | Material not ready | Overcast | 12 | FALSE | 31 |  | 2 | No |  | No Conflict | Yes
BK-0429 | 2026-05-27 | 2026-06-10 |  | 14 | Crane | Level Luffing Crane | LLC 04 | 50 | 15.2 | YST 01 | A | Planning | Transformer Unit | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Rigging Supervisor | High | Rejected | Insufficient lead time | Clear | 11 | FALSE | 55 |  | 3 | No |  | No Conflict | Yes
BK-0430 | 2026-05-08 | 2026-05-11 |  | 3 | Crane | Crawler Crane | CRA-05 | 50 | 29.8 | YST 01 | D | Fabrication | Flare Tower Section | 2 Days | Night Shift (1900-0700) | Team Alpha | Lifting Supervisor | Medium | Completed |  | Partly Cloudy | 13 | FALSE | 91 | Early | 2 | No |  | No Conflict | Yes
BK-0431 | 2026-05-29 | 2026-06-03 |  | 5 | Cometto | Cometto MSPE 8 Axle Lines | COM-04 |  |  | YST 03 | F | Fabrication | Hull Block Section | Full Day | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Completed |  | Thunderstorm | 26 | FALSE | 58 | Delayed | 2 | No |  | No Conflict | Yes
BK-0432 | 2026-05-11 | 2026-05-14 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-28 |  |  | YST 05 | D | Commissioning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Confirmed |  | Overcast | 7 | FALSE | 88 |  | 2 | No |  | No Conflict | Yes
BK-0433 | 2026-05-29 | 2026-06-05 | 2026-06-09 | 7 | MEWP | Telescopic Boom Lift 30m | MEWP-06 |  |  | YST D3 | D | Assembly | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Rescheduled | Operator reassigned | Overcast | 3 | FALSE | 35 |  | 2 | No |  | No Conflict | Yes
BK-0434 | 2026-05-07 | 2026-05-11 |  | 4 | Forklift | Heavy Duty Forklift | FLT-09 | 20 | 11.4 | YST 09 | D | Testing | Safety Equipment | 5 Days | Day Shift (0700-1900) | Team Echo | Advanced Operator | Medium | Pending |  | Overcast | 15 | FALSE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0435 | 2026-05-26 | 2026-06-01 |  | 6 | Crane | Level Luffing Crane | LLC 09 | 40 | 30.2 | YST 16 | E | Commissioning | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Pending |  | Clear | 10 | FALSE | 24 |  | 2 | No |  | No Conflict | Yes
BK-0436 | 2026-05-12 | 2026-05-13 |  | 1 | Crane | Goliath Gantry Crane | GC-15 | 300 | 198.6 | YST 04 | F | Testing | Accommodation Module | Full Day | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | Urgent | Rejected | Load exceeds crane capacity | Thunderstorm | 20 | FALSE | 45 |  | 4 | No |  | No Conflict | Yes
BK-0437 | 2026-05-31 | 2026-06-05 |  | 5 | MEWP | Scissor Lift 10m | MEWP-21 |  |  | YST D4 | F | Commissioning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Beta | Forklift Operator | Urgent | Completed |  | Clear | 9 | FALSE | 90 | Delayed | 4 | No |  | No Conflict | Yes
BK-0438 | 2026-05-15 | 2026-05-23 |  | 8 | MEWP | Scissor Lift 10m | MEWP-28 |  |  | YST 11 | E | Planning | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Foxtrot | Advanced Operator | Medium | Completed |  | Partly Cloudy | 6 | FALSE | 87 | On Time | 2 | No |  | No Conflict | Yes
BK-0439 | 2026-05-26 | 2026-06-03 |  | 8 | Crane | Goliath Gantry Crane | GC-17 | 400 | 216.4 | YST 04 | A | Fabrication | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | Medium | Confirmed |  | Clear | 12 | FALSE | 98 |  | 2 | No |  | No Conflict | Yes
BK-0440 | 2026-05-20 | 2026-05-27 |  | 7 | Crane | Mobile Crane | MOB-18 | 50 | 11 | YST 07 | C | Planning | Engine Module | 2 Days | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | High | Completed |  | Clear | 7 | FALSE | 71 | On Time | 3 | No |  | No Conflict | Yes
BK-0441 | 2026-05-07 | 2026-05-09 |  | 2 | Forklift | Telehandler Forklift | FLT-34 | 4 | 1.5 | YST 08 | D | Outfitting | Electrical Cables | Half Day (AM) | Day Shift (0700-1900) | Team Echo | Advanced Operator | Low | Completed |  | Clear | 5 | FALSE | 87 | On Time | 1 | No |  | No Conflict | Yes
BK-0442 | 2026-05-31 | 2026-06-11 |  | 11 | Crane | Goliath Gantry Crane | GC-18 | 300 | 238.4 | YST 04 | F | Outfitting | Flare Tower Section | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | High | Pending |  | Clear | 2 | FALSE | 45 |  | 3 | Yes | BK-0469 | Yielded to Higher Priority | No
BK-0443 | 2026-05-20 | 2026-05-30 | 2026-06-04 | 10 | MEWP | Telescopic Boom Lift 30m | MEWP-15 |  |  | YST D3 | C | Commissioning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Gamma | Advanced Operator | High | Rescheduled | Project timeline shifted | Light Rain | 11 | FALSE | 31 |  | 3 | No |  | No Conflict | Yes
BK-0444 | 2026-05-24 | 2026-05-29 |  | 5 | Crane | Workshop Crane | WOR-02 | 10 | 7.5 | YST 07 | F | Planning | Anchor Chain | Full Day | Night Shift (1900-0700) | Team Gamma | Advanced Crane Operator | Urgent | Pending |  | Overcast | 8 | FALSE | 68 |  | 4 | No |  | No Conflict | Yes
BK-0445 | 2026-05-18 | 2026-05-20 |  | 2 | Crane | Level Luffing Crane | LLC 15 | 300 | 121.9 | YST 11 | F | Commissioning | Anchor Chain | Full Day | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Medium | Confirmed |  | Overcast | 14 | FALSE | 52 |  | 2 | No |  | No Conflict | Yes
BK-0446 | 2026-05-13 | 2026-05-14 |  | 1 | Crane | Workshop Crane | WOR-15 | 10 | 7 | YST 14 | D | Fabrication | Workshop Equipment | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | High | Cancelled | Client cancelled | Partly Cloudy | 10 | FALSE | 58 |  | 3 | No |  | No Conflict | Yes
BK-0447 | 2026-05-04 | 2026-05-07 |  | 3 | Crane | Workshop Crane | WOR-01 | 20 | 14 | YST 09 | F | Testing | Engine Module | 5 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | Medium | Cancelled | Client cancelled | Clear | 3 | FALSE | 44 |  | 2 | No |  | No Conflict | Yes
BK-0448 | 2026-05-23 | 2026-05-27 |  | 4 | Crane | Level Luffing Crane | LLC 07 | 30 | 18.2 | YST 13 | A | Planning | Helideck Module | 7 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Medium | Confirmed |  | Partly Cloudy | 8 | FALSE | 96 |  | 2 | No |  | No Conflict | Yes
BK-0449 | 2026-05-04 | 2026-05-13 |  | 9 | Forklift | Heavy Duty Forklift | FLT-33 | 15 | 6.6 | YST 02 | E | Outfitting | Scaffolding Materials | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Cancelled | Duplicate booking | High Wind | 28 | FALSE | 31 |  | 3 | No |  | No Conflict | Yes
BK-0450 | 2026-05-01 | 2026-05-06 |  | 5 | Crane | Mobile Crane | MOB-03 | 50 | 39.5 | YST 08 | B | Outfitting | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | Medium | Confirmed |  | Partly Cloudy | 17 | FALSE | 74 |  | 2 | No |  | No Conflict | Yes
BK-0451 | 2026-05-26 | 2026-06-09 |  | 14 | Forklift | Heavy Duty Forklift | FLT-25 | 20 | 6.8 | YST 04 | F | Assembly | Paint Drums | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Confirmed |  | High Wind | 40 | FALSE | 98 |  | 2 | No |  | No Conflict | Yes
BK-0452 | 2026-05-19 | 2026-05-24 |  | 5 | MEWP | Boom Lift 20m | MEWP-08 |  |  | YST 01 | B | Testing | Personnel Access Work | Half Day (AM) | Night Shift (1900-0700) | Team Alpha | Advanced Operator | Medium | Cancelled | Duplicate booking | Clear | 6 | FALSE | 32 |  | 2 | No |  | No Conflict | Yes
BK-0453 | 2026-05-05 | 2026-05-10 |  | 5 | MEWP | Boom Lift 20m | MEWP-24 |  |  | YST D3 | E | Outfitting | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | High | Rejected | Weather conditions unsafe | Overcast | 11 | FALSE | 41 |  | 3 | No |  | No Conflict | Yes
BK-0454 | 2026-05-11 | 2026-05-14 |  | 3 | MEWP | Boom Lift 20m | MEWP-20 |  |  | YST 08 | D | Planning | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Confirmed |  | High Wind | 26 | FALSE | 49 |  | 2 | No |  | No Conflict | Yes
BK-0455 | 2026-05-31 | 2026-06-03 |  | 3 | Crane | Tower Crane | TOW-03 | 15 | 8.2 | YST 14 | B | Testing | Transformer Unit | 2 Days | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | High | Completed |  | Clear | 11 | FALSE | 52 | On Time | 3 | No |  | No Conflict | Yes
BK-0456 | 2026-05-26 | 2026-06-01 |  | 6 | Forklift | Telehandler Forklift | FLT-31 | 7 | 5.7 | YST 13 | D | Planning | PPE Supplies | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Confirmed |  | Light Rain | 15 | FALSE | 98 |  | 2 | No |  | No Conflict | Yes
BK-0457 | 2026-05-10 | 2026-05-17 |  | 7 | Crane | Workshop Crane | WOR-15 | 10 | 7.5 | YST 12 | B | Commissioning | Anchor Chain | Full Day | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | High | Confirmed |  | Partly Cloudy | 6 | FALSE | 95 |  | 3 | No |  | No Conflict | Yes
BK-0458 | 2026-05-17 | 2026-05-26 | 2026-06-01 | 9 | Crane | Mobile Crane | MOB-12 | 100 | 31.7 | YST 07 | A | Outfitting | Turret Assembly | 2 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Low | Rescheduled | Higher priority job took precedence | High Wind | 30 | FALSE | 68 |  | 1 | No |  | No Conflict | Yes
BK-0459 | 2026-05-12 | 2026-05-18 |  | 6 | MEWP | Articulating Boom Lift 26m | MEWP-21 |  |  | YST 02 | C | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Confirmed |  | Overcast | 2 | FALSE | 81 |  | 2 | No |  | No Conflict | Yes
BK-0460 | 2026-05-05 | 2026-05-09 |  | 4 | MEWP | Boom Lift 20m | MEWP-08 |  |  | YST 09 | F | Commissioning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Beta | Forklift Operator | Low | Rejected | Crane already booked | Thunderstorm | 32 | FALSE | 32 |  | 1 | No |  | No Conflict | Yes
BK-0461 | 2026-05-29 | 2026-06-03 |  | 5 | Forklift | Telehandler Forklift | FLT-38 | 5 | 3.7 | YST 17 | E | Assembly | Consumables Pallet | Full Day | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Urgent | Confirmed |  | Light Rain | 10 | FALSE | 65 |  | 4 | No |  | No Conflict | Yes
BK-0462 | 2026-05-23 | 2026-05-27 |  | 4 | Forklift | Reach Forklift | FLT-27 | 1.5 | 0.6 | YST 04 | B | Commissioning | Safety Equipment | 3 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Confirmed |  | Clear | 17 | FALSE | 68 |  | 2 | No |  | No Conflict | Yes
BK-0463 | 2026-05-19 | 2026-05-29 |  | 10 | Crane | Level Luffing Crane | LLC 14 | 40 | 9.5 | YST 07 | C | Planning | Accommodation Module | 2 Days | Night Shift (1900-0700) | Team Alpha | Basic Crane Operator | Urgent | Confirmed |  | Partly Cloudy | 10 | FALSE | 55 |  | 4 | No |  | No Conflict | Yes
BK-0464 | 2026-05-16 | 2026-05-22 |  | 6 | Forklift | Counterbalance Forklift | FLT-38 | 2.5 | 2.1 | YST 09 | E | Testing | Steel Plates | 5 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | Medium | Confirmed |  | High Wind | 33 | FALSE | 61 |  | 2 | No |  | No Conflict | Yes
BK-0465 | 2026-05-20 | 2026-05-25 |  | 5 | Crane | Crawler Crane | CRA-13 | 150 | 95.3 | YST 04 | A | Outfitting | Pipe Spool | 2 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | Urgent | Rejected | Insufficient lead time | Heavy Rain | 22 | TRUE | 27 |  | 4 | No |  | No Conflict | Yes
BK-0466 | 2026-05-28 | 2026-06-04 |  | 7 | Forklift | Heavy Duty Forklift | FLT-33 | 20 | 17.6 | YST 15 | A | Commissioning | Small Fittings Pallet | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Urgent | Rejected | Permit not approved | Partly Cloudy | 3 | TRUE | 51 |  | 4 | No |  | No Conflict | Yes
BK-0467 | 2026-05-13 | 2026-05-22 | 2026-05-24 | 9 | Forklift | Telehandler Forklift | FLT-25 | 7 | 5.4 | YST 16 | F | Testing | Insulation Materials | Full Day | Day Shift (0700-1900) | Team Beta | Advanced Operator | Urgent | Rescheduled | Client request | Clear | 17 | FALSE | 49 |  | 4 | No |  | No Conflict | Yes
BK-0468 | 2026-05-29 | 2026-06-03 | 2026-06-07 | 5 | Crane | Workshop Crane | WOR-06 | 10 | 7.4 | YST 11 | A | Fabrication | Mega Block Section | 5 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Medium | Rescheduled | Operator reassigned | Thunderstorm | 30 | FALSE | 62 |  | 2 | No |  | No Conflict | Yes
BK-0469 | 2026-05-31 | 2026-06-11 |  | 11 | Crane | Goliath Gantry Crane | GC-18 | 600 | 447.7 | YST 19 | E | Planning | Turret Assembly | Half Day (PM) | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Urgent | Rejected | Location conflict with another operation | Overcast | 14 | FALSE | 70 |  | 4 | Yes | BK-0442 | Priority Override | Yes
BK-0470 | 2026-05-18 | 2026-05-31 |  | 13 | Crane | Goliath Gantry Crane | GC-15 | 240 | 185.4 | YST 04 | A | Testing | Engine Module | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | High | Confirmed |  | Partly Cloudy | 12 | FALSE | 40 |  | 3 | No |  | No Conflict | Yes
BK-0471 | 2026-05-10 | 2026-05-12 |  | 2 | MEWP | Telescopic Boom Lift 30m | MEWP-11 |  |  | YST D2 | B | Planning | Personnel Access Work | 5 Days | Night Shift (1900-0700) | Team Beta | Advanced Operator | Medium | Cancelled | Duplicate booking | Partly Cloudy | 16 | FALSE | 34 |  | 2 | No |  | No Conflict | Yes
BK-0472 | 2026-05-16 | 2026-05-24 | 2026-05-26 | 8 | Crane | Crawler Crane | CRA-02 | 100 | 49.7 | YST D4 | F | Testing | Workshop Equipment | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Rescheduled | Material delivery delayed | Partly Cloudy | 8 | TRUE | 41 |  | 2 | No |  | No Conflict | Yes
BK-0473 | 2026-05-27 | 2026-06-04 |  | 8 | Forklift | Heavy Duty Forklift | FLT-32 | 10 | 7.1 | YST D8 | A | Testing | PPE Supplies | 5 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Urgent | Confirmed |  | Partly Cloudy | 15 | FALSE | 88 |  | 4 | No |  | No Conflict | Yes
BK-0474 | 2026-05-13 | 2026-05-18 |  | 5 | MEWP | Articulating Boom Lift 26m | MEWP-23 |  |  | YST 10 | E | Planning | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Echo | Advanced Operator | Medium | Confirmed |  | Light Rain | 11 | FALSE | 50 |  | 2 | No |  | No Conflict | Yes
BK-0475 | 2026-05-19 | 2026-05-22 |  | 3 | Cometto | SPMT 16 Axle Lines | COM-04 |  |  | YST 03 | E | Planning | Hull Block Section | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Low | Cancelled | Material not ready | Overcast | 6 | FALSE | 63 |  | 1 | No |  | No Conflict | Yes
BK-0476 | 2026-05-27 | 2026-05-30 |  | 3 | Crane | Crawler Crane | CRA-04 | 250 | 86.1 | YST 03 | F | Outfitting | Hull Block Section | 14 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Medium | Confirmed |  | Clear | 5 | FALSE | 84 |  | 2 | No |  | No Conflict | Yes
BK-0477 | 2026-05-20 | 2026-06-02 |  | 13 | Cometto | SPMT 24 Axle Lines | COM-08 |  |  | YST 20 | A | Planning | Engine Module | 7 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | High | Completed |  | Clear | 5 | FALSE | 82 | Early | 3 | No |  | No Conflict | Yes
BK-0478 | 2026-05-08 | 2026-05-09 | 2026-05-14 | 1 | MEWP | Telescopic Boom Lift 30m | MEWP-23 |  |  | YST 09 | F | Outfitting | Personnel Access Work | 5 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | Medium | Rescheduled | Weather delay | Clear | 6 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0479 | 2026-05-06 | 2026-05-11 |  | 5 | Cometto | SPMT 24 Axle Lines | COM-09 |  |  | YST 16 | F | Planning | Jacket Structure | 3 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Rejected | Crane already booked | Light Rain | 8 | TRUE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0480 | 2026-05-23 | 2026-05-26 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-02 |  |  | YST 04 | A | Planning | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Beta | Basic Operator | Low | Completed |  | High Wind | 41 | FALSE | 74 | On Time | 1 | No |  | No Conflict | Yes
BK-0481 | 2026-05-31 | 2026-06-08 | 2026-06-10 | 8 | Crane | Level Luffing Crane | LLC 18 | 300 | 183.8 | YST 10 | C | Testing | Workshop Equipment | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Rigging Supervisor | Medium | Rescheduled | Original date conflicts with maintenance | Partly Cloudy | 8 | TRUE | 32 |  | 2 | No |  | No Conflict | Yes
BK-0482 | 2026-05-10 | 2026-05-20 |  | 10 | Crane | Goliath Gantry Crane | GC-20 | 600 | 264 | YST 19 | C | Outfitting | Mega Block Section | 2 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Medium | Pending |  | Overcast | 7 | FALSE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0483 | 2026-05-22 | 2026-05-27 |  | 5 | Cometto | Cometto Eco500 12 Axle Lines | COM-11 |  |  | YST 02 | E | Testing | Mega Block Section | 5 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | High | Cancelled | Material not ready | Clear | 6 | FALSE | 44 |  | 3 | No |  | No Conflict | Yes
BK-0484 | 2026-05-01 | 2026-05-14 |  | 13 | Crane | Crawler Crane | CRA-18 | 50 | 18.2 | YST D1 | C | Fabrication | Engine Module | 2 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Completed |  | Heavy Rain | 17 | FALSE | 54 | On Time | 2 | No |  | No Conflict | Yes
BK-0485 | 2026-05-04 | 2026-05-13 |  | 9 | Crane | Tower Crane | TOW-16 | 25 | 9.8 | YST D8 | E | Planning | Flare Tower Section | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Urgent | Pending |  | Heavy Rain | 15 | FALSE | 31 |  | 4 | No |  | No Conflict | Yes
BK-0486 | 2026-05-12 | 2026-05-22 |  | 10 | Cometto | SPMT 24 Axle Lines | COM-03 |  |  | YST 15 | D | Testing | Jacket Structure | Full Day | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Confirmed |  | Overcast | 3 | FALSE | 80 |  | 2 | No |  | No Conflict | Yes
BK-0487 | 2026-05-12 | 2026-05-20 | 2026-05-27 | 8 | Crane | Tower Crane | TOW-15 | 40 | 15.3 | YST D3 | E | Commissioning | Structural Steel Module | 14 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | Medium | Rescheduled | Higher priority job took precedence | Heavy Rain | 17 | FALSE | 40 |  | 2 | No |  | No Conflict | Yes
BK-0488 | 2026-05-03 | 2026-05-10 |  | 7 | Crane | Goliath Gantry Crane | GC-01 | 200 | 97.6 | YST 01 | D | Commissioning | Construction Materials | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | High | Confirmed |  | Partly Cloudy | 6 | FALSE | 83 |  | 3 | No |  | No Conflict | Yes
BK-0489 | 2026-05-29 | 2026-06-05 |  | 7 | Crane | Level Luffing Crane | LLC 15A | 300 | 183.1 | YST 07 | F | Commissioning | Riser Assembly | Half Day (AM) | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | High | Completed |  | High Wind | 41 | FALSE | 68 | Early | 3 | Yes | BK-0505 | Priority Override | Yes
BK-0490 | 2026-05-22 | 2026-06-03 |  | 12 | Forklift | Heavy Duty Forklift | FLT-09 | 15 | 12 | YST 03 | A | Assembly | Bolt Pallets | 3 Days | Night Shift (1900-0700) | Team Delta | MEWP Operator | Medium | Confirmed |  | Thunderstorm | 27 | FALSE | 94 |  | 2 | No |  | No Conflict | Yes
BK-0491 | 2026-05-04 | 2026-05-08 | 2026-05-11 | 4 | MEWP | Articulating Boom Lift 26m | MEWP-01 |  |  | YST 07 | F | Testing | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Beta | MEWP Operator | Urgent | Rescheduled | Permit delay | Light Rain | 3 | FALSE | 23 |  | 4 | No |  | No Conflict | Yes
BK-0492 | 2026-05-01 | 2026-05-08 |  | 7 | Crane | Crawler Crane | CRA-06 | 50 | 10.2 | YST 01 | E | Fabrication | Pipe Spool | 2 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Confirmed |  | Partly Cloudy | 17 | FALSE | 56 |  | 2 | No |  | No Conflict | Yes
BK-0493 | 2026-05-08 | 2026-05-14 |  | 6 | Crane | Crawler Crane | CRA-09 | 250 | 66.6 | YST 03 | D | Planning | Transformer Unit | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Medium | Completed |  | Partly Cloudy | 8 | FALSE | 48 | On Time | 2 | No |  | No Conflict | Yes
BK-0494 | 2026-05-24 | 2026-05-28 |  | 4 | Crane | Workshop Crane | WOR-09 | 10 | 2.8 | YST D6 | C | Outfitting | Workshop Equipment | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | High | Cancelled | Client cancelled | Partly Cloudy | 14 | FALSE | 28 |  | 3 | No |  | No Conflict | Yes
BK-0495 | 2026-05-05 | 2026-05-09 |  | 4 | Crane | Workshop Crane | WOR-11 | 10 | 5.7 | YST 02 | D | Planning | Workshop Equipment | 2 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Medium | Completed |  | Light Rain | 9 | FALSE | 51 | On Time | 2 | No |  | No Conflict | Yes
BK-0496 | 2026-05-25 | 2026-05-27 |  | 2 | Crane | Workshop Crane | WOR-16 | 10 | 3.4 | YST D3 | B | Testing | Mega Block Section | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Crane Operator | High | Cancelled | Client cancelled | Overcast | 6 | FALSE | 37 |  | 3 | No |  | No Conflict | Yes
BK-0497 | 2026-05-07 | 2026-05-19 |  | 12 | Crane | Tower Crane | TOW-02 | 15 | 6.8 | YST 10 | C | Outfitting | Flare Tower Section | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | High | Completed |  | Partly Cloudy | 18 | FALSE | 47 | On Time | 3 | No |  | No Conflict | Yes
BK-0498 | 2026-05-09 | 2026-05-21 |  | 12 | Cometto | Cometto Eco500 12 Axle Lines | COM-03 |  |  | YST 13 | C | Testing | Engine Module | Half Day (AM) | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Completed |  | Clear | 7 | FALSE | 71 | On Time | 2 | No |  | No Conflict | Yes
BK-0499 | 2026-05-10 | 2026-05-12 |  | 2 | Cometto | Cometto Eco500 12 Axle Lines | COM-12 |  |  | YST 13 | F | Assembly | Mega Block Section | 5 Days | Night Shift (1900-0700) | Team Echo | Basic Operator | Medium | Completed |  | Clear | 14 | FALSE | 46 | On Time | 2 | No |  | No Conflict | Yes
BK-0500 | 2026-05-24 | 2026-05-31 |  | 7 | Crane | Workshop Crane | WOR-15 | 10 | 2.3 | YST 10 | D | Fabrication | Turret Assembly | 7 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | High | Completed |  | Partly Cloudy | 6 | FALSE | 75 | Delayed | 3 | No |  | No Conflict | Yes
BK-0501 | 2026-05-29 | 2026-06-09 |  | 11 | Forklift | Telehandler Forklift | FLT-28 | 5 | 1.6 | YST 15 | C | Commissioning | Insulation Materials | Half Day (AM) | Day Shift (0700-1900) | Team Echo | Forklift Operator | High | Confirmed |  | High Wind | 34 | FALSE | 90 |  | 3 | No |  | No Conflict | Yes
BK-0502 | 2026-05-23 | 2026-05-26 |  | 3 | Forklift | Reach Forklift | FLT-33 | 1.5 | 1.2 | YST 06 | A | Fabrication | Timber Dunnage | 2 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | High | Completed |  | Overcast | 2 | FALSE | 69 | Delayed | 3 | No |  | No Conflict | Yes
BK-0503 | 2026-05-24 | 2026-05-30 |  | 6 | Crane | Goliath Gantry Crane | GC-19 | 300 | 217.2 | YST 19 | B | Assembly | Accommodation Module | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Medium | Confirmed |  | Thunderstorm | 28 | FALSE | 55 |  | 2 | No |  | No Conflict | Yes
BK-0504 | 2026-05-27 | 2026-05-30 |  | 3 | Crane | Workshop Crane | WOR-03 | 20 | 11.5 | YST 15 | E | Assembly | Pipe Spool | 10 Days | Night Shift (1900-0700) | Team Gamma | Basic Crane Operator | High | Completed |  | Partly Cloudy | 3 | FALSE | 62 | On Time | 3 | Yes | BK-0550 | First-Come-First-Served | Yes
BK-0505 | 2026-05-31 | 2026-06-04 |  | 4 | Crane | Level Luffing Crane | LLC 15A | 300 | 99.7 | YST D3 | E | Testing | Engine Module | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Cancelled | Budget constraint | Clear | 16 | FALSE | 60 |  | 2 | Yes | BK-0489 | Yielded to Higher Priority | No
BK-0506 | 2026-05-26 | 2026-06-05 |  | 10 | Crane | Mobile Crane | MOB-05 | 50 | 29.4 | YST 07 | B | Fabrication | Pipe Spool | 7 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Medium | Rejected | Insufficient lead time | Overcast | 7 | FALSE | 45 |  | 2 | No |  | No Conflict | Yes
BK-0507 | 2026-05-22 | 2026-05-29 |  | 7 | Crane | Level Luffing Crane | LLC 21 | 100 | 21.2 | YST 08 | A | Testing | Mooring Winch | 10 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Medium | Rejected | Crane under scheduled maintenance | Clear | 14 | TRUE | 69 |  | 2 | No |  | No Conflict | Yes
BK-0508 | 2026-05-03 | 2026-05-07 |  | 4 | Forklift | Counterbalance Forklift | FLT-35 | 2.5 | 1.2 | YST D6 | E | Outfitting | Insulation Materials | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Low | Confirmed |  | Light Rain | 11 | FALSE | 43 |  | 1 | Yes | BK-0401 | Yielded to Higher Priority | No
BK-0509 | 2026-05-18 | 2026-05-26 |  | 8 | MEWP | Scissor Lift 10m | MEWP-27 |  |  | YST 01 | B | Planning | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Rejected | Location conflict with another operation | Thunderstorm | 20 | TRUE | 61 |  | 2 | No |  | No Conflict | Yes
BK-0510 | 2026-05-10 | 2026-05-13 |  | 3 | Forklift | Reach Forklift | FLT-08 | 1.5 | 1.3 | YST 16 | A | Assembly | PPE Supplies | Full Day | Night Shift (1900-0700) | Team Gamma | Forklift Operator | Medium | Cancelled | Project postponed | Thunderstorm | 22 | FALSE | 47 |  | 2 | No |  | No Conflict | Yes
BK-0511 | 2026-05-17 | 2026-05-21 |  | 4 | Crane | Mobile Crane | MOB-10 | 50 | 33.7 | YST D8 | C | Assembly | Workshop Equipment | 3 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Medium | Completed |  | Light Rain | 4 | FALSE | 49 | Delayed | 2 | No |  | No Conflict | Yes
BK-0512 | 2026-05-05 | 2026-05-09 | 2026-05-12 | 4 | Crane | Workshop Crane | WOR-19 | 20 | 9.1 | YST 06 | B | Outfitting | Engine Module | 2 Days | Night Shift (1900-0700) | Team Beta | Heavy Lift Specialist | Low | Rescheduled | Material delivery delayed | Partly Cloudy | 17 | FALSE | 60 |  | 1 | No |  | No Conflict | Yes
BK-0513 | 2026-05-05 | 2026-05-15 |  | 10 | Cometto | Cometto Eco500 12 Axle Lines | COM-09 |  |  | YST 14 | A | Testing | Offshore Platform Topside | 3 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Completed |  | Overcast | 18 | FALSE | 84 | Delayed | 2 | No |  | No Conflict | Yes
BK-0514 | 2026-05-08 | 2026-05-16 |  | 8 | Crane | Level Luffing Crane | LLC 18 | 40 | 13.8 | YST 01 | B | Assembly | Pipe Spool | 3 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Low | Completed |  | Partly Cloudy | 15 | FALSE | 43 | Delayed | 1 | No |  | No Conflict | Yes
BK-0515 | 2026-05-04 | 2026-05-17 |  | 13 | Cometto | SPMT 24 Axle Lines | COM-12 |  |  | YST 19 | D | Testing | Engine Module | 10 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Pending |  | Heavy Rain | 10 | FALSE | 29 |  | 2 | No |  | No Conflict | Yes
BK-0516 | 2026-05-03 | 2026-05-06 |  | 3 | Crane | Mobile Crane | MOB-05 | 50 | 13.3 | YST 03 | D | Commissioning | Mooring Winch | 5 Days | Day Shift (0700-1900) | Team Gamma | Basic Crane Operator | Medium | Cancelled | Client cancelled | Overcast | 11 | FALSE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0517 | 2026-05-25 | 2026-05-28 |  | 3 | Crane | Mobile Crane | MOB-15 | 100 | 51.3 | YST D8 | D | Fabrication | Riser Assembly | 3 Days | Night Shift (1900-0700) | Team Echo | Lifting Supervisor | Medium | Cancelled | Project postponed | Clear | 4 | FALSE | 67 |  | 2 | No |  | No Conflict | Yes
BK-0518 | 2026-05-07 | 2026-05-12 |  | 5 | Crane | Mobile Crane | MOB-03 | 50 | 29.4 | YST D1 | D | Fabrication | Construction Materials | 5 Days | Day Shift (0700-1900) | Team Gamma | Basic Crane Operator | High | Completed |  | Clear | 13 | FALSE | 46 | On Time | 3 | No |  | No Conflict | Yes
BK-0519 | 2026-05-12 | 2026-05-19 |  | 7 | Forklift | Counterbalance Forklift | FLT-35 | 3 | 1.3 | YST 10 | E | Fabrication | PPE Supplies | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Basic Operator | High | Completed |  | Overcast | 3 | FALSE | 76 | Delayed | 3 | No |  | No Conflict | Yes
BK-0520 | 2026-05-19 | 2026-06-02 | 2026-06-05 | 14 | MEWP | Scissor Lift 10m | MEWP-03 |  |  | YST 11 | E | Fabrication | Personnel Access Work | 10 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | High | Rescheduled | Project timeline shifted | Partly Cloudy | 14 | FALSE | 26 |  | 3 | No |  | No Conflict | Yes
BK-0521 | 2026-05-14 | 2026-05-25 |  | 11 | MEWP | Boom Lift 20m | MEWP-19 |  |  | YST 01 | D | Planning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Confirmed |  | Heavy Rain | 12 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0522 | 2026-05-29 | 2026-06-01 |  | 3 | Cometto | Cometto Eco500 12 Axle Lines | COM-09 |  |  | YST 20 | D | Fabrication | Hull Block Section | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Medium | Rejected | Location conflict with another operation | Partly Cloudy | 13 | TRUE | 65 |  | 2 | No |  | No Conflict | Yes
BK-0523 | 2026-05-25 | 2026-06-02 | 2026-06-05 | 8 | Crane | Tower Crane | TOW-16 | 10 | 3 | YST 12 | A | Outfitting | Construction Materials | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Medium | Rescheduled | Weather delay | Clear | 12 | TRUE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0524 | 2026-05-03 | 2026-05-05 | 2026-05-09 | 2 | Cometto | SPMT 24 Axle Lines | COM-05 |  |  | YST 05 | D | Planning | Offshore Platform Topside | 5 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | Urgent | Rescheduled | Permit delay | Partly Cloudy | 11 | FALSE | 28 |  | 4 | No |  | No Conflict | Yes
BK-0525 | 2026-05-12 | 2026-05-18 | 2026-05-19 | 6 | MEWP | Articulating Boom Lift 26m | MEWP-03 |  |  | YST 12 | A | Testing | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Urgent | Rescheduled | Operator reassigned | High Wind | 26 | FALSE | 55 |  | 4 | No |  | No Conflict | Yes
BK-0526 | 2026-05-05 | 2026-05-15 |  | 10 | Crane | Goliath Gantry Crane | GC-10 | 600 | 159.3 | YST 04 | F | Testing | Flare Tower Section | Full Day | Night Shift (1900-0700) | Team Foxtrot | Advanced Crane Operator | Low | Completed |  | Thunderstorm | 34 | FALSE | 46 | Early | 1 | No |  | No Conflict | Yes
BK-0527 | 2026-05-30 | 2026-06-04 |  | 5 | Crane | Mobile Crane | MOB-11 | 75 | 21.5 | YST 02 | D | Planning | Pipe Spool | 14 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | High | Confirmed |  | Partly Cloudy | 17 | FALSE | 76 |  | 3 | No |  | No Conflict | Yes
BK-0528 | 2026-05-02 | 2026-05-16 |  | 14 | Forklift | Counterbalance Forklift | FLT-31 | 5 | 1.9 | YST D6 | C | Assembly | Scaffolding Materials | Full Day | Day Shift (0700-1900) | Team Alpha | Basic Operator | Urgent | Cancelled | Client cancelled | Overcast | 4 | FALSE | 39 |  | 4 | Yes | BK-0345 | Priority Override | Yes
BK-0529 | 2026-06-28 | 2026-07-03 | 2026-07-08 | 5 | Crane | Crawler Crane | CRA-14 | 100 | 77.9 | YST 01 | D | Outfitting | Engine Module | 2 Days | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | Medium | Rescheduled | Permit delay | Partly Cloudy | 7 | FALSE | 20 |  | 2 | No |  | No Conflict | Yes
BK-0530 | 2026-06-26 | 2026-07-07 |  | 11 | Crane | Workshop Crane | WOR-11 | 10 | 7.9 | YST 14 | F | Outfitting | Workshop Equipment | Half Day (AM) | Night Shift (1900-0700) | Team Beta | Lifting Supervisor | Medium | Completed |  | Clear | 2 | FALSE | 94 | On Time | 2 | No |  | No Conflict | Yes
BK-0531 | 2026-06-15 | 2026-06-22 |  | 7 | MEWP | Scissor Lift 10m | MEWP-24 |  |  | YST 07 | B | Assembly | Personnel Access Work | 10 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Cancelled | Budget constraint | Clear | 8 | FALSE | 20 |  | 3 | No |  | No Conflict | Yes
BK-0532 | 2026-06-12 | 2026-06-22 | 2026-06-26 | 10 | Crane | Crawler Crane | CRA-15 | 50 | 22.9 | YST D4 | C | Planning | Mooring Winch | 2 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | Medium | Rescheduled | Permit delay | Thunderstorm | 34 | TRUE | 47 |  | 2 | No |  | No Conflict | Yes
BK-0533 | 2026-06-10 | 2026-06-20 |  | 10 | Cometto | SPMT 24 Axle Lines | COM-12 |  |  | YST 18 | A | Planning | Mega Block Section | 3 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Urgent | Rejected | Safety inspection required first | Overcast | 15 | FALSE | 26 |  | 4 | No |  | No Conflict | Yes
BK-0534 | 2026-06-21 | 2026-06-26 |  | 5 | MEWP | Scissor Lift 10m | MEWP-28 |  |  | YST 10 | D | Planning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | High | Confirmed |  | Partly Cloudy | 16 | FALSE | 92 |  | 3 | No |  | No Conflict | Yes
BK-0535 | 2026-06-21 | 2026-06-29 | 2026-07-06 | 8 | Cometto | Cometto MSPE 8 Axle Lines | COM-09 |  |  | YST 13 | D | Commissioning | Hull Block Section | Full Day | Night Shift (1900-0700) | Team Gamma | Basic Operator | Medium | Rescheduled | Original date conflicts with maintenance | Clear | 15 | TRUE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0536 | 2026-06-27 | 2026-07-03 |  | 6 | Cometto | SPMT 16 Axle Lines | COM-10 |  |  | YST 13 | A | Testing | Hull Block Section | 14 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Medium | Cancelled | Project postponed | Partly Cloudy | 14 | FALSE | 45 |  | 2 | No |  | No Conflict | Yes
BK-0537 | 2026-06-29 | 2026-07-03 |  | 4 | Crane | Goliath Gantry Crane | GC-13 | 200 | 64.5 | YST 19 | C | Testing | Helideck Module | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Cancelled | Material not ready | Clear | 12 | FALSE | 20 |  | 3 | No |  | No Conflict | Yes
BK-0538 | 2026-06-21 | 2026-06-30 |  | 9 | Crane | Tower Crane | TOW-01 | 10 | 3.8 | YST D8 | B | Fabrication | Anchor Chain | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Rejected | Weather conditions unsafe | Overcast | 9 | FALSE | 70 |  | 3 | No |  | No Conflict | Yes
BK-0539 | 2026-06-13 | 2026-06-22 | 2026-06-29 | 9 | Cometto | SPMT 16 Axle Lines | COM-11 |  |  | YST 02 | A | Planning | Hull Block Section | Half Day (AM) | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Medium | Rescheduled | Weather delay | Clear | 10 | TRUE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0540 | 2026-06-07 | 2026-06-12 |  | 5 | MEWP | Scissor Lift 10m | MEWP-03 |  |  | YST D2 | C | Commissioning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | High | Completed |  | Thunderstorm | 25 | FALSE | 40 | Early | 3 | No |  | No Conflict | Yes
BK-0541 | 2026-06-22 | 2026-06-29 |  | 7 | MEWP | Scissor Lift 10m | MEWP-11 |  |  | YST 04 | E | Commissioning | Personnel Access Work | 14 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Confirmed |  | Clear | 5 | FALSE | 41 |  | 3 | No |  | No Conflict | Yes
BK-0542 | 2026-06-18 | 2026-06-19 |  | 1 | MEWP | Boom Lift 20m | MEWP-28 |  |  | YST 07 | F | Commissioning | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Completed |  | High Wind | 33 | FALSE | 52 | Early | 2 | No |  | No Conflict | Yes
BK-0543 | 2026-06-12 | 2026-06-20 |  | 8 | Cometto | SPMT 24 Axle Lines | COM-07 |  |  | YST 19 | F | Assembly | Offshore Platform Topside | 3 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Confirmed |  | High Wind | 28 | FALSE | 89 |  | 2 | No |  | No Conflict | Yes
BK-0544 | 2026-06-19 | 2026-06-23 |  | 4 | Forklift | Reach Forklift | FLT-39 | 3 | 1.7 | YST 15 | B | Testing | Scaffolding Materials | 5 Days | Night Shift (1900-0700) | Team Echo | MEWP Operator | Medium | Completed |  | Partly Cloudy | 4 | FALSE | 72 | On Time | 2 | No |  | No Conflict | Yes
BK-0545 | 2026-06-14 | 2026-06-18 |  | 4 | Forklift | Telehandler Forklift | FLT-12 | 7 | 2.6 | YST 01 | F | Assembly | Insulation Materials | 5 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | Medium | Confirmed |  | Partly Cloudy | 12 | FALSE | 40 |  | 2 | No |  | No Conflict | Yes
BK-0546 | 2026-06-23 | 2026-06-27 |  | 4 | MEWP | Articulating Boom Lift 26m | MEWP-18 |  |  | YST 08 | C | Commissioning | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Confirmed |  | Overcast | 4 | FALSE | 81 |  | 2 | No |  | No Conflict | Yes
BK-0547 | 2026-06-14 | 2026-06-22 |  | 8 | Crane | Crawler Crane | CRA-16 | 100 | 54.6 | YST 04 | E | Assembly | Hull Block Section | 3 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Medium | Completed |  | Overcast | 9 | FALSE | 81 | Delayed | 2 | No |  | No Conflict | Yes
BK-0548 | 2026-06-19 | 2026-07-03 |  | 14 | Forklift | Telehandler Forklift | FLT-03 | 4 | 2.9 | YST D7 | D | Planning | Consumables Pallet | 7 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Confirmed |  | Light Rain | 15 | FALSE | 88 |  | 2 | No |  | No Conflict | Yes
BK-0549 | 2026-06-12 | 2026-06-17 |  | 5 | MEWP | Articulating Boom Lift 26m | MEWP-20 |  |  | YST D4 | A | Assembly | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Delta | Basic Operator | Medium | Cancelled | Client cancelled | High Wind | 28 | FALSE | 20 |  | 2 | No |  | No Conflict | Yes
BK-0550 | 2026-06-05 | 2026-06-07 |  | 2 | Crane | Workshop Crane | WOR-03 | 20 | 14.6 | YST 11 | A | Commissioning | Structural Steel Module | Full Day | Night Shift (1900-0700) | Team Gamma | Basic Crane Operator | High | Pending |  | Heavy Rain | 18 | FALSE | 23 |  | 3 | Yes | BK-0504 | Later Request - Reassigned | No
BK-0551 | 2026-06-10 | 2026-06-12 | 2026-06-15 | 2 | Crane | Tower Crane | TOW-06 | 40 | 20.5 | YST 16 | E | Outfitting | Turret Assembly | 7 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Medium | Rescheduled | Safety stand-down | Overcast | 5 | FALSE | 37 |  | 2 | No |  | No Conflict | Yes
BK-0552 | 2026-06-25 | 2026-07-04 | 2026-07-06 | 9 | Crane | Crawler Crane | CRA-12 | 150 | 35.4 | YST D4 | F | Planning | Engine Module | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Crane Operator | High | Rescheduled | Operator reassigned | Clear | 17 | FALSE | 44 |  | 3 | No |  | No Conflict | Yes
BK-0553 | 2026-06-16 | 2026-06-18 |  | 2 | Crane | Tower Crane | TOW-15 | 25 | 12.7 | YST 16 | C | Outfitting | Turret Assembly | 3 Days | Night Shift (1900-0700) | Team Alpha | Rigging Supervisor | Urgent | Completed |  | High Wind | 44 | FALSE | 52 | On Time | 4 | No |  | No Conflict | Yes
BK-0554 | 2026-06-14 | 2026-06-17 |  | 3 | Crane | Tower Crane | TOW-04 | 10 | 2.7 | YST 12 | F | Testing | Mooring Winch | 5 Days | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Medium | Confirmed |  | Partly Cloudy | 10 | FALSE | 62 |  | 2 | No |  | No Conflict | Yes
BK-0555 | 2026-06-14 | 2026-06-17 |  | 3 | Crane | Mobile Crane | MOB-09 | 75 | 38.8 | YST 01 | C | Fabrication | Mooring Winch | 2 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Completed |  | Partly Cloudy | 10 | FALSE | 67 | On Time | 3 | No |  | No Conflict | Yes
BK-0556 | 2026-06-02 | 2026-06-09 | 2026-06-16 | 7 | Forklift | Heavy Duty Forklift | FLT-37 | 10 | 3.6 | YST 02 | F | Commissioning | Pipe Bundles | Full Day | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Rescheduled | Higher priority job took precedence | Partly Cloudy | 14 | FALSE | 30 |  | 2 | Yes | BK-0601 | First-Come-First-Served | Yes
BK-0557 | 2026-06-07 | 2026-06-11 | 2026-06-17 | 4 | Crane | Tower Crane | TOW-06 | 25 | 7.5 | YST 09 | F | Fabrication | Engine Module | 3 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | High | Rescheduled | Safety stand-down | Clear | 4 | TRUE | 20 |  | 3 | No |  | No Conflict | Yes
BK-0558 | 2026-06-16 | 2026-06-21 | 2026-06-28 | 5 | Crane | Crawler Crane | CRA-01 | 50 | 27 | YST 03 | D | Planning | Workshop Equipment | 3 Days | Night Shift (1900-0700) | Team Echo | Lifting Supervisor | Low | Rescheduled | Operator reassigned | Clear | 2 | FALSE | 30 |  | 1 | No |  | No Conflict | Yes
BK-0559 | 2026-06-05 | 2026-06-14 |  | 9 | Crane | Workshop Crane | WOR-12 | 20 | 13.3 | YST D5 | C | Assembly | Mooring Winch | 14 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Completed |  | Overcast | 18 | FALSE | 97 | Delayed | 2 | Yes | BK-0561 | Yielded to Higher Priority | No
BK-0560 | 2026-06-16 | 2026-06-18 |  | 2 | Cometto | Cometto MSPE 8 Axle Lines | COM-04 |  |  | YST 03 | F | Outfitting | Offshore Platform Topside | 3 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Low | Pending |  | Partly Cloudy | 4 | FALSE | 44 |  | 1 | No |  | No Conflict | Yes
BK-0561 | 2026-06-21 | 2026-06-23 |  | 2 | Crane | Workshop Crane | WOR-12 | 20 | 14 | YST 09 | B | Planning | Accommodation Module | 7 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Urgent | Completed |  | Overcast | 12 | FALSE | 90 | On Time | 4 | Yes | BK-0559 | Priority Override | Yes
BK-0562 | 2026-06-26 | 2026-07-05 |  | 9 | Crane | Level Luffing Crane | LLC 22 | 100 | 20.9 | YST 05 | D | Assembly | Mooring Winch | Half Day (PM) | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | High | Confirmed |  | Clear | 11 | FALSE | 58 |  | 3 | No |  | No Conflict | Yes
BK-0563 | 2026-06-27 | 2026-07-04 |  | 7 | Crane | Crawler Crane | CRA-01 | 50 | 14.3 | YST 07 | E | Fabrication | Pipe Spool | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | High | Pending |  | High Wind | 33 | FALSE | 47 |  | 3 | No |  | No Conflict | Yes
BK-0564 | 2026-06-19 | 2026-07-01 | 2026-07-03 | 12 | Crane | Level Luffing Crane | LLC 22 | 100 | 60.7 | YST 12 | E | Assembly | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Urgent | Rescheduled | Permit delay | Clear | 15 | TRUE | 69 |  | 4 | No |  | No Conflict | Yes
BK-0565 | 2026-06-09 | 2026-06-12 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-03 |  |  | YST 10 | D | Planning | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Delta | Forklift Operator | Medium | Completed |  | Clear | 16 | FALSE | 72 | Early | 2 | No |  | No Conflict | Yes
BK-0566 | 2026-06-23 | 2026-06-28 |  | 5 | Crane | Mobile Crane | MOB-01 | 100 | 27.6 | YST 07 | C | Fabrication | Mooring Winch | 7 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Low | Confirmed |  | Overcast | 13 | FALSE | 76 |  | 1 | No |  | No Conflict | Yes
BK-0567 | 2026-06-29 | 2026-07-03 |  | 4 | Forklift | Reach Forklift | FLT-30 | 2 | 1.6 | YST 13 | C | Commissioning | Steel Plates | 5 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | High | Confirmed |  | Clear | 5 | FALSE | 84 |  | 3 | No |  | No Conflict | Yes
BK-0568 | 2026-06-11 | 2026-06-22 |  | 11 | Crane | Tower Crane | TOW-05 | 10 | 6.8 | YST 14 | B | Assembly | Transformer Unit | 3 Days | Night Shift (1900-0700) | Team Beta | Heavy Lift Specialist | Medium | Cancelled | Project postponed | Overcast | 2 | FALSE | 27 |  | 2 | No |  | No Conflict | Yes
BK-0569 | 2026-06-03 | 2026-06-04 |  | 1 | MEWP | Scissor Lift 10m | MEWP-08 |  |  | YST 04 | A | Assembly | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Confirmed |  | Partly Cloudy | 7 | FALSE | 93 |  | 2 | No |  | No Conflict | Yes
BK-0570 | 2026-06-28 | 2026-07-05 |  | 7 | Forklift | Reach Forklift | FLT-02 | 1.5 | 0.7 | YST 14 | F | Testing | Welding Materials | Full Day | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Medium | Pending |  | Clear | 17 | FALSE | 57 |  | 2 | No |  | No Conflict | Yes
BK-0571 | 2026-06-16 | 2026-06-21 |  | 5 | Crane | Mobile Crane | MOB-14 | 25 | 5.6 | YST 08 | C | Planning | Anchor Chain | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | High | Confirmed |  | Overcast | 16 | FALSE | 48 |  | 3 | No |  | No Conflict | Yes
BK-0572 | 2026-06-15 | 2026-06-26 |  | 11 | MEWP | Scissor Lift 10m | MEWP-12 |  |  | YST 06 | D | Testing | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Beta | Advanced Operator | Medium | Cancelled | Budget constraint | Clear | 6 | FALSE | 41 |  | 2 | No |  | No Conflict | Yes
BK-0573 | 2026-06-15 | 2026-06-23 |  | 8 | Forklift | Telehandler Forklift | FLT-31 | 5 | 3.6 | YST 13 | E | Commissioning | Safety Equipment | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Cancelled | Budget constraint | Partly Cloudy | 6 | FALSE | 42 |  | 2 | No |  | No Conflict | Yes
BK-0574 | 2026-06-19 | 2026-06-26 |  | 7 | Crane | Level Luffing Crane | LLC 04 | 30 | 19.1 | YST 06 | F | Fabrication | Mega Block Section | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Medium | Rejected | Location conflict with another operation | Clear | 7 | FALSE | 23 |  | 2 | No |  | No Conflict | Yes
BK-0575 | 2026-06-20 | 2026-06-24 |  | 4 | Crane | Workshop Crane | WOR-12 | 10 | 5.3 | YST D5 | D | Fabrication | Helideck Module | 3 Days | Night Shift (1900-0700) | Team Beta | Basic Crane Operator | Medium | Cancelled | Material not ready | High Wind | 43 | FALSE | 48 |  | 2 | No |  | No Conflict | Yes
BK-0576 | 2026-06-22 | 2026-06-26 |  | 4 | Crane | Goliath Gantry Crane | GC-14 | 400 | 216.4 | YST 19 | B | Planning | Helideck Module | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Lifting Supervisor | Low | Confirmed |  | Partly Cloudy | 15 | FALSE | 61 |  | 1 | No |  | No Conflict | Yes
BK-0577 | 2026-06-06 | 2026-06-14 |  | 8 | Forklift | Reach Forklift | FLT-37 | 2 | 1.6 | YST D7 | B | Planning | Tool Containers | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | High | Pending |  | Partly Cloudy | 14 | FALSE | 28 |  | 3 | No |  | No Conflict | Yes
BK-0578 | 2026-06-26 | 2026-07-02 |  | 6 | Crane | Mobile Crane | MOB-18 | 50 | 39 | YST 01 | F | Assembly | Construction Materials | 2 Days | Day Shift (0700-1900) | Team Gamma | Basic Crane Operator | Urgent | Completed |  | Clear | 7 | FALSE | 76 | On Time | 4 | No |  | No Conflict | Yes
BK-0579 | 2026-06-17 | 2026-06-29 | 2026-07-01 | 12 | MEWP | Telescopic Boom Lift 30m | MEWP-18 |  |  | YST 02 | F | Planning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Urgent | Rescheduled | Equipment breakdown | Clear | 15 | FALSE | 23 |  | 4 | No |  | No Conflict | Yes
BK-0580 | 2026-06-07 | 2026-06-14 |  | 7 | Cometto | Cometto MSPE 8 Axle Lines | COM-02 |  |  | YST 04 | A | Assembly | Offshore Platform Topside | 5 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | High | Rejected | Safety inspection required first | High Wind | 38 | FALSE | 55 |  | 3 | No |  | No Conflict | Yes
BK-0581 | 2026-06-16 | 2026-06-28 |  | 12 | Crane | Level Luffing Crane | LLC 17 | 30 | 19.9 | YST 02 | B | Planning | Mooring Winch | Full Day | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Rejected | Project schedule changed | High Wind | 25 | FALSE | 44 |  | 2 | No |  | No Conflict | Yes
BK-0582 | 2026-06-22 | 2026-06-30 |  | 8 | Crane | Mobile Crane | MOB-13 | 25 | 10.3 | YST 07 | A | Testing | Helideck Module | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Confirmed |  | High Wind | 36 | FALSE | 98 |  | 2 | No |  | No Conflict | Yes
BK-0583 | 2026-06-02 | 2026-06-05 |  | 3 | Crane | Level Luffing Crane | LLC 16A | 40 | 9.4 | YST 15 | F | Fabrication | Turret Assembly | 7 Days | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Low | Rejected | Operator not available | Light Rain | 4 | TRUE | 42 |  | 1 | No |  | No Conflict | Yes
BK-0584 | 2026-06-20 | 2026-06-28 |  | 8 | Crane | Crawler Crane | CRA-16 | 100 | 73.9 | YST D2 | D | Commissioning | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Medium | Pending |  | Overcast | 13 | FALSE | 48 |  | 2 | No |  | No Conflict | Yes
BK-0585 | 2026-06-23 | 2026-06-27 | 2026-07-02 | 4 | Crane | Tower Crane | TOW-09 | 25 | 8.1 | YST 14 | F | Testing | Transformer Unit | 2 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Low | Rescheduled | Client request | Partly Cloudy | 4 | TRUE | 67 |  | 1 | No |  | No Conflict | Yes
BK-0586 | 2026-06-07 | 2026-06-09 |  | 2 | Cometto | Cometto Eco500 12 Axle Lines | COM-12 |  |  | YST 01 | C | Assembly | Hull Block Section | 2 Days | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Low | Rejected | Crane already booked | Overcast | 11 | TRUE | 59 |  | 1 | No |  | No Conflict | Yes
BK-0587 | 2026-06-13 | 2026-06-19 |  | 6 | Forklift | Reach Forklift | FLT-14 | 3 | 2.3 | YST 02 | E | Assembly | Valve Crates | 2 Days | Day Shift (0700-1900) | Team Echo | Advanced Operator | Low | Completed |  | High Wind | 44 | FALSE | 93 | Early | 1 | No |  | No Conflict | Yes
BK-0588 | 2026-06-26 | 2026-07-05 |  | 9 | Crane | Level Luffing Crane | LLC 14 | 50 | 22.7 | YST D4 | F | Commissioning | Anchor Chain | 5 Days | Night Shift (1900-0700) | Team Alpha | Heavy Lift Specialist | High | Pending |  | Clear | 16 | FALSE | 69 |  | 3 | No |  | No Conflict | Yes
BK-0589 | 2026-06-17 | 2026-06-21 |  | 4 | Forklift | Reach Forklift | FLT-18 | 2 | 1.3 | YST 05 | C | Assembly | Steel Plates | 5 Days | Night Shift (1900-0700) | Team Alpha | Advanced Operator | Urgent | Rejected | Operator not available | Overcast | 3 | FALSE | 69 |  | 4 | No |  | No Conflict | Yes
BK-0590 | 2026-06-20 | 2026-06-21 | 2026-06-26 | 1 | Crane | Workshop Crane | WOR-06 | 20 | 8.9 | YST 12 | D | Commissioning | Flare Tower Section | 2 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Medium | Rescheduled | Weather delay | Light Rain | 8 | TRUE | 59 |  | 2 | No |  | No Conflict | Yes
BK-0591 | 2026-06-11 | 2026-06-24 |  | 13 | Crane | Crawler Crane | CRA-16 | 150 | 91.6 | YST 05 | B | Planning | Flare Tower Section | Half Day (PM) | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Urgent | Cancelled | Budget constraint | Overcast | 7 | FALSE | 40 |  | 4 | No |  | No Conflict | Yes
BK-0592 | 2026-06-02 | 2026-06-09 |  | 7 | Crane | Workshop Crane | WOR-12 | 20 | 6.4 | YST 12 | D | Planning | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | Medium | Confirmed |  | Partly Cloudy | 9 | FALSE | 93 |  | 2 | No |  | No Conflict | Yes
BK-0593 | 2026-06-27 | 2026-07-05 |  | 8 | Crane | Mobile Crane | MOB-11 | 75 | 17 | YST 03 | C | Testing | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | Urgent | Completed |  | Clear | 13 | FALSE | 98 | Delayed | 4 | No |  | No Conflict | Yes
BK-0594 | 2026-06-04 | 2026-06-11 | 2026-06-15 | 7 | Forklift | Telehandler Forklift | FLT-10 | 4 | 2.5 | YST 13 | B | Testing | Pipe Bundles | 2 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Urgent | Rescheduled | Client request | Partly Cloudy | 15 | FALSE | 58 |  | 4 | No |  | No Conflict | Yes
BK-0595 | 2026-06-22 | 2026-06-28 |  | 6 | Crane | Crawler Crane | CRA-08 | 100 | 41.7 | YST D2 | A | Commissioning | Accommodation Module | 2 Days | Night Shift (1900-0700) | Team Gamma | Advanced Crane Operator | Medium | Completed |  | Clear | 15 | FALSE | 72 | On Time | 2 | No |  | No Conflict | Yes
BK-0596 | 2026-06-12 | 2026-06-20 |  | 8 | MEWP | Telescopic Boom Lift 30m | MEWP-08 |  |  | YST D2 | D | Commissioning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Beta | Forklift Operator | Urgent | Completed |  | Overcast | 6 | FALSE | 90 | On Time | 4 | No |  | No Conflict | Yes
BK-0597 | 2026-06-11 | 2026-06-13 |  | 2 | Crane | Tower Crane | TOW-07 | 15 | 4.1 | YST D8 | E | Commissioning | Mooring Winch | 7 Days | Night Shift (1900-0700) | Team Alpha | Basic Crane Operator | Medium | Completed |  | High Wind | 28 | FALSE | 67 | On Time | 2 | No |  | No Conflict | Yes
BK-0598 | 2026-06-06 | 2026-06-20 |  | 14 | Crane | Tower Crane | TOW-05 | 40 | 31.9 | YST D2 | C | Testing | Pipe Spool | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | Medium | Completed |  | Overcast | 5 | FALSE | 87 | Early | 2 | No |  | No Conflict | Yes
BK-0599 | 2026-06-15 | 2026-06-27 |  | 12 | MEWP | Telescopic Boom Lift 30m | MEWP-25 |  |  | YST 10 | E | Planning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | High | Pending |  | Clear | 2 | FALSE | 43 |  | 3 | Yes | BK-0642 | First-Come-First-Served | Yes
BK-0600 | 2026-06-22 | 2026-06-29 |  | 7 | Crane | Mobile Crane | MOB-19 | 50 | 18.6 | YST D1 | E | Testing | Turret Assembly | Full Day | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | Medium | Completed |  | Heavy Rain | 23 | FALSE | 88 | On Time | 2 | No |  | No Conflict | Yes
BK-0601 | 2026-06-05 | 2026-06-06 |  | 1 | Forklift | Heavy Duty Forklift | FLT-37 | 25 | 11.8 | YST 17 | C | Outfitting | Gasket Boxes | 7 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Confirmed |  | Partly Cloudy | 7 | FALSE | 78 |  | 2 | Yes | BK-0556 | Later Request - Reassigned | No
BK-0602 | 2026-06-25 | 2026-06-27 |  | 2 | Crane | Crawler Crane | CRA-18 | 100 | 49.3 | YST 02 | E | Testing | Mega Block Section | 5 Days | Night Shift (1900-0700) | Team Alpha | Rigging Supervisor | High | Confirmed |  | Light Rain | 2 | FALSE | 63 |  | 3 | No |  | No Conflict | Yes
BK-0603 | 2026-06-07 | 2026-06-11 |  | 4 | Forklift | Reach Forklift | FLT-30 | 3 | 2.7 | YST 17 | D | Outfitting | Welding Materials | Full Day | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Urgent | Confirmed |  | Clear | 6 | FALSE | 47 |  | 4 | No |  | No Conflict | Yes
BK-0604 | 2026-06-12 | 2026-06-22 |  | 10 | Cometto | Cometto Eco500 12 Axle Lines | COM-06 |  |  | YST 19 | A | Commissioning | Engine Module | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Advanced Operator | High | Pending |  | Overcast | 3 | FALSE | 65 |  | 3 | No |  | No Conflict | Yes
BK-0605 | 2026-06-26 | 2026-07-02 |  | 6 | Crane | Tower Crane | TOW-05 | 10 | 3.7 | YST 09 | B | Outfitting | Mega Block Section | 3 Days | Night Shift (1900-0700) | Team Beta | Basic Crane Operator | High | Completed |  | Light Rain | 17 | FALSE | 96 | On Time | 3 | No |  | No Conflict | Yes
BK-0606 | 2026-06-17 | 2026-06-27 |  | 10 | Cometto | Cometto MSPE 8 Axle Lines | COM-08 |  |  | YST 14 | E | Outfitting | Engine Module | 3 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Low | Cancelled | Material not ready | Overcast | 9 | FALSE | 53 |  | 1 | No |  | No Conflict | Yes
BK-0607 | 2026-06-22 | 2026-07-05 |  | 13 | Forklift | Heavy Duty Forklift | FLT-32 | 20 | 11 | YST D2 | B | Planning | Small Fittings Pallet | 5 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Medium | Completed |  | High Wind | 34 | FALSE | 55 | Delayed | 2 | No |  | No Conflict | Yes
BK-0608 | 2026-06-04 | 2026-06-07 |  | 3 | Forklift | Counterbalance Forklift | FLT-09 | 5 | 4.2 | YST D3 | A | Assembly | Consumables Pallet | 5 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Cancelled | Client cancelled | Clear | 8 | FALSE | 55 |  | 3 | No |  | No Conflict | Yes
BK-0609 | 2026-06-25 | 2026-06-29 |  | 4 | Cometto | SPMT 24 Axle Lines | COM-07 |  |  | YST 14 | F | Planning | Offshore Platform Topside | 2 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | Medium | Completed |  | Partly Cloudy | 15 | FALSE | 96 | On Time | 2 | No |  | No Conflict | Yes
BK-0610 | 2026-06-07 | 2026-06-16 |  | 9 | Crane | Tower Crane | TOW-18 | 25 | 12.8 | YST 12 | C | Testing | Construction Materials | Half Day (AM) | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Low | Cancelled | Project postponed | Clear | 3 | FALSE | 30 |  | 1 | No |  | No Conflict | Yes
BK-0611 | 2026-06-27 | 2026-07-04 |  | 7 | Forklift | Heavy Duty Forklift | FLT-24 | 20 | 15.5 | YST D6 | A | Testing | PPE Supplies | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Confirmed |  | Clear | 14 | FALSE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0612 | 2026-06-10 | 2026-06-11 |  | 1 | MEWP | Boom Lift 20m | MEWP-09 |  |  | YST 02 | F | Assembly | Personnel Access Work | 5 Days | Night Shift (1900-0700) | Team Delta | Basic Operator | High | Confirmed |  | Heavy Rain | 12 | FALSE | 86 |  | 3 | No |  | No Conflict | Yes
BK-0613 | 2026-06-23 | 2026-07-02 |  | 9 | Crane | Level Luffing Crane | LLC 05 | 300 | 114.4 | YST D4 | C | Assembly | Riser Assembly | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Medium | Cancelled | Client cancelled | Partly Cloudy | 2 | FALSE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0614 | 2026-06-21 | 2026-06-28 |  | 7 | Crane | Mobile Crane | MOB-18 | 25 | 16.4 | YST 04 | A | Outfitting | Anchor Chain | Full Day | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Completed |  | Overcast | 13 | FALSE | 68 | On Time | 2 | No |  | No Conflict | Yes
BK-0615 | 2026-06-01 | 2026-06-06 |  | 5 | Crane | Crawler Crane | CRA-10 | 250 | 110.5 | YST D2 | D | Testing | Engine Module | 2 Days | Night Shift (1900-0700) | Team Alpha | Lifting Supervisor | Low | Confirmed |  | Clear | 6 | FALSE | 73 |  | 1 | No |  | No Conflict | Yes
BK-0616 | 2026-06-24 | 2026-07-04 |  | 10 | Forklift | Counterbalance Forklift | FLT-20 | 7 | 5.3 | YST 09 | D | Planning | Scaffolding Materials | 5 Days | Night Shift (1900-0700) | Team Alpha | Forklift Operator | Medium | Pending |  | Clear | 8 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0617 | 2026-06-16 | 2026-06-20 |  | 4 | Cometto | SPMT 16 Axle Lines | COM-09 |  |  | YST 15 | F | Planning | Offshore Platform Topside | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Low | Confirmed |  | Partly Cloudy | 2 | FALSE | 87 |  | 1 | No |  | No Conflict | Yes
BK-0618 | 2026-06-04 | 2026-06-07 |  | 3 | Crane | Level Luffing Crane | LLC 06 | 30 | 23.9 | YST 15 | D | Planning | Mooring Winch | 3 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | High | Pending |  | Clear | 15 | FALSE | 63 |  | 3 | No |  | No Conflict | Yes
BK-0619 | 2026-06-09 | 2026-06-15 |  | 6 | MEWP | Articulating Boom Lift 26m | MEWP-05 |  |  | YST 06 | E | Assembly | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Echo | MEWP Operator | Urgent | Completed |  | Partly Cloudy | 8 | FALSE | 87 | Delayed | 4 | No |  | No Conflict | Yes
BK-0620 | 2026-06-28 | 2026-07-10 |  | 12 | Crane | Workshop Crane | WOR-14 | 20 | 5.1 | YST 01 | F | Planning | Pipe Spool | Full Day | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Medium | Confirmed |  | Partly Cloudy | 12 | FALSE | 78 |  | 2 | No |  | No Conflict | Yes
BK-0621 | 2026-06-06 | 2026-06-08 | 2026-06-10 | 2 | MEWP | Boom Lift 20m | MEWP-21 |  |  | YST 12 | E | Commissioning | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | MEWP Operator | High | Rescheduled | Client request | Partly Cloudy | 14 | FALSE | 62 |  | 3 | No |  | No Conflict | Yes
BK-0622 | 2026-06-03 | 2026-06-10 |  | 7 | Crane | Goliath Gantry Crane | GC-20 | 300 | 97.7 | YST 01 | E | Testing | Accommodation Module | Half Day (PM) | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | High | Completed |  | Overcast | 17 | FALSE | 54 | Early | 3 | No |  | No Conflict | Yes
BK-0623 | 2026-06-03 | 2026-06-15 |  | 12 | MEWP | Boom Lift 20m | MEWP-16 |  |  | YST 06 | D | Commissioning | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Rejected | Crane already booked | Partly Cloudy | 11 | TRUE | 45 |  | 2 | No |  | No Conflict | Yes
BK-0624 | 2026-06-13 | 2026-06-22 | 2026-06-28 | 9 | Cometto | SPMT 16 Axle Lines | COM-06 |  |  | YST 05 | C | Commissioning | Jacket Structure | 3 Days | Night Shift (1900-0700) | Team Beta | Forklift Operator | Urgent | Rescheduled | Safety stand-down | Clear | 15 | FALSE | 36 |  | 4 | No |  | No Conflict | Yes
BK-0625 | 2026-06-04 | 2026-06-11 |  | 7 | Crane | Crawler Crane | CRA-12 | 100 | 76 | YST 01 | E | Fabrication | Flare Tower Section | 7 Days | Night Shift (1900-0700) | Team Gamma | Lifting Supervisor | High | Completed |  | Partly Cloudy | 7 | FALSE | 52 | On Time | 3 | No |  | No Conflict | Yes
BK-0626 | 2026-06-17 | 2026-06-20 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-30 |  |  | YST 04 | C | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | High | Confirmed |  | Partly Cloudy | 3 | FALSE | 85 |  | 3 | No |  | No Conflict | Yes
BK-0627 | 2026-06-09 | 2026-06-13 |  | 4 | Crane | Tower Crane | TOW-15 | 10 | 6.2 | YST D3 | A | Assembly | Construction Materials | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | High | Rejected | Insufficient lead time | Clear | 6 | TRUE | 27 |  | 3 | No |  | No Conflict | Yes
BK-0628 | 2026-06-02 | 2026-06-07 |  | 5 | Cometto | SPMT 16 Axle Lines | COM-05 |  |  | YST 02 | F | Assembly | Jacket Structure | 14 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Completed |  | Heavy Rain | 15 | FALSE | 77 | Delayed | 3 | No |  | No Conflict | Yes
BK-0629 | 2026-06-12 | 2026-06-18 |  | 6 | Forklift | Reach Forklift | FLT-05 | 3 | 2.1 | YST D7 | D | Planning | Pipe Bundles | Full Day | Night Shift (1900-0700) | Team Beta | Advanced Operator | High | Confirmed |  | Clear | 8 | FALSE | 80 |  | 3 | No |  | No Conflict | Yes
BK-0630 | 2026-06-24 | 2026-07-04 | 2026-07-11 | 10 | Forklift | Telehandler Forklift | FLT-08 | 5 | 3.7 | YST 18 | A | Planning | Bolt Pallets | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Low | Rescheduled | Permit delay | Thunderstorm | 25 | FALSE | 21 |  | 1 | No |  | No Conflict | Yes
BK-0631 | 2026-06-06 | 2026-06-15 |  | 9 | Crane | Crawler Crane | CRA-08 | 250 | 76.7 | YST 02 | C | Planning | Riser Assembly | Full Day | Day Shift (0700-1900) | Team Beta | Advanced Crane Operator | High | Cancelled | Duplicate booking | Partly Cloudy | 11 | FALSE | 46 |  | 3 | No |  | No Conflict | Yes
BK-0632 | 2026-06-08 | 2026-06-18 |  | 10 | Crane | Goliath Gantry Crane | GC-18 | 240 | 53.3 | YST 04 | E | Outfitting | Accommodation Module | Full Day | Day Shift (0700-1900) | Team Echo | Lifting Supervisor | Medium | Rejected | Location conflict with another operation | Light Rain | 7 | TRUE | 56 |  | 2 | No |  | No Conflict | Yes
BK-0633 | 2026-06-07 | 2026-06-21 |  | 14 | Crane | Workshop Crane | WOR-17 | 20 | 15.1 | YST 10 | C | Fabrication | Pipe Spool | 3 Days | Night Shift (1900-0700) | Team Gamma | Advanced Crane Operator | Low | Rejected | Insufficient lead time | Partly Cloudy | 3 | FALSE | 49 |  | 1 | No |  | No Conflict | Yes
BK-0634 | 2026-06-19 | 2026-06-23 |  | 4 | MEWP | Scissor Lift 10m | MEWP-23 |  |  | YST 11 | C | Commissioning | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Completed |  | Thunderstorm | 25 | FALSE | 59 | On Time | 2 | No |  | No Conflict | Yes
BK-0635 | 2026-06-18 | 2026-06-21 |  | 3 | Crane | Tower Crane | TOW-14 | 40 | 9 | YST D8 | C | Outfitting | Construction Materials | 5 Days | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | Medium | Completed |  | Overcast | 11 | FALSE | 54 | Delayed | 2 | No |  | No Conflict | Yes
BK-0636 | 2026-06-29 | 2026-07-11 | 2026-07-12 | 12 | Crane | Mobile Crane | MOB-19 | 75 | 48.8 | YST D7 | E | Fabrication | Anchor Chain | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | Basic Crane Operator | Urgent | Rescheduled | Equipment breakdown | High Wind | 43 | FALSE | 23 |  | 4 | No |  | No Conflict | Yes
BK-0637 | 2026-06-10 | 2026-06-19 |  | 9 | Crane | Crawler Crane | CRA-15 | 250 | 73.1 | YST 07 | B | Fabrication | Structural Steel Module | Half Day (AM) | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | Medium | Confirmed |  | Partly Cloudy | 9 | FALSE | 89 |  | 2 | No |  | No Conflict | Yes
BK-0638 | 2026-06-12 | 2026-06-13 |  | 1 | Crane | Level Luffing Crane | LLC 13 | 100 | 65.8 | YST D2 | B | Planning | Workshop Equipment | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Crane Operator | Medium | Completed |  | Partly Cloudy | 12 | FALSE | 89 | On Time | 2 | No |  | No Conflict | Yes
BK-0639 | 2026-06-10 | 2026-06-20 |  | 10 | Cometto | SPMT 24 Axle Lines | COM-09 |  |  | YST 17 | E | Fabrication | Offshore Platform Topside | Half Day (AM) | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Urgent | Confirmed |  | Light Rain | 13 | FALSE | 72 |  | 4 | No |  | No Conflict | Yes
BK-0640 | 2026-06-27 | 2026-06-28 |  | 1 | MEWP | Telescopic Boom Lift 30m | MEWP-21 |  |  | YST 03 | C | Outfitting | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Completed |  | Overcast | 15 | FALSE | 59 | On Time | 2 | No |  | No Conflict | Yes
BK-0641 | 2026-06-27 | 2026-07-03 |  | 6 | Crane | Mobile Crane | MOB-17 | 50 | 14.8 | YST 03 | F | Outfitting | Anchor Chain | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Cancelled | Budget constraint | Light Rain | 2 | FALSE | 44 |  | 2 | No |  | No Conflict | Yes
BK-0642 | 2026-06-22 | 2026-06-28 |  | 6 | MEWP | Telescopic Boom Lift 30m | MEWP-25 |  |  | YST D2 | D | Testing | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | High | Cancelled | Budget constraint | Partly Cloudy | 17 | FALSE | 43 |  | 3 | Yes | BK-0599 | Later Request - Reassigned | No
BK-0643 | 2026-07-26 | 2026-07-29 |  | 3 | Crane | Mobile Crane | MOB-11 | 25 | 9.2 | YST 03 | F | Outfitting | Hull Block Section | 10 Days | Night Shift (1900-0700) | Team Gamma | Basic Crane Operator | Medium | Rejected | Permit not approved | Partly Cloudy | 16 | FALSE | 23 |  | 2 | No |  | No Conflict | Yes
BK-0644 | 2026-07-29 | 2026-08-05 |  | 7 | Crane | Mobile Crane | MOB-01 | 75 | 31.1 | YST D8 | C | Commissioning | Accommodation Module | 3 Days | Day Shift (0700-1900) | Team Gamma | Basic Crane Operator | Medium | Completed |  | Clear | 5 | FALSE | 87 | On Time | 2 | No |  | No Conflict | Yes
BK-0645 | 2026-07-06 | 2026-07-08 |  | 2 | Crane | Workshop Crane | WOR-09 | 10 | 4.3 | YST D6 | C | Assembly | Anchor Chain | 2 Days | Day Shift (0700-1900) | Team Echo | Lifting Supervisor | Medium | Rejected | Crane already booked | Clear | 5 | FALSE | 60 |  | 2 | No |  | No Conflict | Yes
BK-0646 | 2026-07-24 | 2026-07-28 |  | 4 | Crane | Goliath Gantry Crane | GC-10 | 300 | 185 | YST 19 | C | Testing | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | High | Pending |  | Partly Cloudy | 9 | FALSE | 56 |  | 3 | No |  | No Conflict | Yes
BK-0647 | 2026-07-16 | 2026-07-19 |  | 3 | Forklift | Telehandler Forklift | FLT-39 | 4 | 1.8 | YST 09 | A | Outfitting | Pipe Bundles | 2 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Completed |  | Overcast | 10 | FALSE | 80 | On Time | 2 | No |  | No Conflict | Yes
BK-0648 | 2026-07-08 | 2026-07-11 |  | 3 | Cometto | Cometto Eco500 12 Axle Lines | COM-05 |  |  | YST 02 | C | Testing | Jacket Structure | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | High | Cancelled | Duplicate booking | Partly Cloudy | 2 | FALSE | 42 |  | 3 | No |  | No Conflict | Yes
BK-0649 | 2026-07-27 | 2026-08-01 |  | 5 | MEWP | Telescopic Boom Lift 30m | MEWP-18 |  |  | YST 07 | E | Planning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Cancelled | Budget constraint | Overcast | 13 | FALSE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0650 | 2026-07-10 | 2026-07-14 | 2026-07-21 | 4 | Crane | Workshop Crane | WOR-20 | 20 | 15.9 | YST 01 | A | Assembly | Structural Steel Module | 3 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Medium | Rescheduled | Client request | Overcast | 17 | TRUE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0651 | 2026-07-04 | 2026-07-06 |  | 2 | Crane | Level Luffing Crane | LLC 06 | 300 | 117.5 | YST 10 | B | Outfitting | Structural Steel Module | 5 Days | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | High | Completed |  | Thunderstorm | 28 | FALSE | 46 | Delayed | 3 | No |  | No Conflict | Yes
BK-0652 | 2026-07-22 | 2026-08-04 | 2026-08-08 | 13 | Forklift | Telehandler Forklift | FLT-32 | 7 | 5.3 | YST 08 | D | Assembly | Consumables Pallet | 5 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Rescheduled | Weather delay | Clear | 12 | FALSE | 61 |  | 2 | No |  | No Conflict | Yes
BK-0653 | 2026-07-14 | 2026-07-19 |  | 5 | MEWP | Boom Lift 20m | MEWP-20 |  |  | YST 05 | A | Assembly | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Echo | Forklift Operator | High | Completed |  | Overcast | 7 | FALSE | 70 | Delayed | 3 | No |  | No Conflict | Yes
BK-0654 | 2026-07-31 | 2026-08-05 |  | 5 | Cometto | SPMT 24 Axle Lines | COM-04 |  |  | YST 16 | D | Commissioning | Jacket Structure | 7 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | High | Completed |  | Thunderstorm | 30 | FALSE | 44 | Early | 3 | No |  | No Conflict | Yes
BK-0655 | 2026-07-07 | 2026-07-14 |  | 7 | MEWP | Telescopic Boom Lift 30m | MEWP-26 |  |  | YST 08 | C | Fabrication | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Cancelled | Client cancelled | Clear | 4 | FALSE | 63 |  | 2 | No |  | No Conflict | Yes
BK-0656 | 2026-07-22 | 2026-07-27 |  | 5 | MEWP | Telescopic Boom Lift 30m | MEWP-03 |  |  | YST D1 | E | Commissioning | Personnel Access Work | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Operator | Medium | Cancelled | Client cancelled | High Wind | 25 | FALSE | 38 |  | 2 | No |  | No Conflict | Yes
BK-0657 | 2026-07-26 | 2026-07-31 |  | 5 | Forklift | Counterbalance Forklift | FLT-28 | 5 | 3.5 | YST 13 | A | Commissioning | Timber Dunnage | 5 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | High | Pending |  | Clear | 15 | FALSE | 35 |  | 3 | No |  | No Conflict | Yes
BK-0658 | 2026-07-26 | 2026-08-01 |  | 6 | Crane | Crawler Crane | CRA-16 | 50 | 27.8 | YST 08 | D | Commissioning | Riser Assembly | 5 Days | Night Shift (1900-0700) | Team Gamma | Rigging Supervisor | Medium | Completed |  | Clear | 10 | FALSE | 49 | Delayed | 2 | No |  | No Conflict | Yes
BK-0659 | 2026-07-01 | 2026-07-04 |  | 3 | Crane | Crawler Crane | CRA-06 | 150 | 107.3 | YST 05 | F | Commissioning | Turret Assembly | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Medium | Completed |  | Clear | 11 | FALSE | 54 | On Time | 2 | No |  | No Conflict | Yes
BK-0660 | 2026-07-07 | 2026-07-14 | 2026-07-18 | 7 | Crane | Level Luffing Crane | LLC 17 | 50 | 19.4 | YST 12 | C | Commissioning | Turret Assembly | 5 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Medium | Rescheduled | Safety stand-down | Clear | 18 | FALSE | 53 |  | 2 | No |  | No Conflict | Yes
BK-0661 | 2026-07-06 | 2026-07-12 |  | 6 | Crane | Workshop Crane | WOR-10 | 10 | 5.4 | YST 14 | F | Fabrication | Mega Block Section | Full Day | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | High | Rejected | Crane under scheduled maintenance | Partly Cloudy | 16 | FALSE | 70 |  | 3 | No |  | No Conflict | Yes
BK-0662 | 2026-07-26 | 2026-08-01 |  | 6 | Crane | Goliath Gantry Crane | GC-17 | 300 | 234.7 | YST 19 | E | Commissioning | Hull Block Section | 3 Days | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Low | Pending |  | Partly Cloudy | 4 | FALSE | 56 |  | 1 | No |  | No Conflict | Yes
BK-0663 | 2026-07-17 | 2026-07-20 |  | 3 | Crane | Workshop Crane | WOR-15 | 10 | 7.4 | YST 11 | B | Commissioning | Mega Block Section | Full Day | Night Shift (1900-0700) | Team Gamma | Basic Crane Operator | High | Confirmed |  | Light Rain | 4 | FALSE | 59 |  | 3 | No |  | No Conflict | Yes
BK-0664 | 2026-07-02 | 2026-07-05 |  | 3 | Crane | Tower Crane | TOW-18 | 40 | 21 | YST D3 | D | Planning | Engine Module | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Low | Completed |  | Partly Cloudy | 5 | FALSE | 71 | On Time | 1 | No |  | No Conflict | Yes
BK-0665 | 2026-07-01 | 2026-07-08 |  | 7 | Forklift | Counterbalance Forklift | FLT-38 | 7 | 3.5 | YST D5 | D | Testing | Tool Containers | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Urgent | Completed |  | Clear | 7 | FALSE | 58 | Early | 4 | No |  | No Conflict | Yes
BK-0666 | 2026-07-10 | 2026-07-14 |  | 4 | MEWP | Articulating Boom Lift 26m | MEWP-22 |  |  | YST 09 | B | Outfitting | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Rejected | Insufficient lead time | Clear | 18 | TRUE | 68 |  | 2 | No |  | No Conflict | Yes
BK-0667 | 2026-07-14 | 2026-07-22 |  | 8 | Crane | Mobile Crane | MOB-18 | 75 | 36.2 | YST D8 | E | Assembly | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | High | Completed |  | Partly Cloudy | 18 | FALSE | 79 | On Time | 3 | No |  | No Conflict | Yes
BK-0668 | 2026-07-22 | 2026-07-25 |  | 3 | Crane | Mobile Crane | MOB-06 | 50 | 24.2 | YST 03 | F | Assembly | Construction Materials | 2 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | High | Rejected | Operator not available | Clear | 10 | FALSE | 39 |  | 3 | No |  | No Conflict | Yes
BK-0669 | 2026-07-11 | 2026-07-19 |  | 8 | Forklift | Telehandler Forklift | FLT-37 | 7 | 2.2 | YST 10 | F | Fabrication | Scaffolding Materials | 2 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Low | Completed |  | High Wind | 33 | FALSE | 53 | Delayed | 1 | No |  | No Conflict | Yes
BK-0670 | 2026-07-09 | 2026-07-13 |  | 4 | Crane | Crawler Crane | CRA-18 | 250 | 98.8 | YST 07 | C | Planning | Pipe Spool | 3 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | High | Completed |  | Clear | 7 | FALSE | 86 | Delayed | 3 | No |  | No Conflict | Yes
BK-0671 | 2026-07-31 | 2026-08-13 |  | 13 | Crane | Workshop Crane | WOR-09 | 20 | 5.3 | YST D6 | C | Testing | Mega Block Section | 14 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Cancelled | Client cancelled | Partly Cloudy | 11 | FALSE | 40 |  | 2 | No |  | No Conflict | Yes
BK-0672 | 2026-07-25 | 2026-08-03 |  | 9 | Forklift | Heavy Duty Forklift | FLT-36 | 20 | 7.7 | YST 19 | E | Testing | Tool Containers | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Cancelled | Duplicate booking | Light Rain | 2 | FALSE | 43 |  | 2 | Yes | BK-0688 | Yielded to Higher Priority | No
BK-0673 | 2026-07-29 | 2026-08-07 |  | 9 | Cometto | Cometto Eco500 12 Axle Lines | COM-08 |  |  | YST 03 | C | Testing | Mega Block Section | Full Day | Day Shift (0700-1900) | Team Beta | Basic Operator | High | Cancelled | Material not ready | Overcast | 2 | FALSE | 47 |  | 3 | No |  | No Conflict | Yes
BK-0674 | 2026-07-13 | 2026-07-23 |  | 10 | Forklift | Counterbalance Forklift | FLT-03 | 5 | 3.2 | YST 01 | E | Assembly | Scaffolding Materials | 10 Days | Night Shift (1900-0700) | Team Gamma | MEWP Operator | High | Completed |  | Overcast | 4 | FALSE | 89 | On Time | 3 | No |  | No Conflict | Yes
BK-0675 | 2026-07-06 | 2026-07-15 | 2026-07-21 | 9 | Forklift | Counterbalance Forklift | FLT-05 | 7 | 2.9 | YST 20 | F | Fabrication | Tool Containers | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Rescheduled | Safety stand-down | Overcast | 4 | FALSE | 64 |  | 2 | No |  | No Conflict | Yes
BK-0676 | 2026-07-27 | 2026-08-08 |  | 12 | Forklift | Reach Forklift | FLT-02 | 2.5 | 1.9 | YST 01 | F | Assembly | Consumables Pallet | Half Day (AM) | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Completed |  | Partly Cloudy | 8 | FALSE | 62 | Early | 2 | No |  | No Conflict | Yes
BK-0677 | 2026-07-23 | 2026-08-03 |  | 11 | Crane | Goliath Gantry Crane | GC-10 | 240 | 142.8 | YST 04 | A | Assembly | Structural Steel Module | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | High | Pending |  | Heavy Rain | 17 | FALSE | 30 |  | 3 | No |  | No Conflict | Yes
BK-0678 | 2026-07-14 | 2026-07-28 |  | 14 | Crane | Goliath Gantry Crane | GC-18 | 300 | 138.9 | YST 01 | F | Fabrication | Structural Steel Module | Half Day (PM) | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | Medium | Cancelled | Material not ready | Partly Cloudy | 16 | FALSE | 57 |  | 2 | No |  | No Conflict | Yes
BK-0679 | 2026-07-27 | 2026-07-29 |  | 2 | Forklift | Counterbalance Forklift | FLT-08 | 3 | 1.5 | YST D5 | B | Fabrication | Tool Containers | 10 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | High | Completed |  | High Wind | 41 | FALSE | 47 | Early | 3 | No |  | No Conflict | Yes
BK-0680 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 1 | Forklift | Reach Forklift | FLT-20 | 1.5 | 1.2 | YST 12 | A | Commissioning | Bolt Pallets | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Rescheduled | Higher priority job took precedence | Overcast | 14 | FALSE | 40 |  | 2 | No |  | No Conflict | Yes
BK-0681 | 2026-07-05 | 2026-07-15 |  | 10 | Crane | Level Luffing Crane | LLC 05 | 40 | 27.8 | YST D1 | F | Commissioning | Structural Steel Module | 5 Days | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | High | Completed |  | Clear | 15 | FALSE | 51 | Early | 3 | No |  | No Conflict | Yes
BK-0682 | 2026-07-31 | 2026-08-03 |  | 3 | Forklift | Heavy Duty Forklift | FLT-02 | 20 | 10 | YST 04 | E | Assembly | PPE Supplies | 3 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Rejected | Crane under scheduled maintenance | Clear | 2 | FALSE | 29 |  | 2 | No |  | No Conflict | Yes
BK-0683 | 2026-07-30 | 2026-08-04 |  | 5 | MEWP | Boom Lift 20m | MEWP-04 |  |  | YST 06 | D | Outfitting | Personnel Access Work | Half Day (AM) | Night Shift (1900-0700) | Team Alpha | Advanced Operator | Medium | Confirmed |  | High Wind | 42 | FALSE | 94 |  | 2 | No |  | No Conflict | Yes
BK-0684 | 2026-07-20 | 2026-07-30 |  | 10 | Crane | Mobile Crane | MOB-11 | 100 | 27.5 | YST 05 | D | Commissioning | Structural Steel Module | 3 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | High | Confirmed |  | Light Rain | 8 | FALSE | 91 |  | 3 | No |  | No Conflict | Yes
BK-0685 | 2026-07-31 | 2026-08-03 |  | 3 | Cometto | Cometto MSPE 8 Axle Lines | COM-05 |  |  | YST 19 | C | Assembly | Offshore Platform Topside | 7 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Cancelled | Budget constraint | Overcast | 16 | FALSE | 53 |  | 2 | No |  | No Conflict | Yes
BK-0686 | 2026-07-19 | 2026-08-02 |  | 14 | Crane | Goliath Gantry Crane | GC-13 | 300 | 62.6 | YST 04 | F | Planning | Pipe Spool | 3 Days | Night Shift (1900-0700) | Team Alpha | Rigging Supervisor | High | Rejected | Weather conditions unsafe | Light Rain | 7 | TRUE | 40 |  | 3 | No |  | No Conflict | Yes
BK-0687 | 2026-07-01 | 2026-07-08 |  | 7 | MEWP | Articulating Boom Lift 26m | MEWP-21 |  |  | YST 07 | E | Assembly | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | Medium | Completed |  | Partly Cloudy | 5 | FALSE | 81 | Delayed | 2 | No |  | No Conflict | Yes
BK-0688 | 2026-07-30 | 2026-08-03 |  | 4 | Forklift | Heavy Duty Forklift | FLT-36 | 20 | 7.1 | YST 11 | C | Outfitting | Small Fittings Pallet | 2 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | High | Completed |  | Overcast | 6 | FALSE | 93 | On Time | 3 | Yes | BK-0672 | Priority Override | Yes
BK-0689 | 2026-07-18 | 2026-07-26 |  | 8 | Crane | Crawler Crane | CRA-18 | 150 | 99.8 | YST 08 | E | Fabrication | Anchor Chain | 14 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | Medium | Rejected | Load exceeds crane capacity | Clear | 9 | FALSE | 69 |  | 2 | No |  | No Conflict | Yes
BK-0690 | 2026-07-05 | 2026-07-12 |  | 7 | MEWP | Scissor Lift 10m | MEWP-18 |  |  | YST 12 | F | Fabrication | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Echo | MEWP Operator | Medium | Confirmed |  | Overcast | 9 | FALSE | 88 |  | 2 | No |  | No Conflict | Yes
BK-0691 | 2026-07-23 | 2026-07-26 |  | 3 | Forklift | Reach Forklift | FLT-26 | 2 | 0.7 | YST 09 | B | Commissioning | Pipe Bundles | Full Day | Night Shift (1900-0700) | Team Delta | Forklift Operator | Urgent | Completed |  | High Wind | 25 | FALSE | 82 | On Time | 4 | No |  | No Conflict | Yes
BK-0692 | 2026-07-30 | 2026-08-08 |  | 9 | MEWP | Scissor Lift 10m | MEWP-25 |  |  | YST 02 | B | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | High | Rejected | Weather conditions unsafe | Light Rain | 15 | TRUE | 42 |  | 3 | No |  | No Conflict | Yes
BK-0693 | 2026-07-03 | 2026-07-06 |  | 3 | Forklift | Heavy Duty Forklift | FLT-14 | 25 | 11 | YST 04 | C | Testing | Welding Materials | 2 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Low | Confirmed |  | Clear | 17 | FALSE | 92 |  | 1 | No |  | No Conflict | Yes
BK-0694 | 2026-07-04 | 2026-07-11 | 2026-07-17 | 7 | MEWP | Boom Lift 20m | MEWP-29 |  |  | YST 03 | A | Outfitting | Personnel Access Work | 10 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | Urgent | Rescheduled | Safety stand-down | Light Rain | 10 | FALSE | 30 |  | 4 | No |  | No Conflict | Yes
BK-0695 | 2026-07-23 | 2026-08-03 | 2026-08-10 | 11 | MEWP | Articulating Boom Lift 26m | MEWP-17 |  |  | YST 08 | B | Commissioning | Personnel Access Work | Half Day (PM) | Night Shift (1900-0700) | Team Echo | Advanced Operator | Urgent | Rescheduled | Weather delay | Partly Cloudy | 15 | FALSE | 37 |  | 4 | No |  | No Conflict | Yes
BK-0696 | 2026-07-24 | 2026-08-02 |  | 9 | Forklift | Telehandler Forklift | FLT-23 | 7 | 6.3 | YST D2 | E | Outfitting | Gasket Boxes | Half Day (PM) | Day Shift (0700-1900) | Team Delta | MEWP Operator | Medium | Completed |  | Overcast | 5 | FALSE | 71 | Delayed | 2 | No |  | No Conflict | Yes
BK-0697 | 2026-07-27 | 2026-08-03 |  | 7 | MEWP | Telescopic Boom Lift 30m | MEWP-20 |  |  | YST 02 | A | Fabrication | Personnel Access Work | Half Day (PM) | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Urgent | Pending |  | Partly Cloudy | 15 | FALSE | 65 |  | 4 | No |  | No Conflict | Yes
BK-0698 | 2026-07-24 | 2026-07-25 |  | 1 | MEWP | Telescopic Boom Lift 30m | MEWP-19 |  |  | YST D3 | D | Commissioning | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Cancelled | Client cancelled | Thunderstorm | 26 | FALSE | 60 |  | 3 | No |  | No Conflict | Yes
BK-0699 | 2026-07-31 | 2026-08-04 |  | 4 | Crane | Mobile Crane | MOB-09 | 25 | 16.5 | YST 08 | D | Planning | Flare Tower Section | 2 Days | Day Shift (0700-1900) | Team Gamma | Basic Crane Operator | Urgent | Completed |  | Partly Cloudy | 10 | FALSE | 75 | Delayed | 4 | No |  | No Conflict | Yes
BK-0700 | 2026-07-18 | 2026-07-25 |  | 7 | Cometto | SPMT 16 Axle Lines | COM-08 |  |  | YST 20 | B | Assembly | Hull Block Section | 7 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Rejected | Crane already booked | Light Rain | 5 | FALSE | 40 |  | 2 | No |  | No Conflict | Yes
BK-0701 | 2026-07-20 | 2026-07-26 | 2026-07-31 | 6 | Crane | Mobile Crane | MOB-16 | 50 | 37.3 | YST 05 | C | Planning | Flare Tower Section | 2 Days | Night Shift (1900-0700) | Team Gamma | Heavy Lift Specialist | High | Rescheduled | Client request | Clear | 11 | TRUE | 55 |  | 3 | No |  | No Conflict | Yes
BK-0702 | 2026-07-06 | 2026-07-11 |  | 5 | Cometto | Cometto Eco500 12 Axle Lines | COM-12 |  |  | YST 02 | C | Testing | Engine Module | 3 Days | Night Shift (1900-0700) | Team Delta | MEWP Operator | Urgent | Confirmed |  | Partly Cloudy | 6 | FALSE | 46 |  | 4 | No |  | No Conflict | Yes
BK-0703 | 2026-07-28 | 2026-08-10 |  | 13 | Forklift | Telehandler Forklift | FLT-29 | 3 | 1.3 | YST 11 | D | Fabrication | Valve Crates | 5 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | High | Completed |  | Light Rain | 9 | FALSE | 81 | Delayed | 3 | No |  | No Conflict | Yes
BK-0704 | 2026-07-05 | 2026-07-06 |  | 1 | Crane | Level Luffing Crane | LLC 15 | 300 | 194.4 | YST 17 | E | Testing | Flare Tower Section | 2 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Medium | Confirmed |  | Partly Cloudy | 14 | FALSE | 63 |  | 2 | No |  | No Conflict | Yes
BK-0705 | 2026-07-26 | 2026-08-05 | 2026-08-08 | 10 | Crane | Crawler Crane | CRA-12 | 100 | 78.9 | YST 06 | B | Testing | Transformer Unit | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | Urgent | Rescheduled | Client request | Overcast | 5 | FALSE | 54 |  | 4 | No |  | No Conflict | Yes
BK-0706 | 2026-07-04 | 2026-07-14 |  | 10 | MEWP | Articulating Boom Lift 26m | MEWP-15 |  |  | YST 08 | D | Planning | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Delta | Basic Operator | High | Completed |  | High Wind | 30 | FALSE | 68 | Delayed | 3 | No |  | No Conflict | Yes
BK-0707 | 2026-07-02 | 2026-07-13 | 2026-07-19 | 11 | MEWP | Boom Lift 20m | MEWP-22 |  |  | YST 03 | F | Planning | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Gamma | Advanced Operator | High | Rescheduled | Project timeline shifted | Overcast | 17 | FALSE | 33 |  | 3 | No |  | No Conflict | Yes
BK-0708 | 2026-07-15 | 2026-07-19 |  | 4 | Cometto | SPMT 16 Axle Lines | COM-10 |  |  | YST 13 | F | Testing | Hull Block Section | 5 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Medium | Pending |  | Partly Cloudy | 2 | FALSE | 23 |  | 2 | No |  | No Conflict | Yes
BK-0709 | 2026-07-23 | 2026-08-01 |  | 9 | MEWP | Scissor Lift 10m | MEWP-17 |  |  | YST 03 | B | Fabrication | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Cancelled | Duplicate booking | Clear | 17 | FALSE | 25 |  | 2 | No |  | No Conflict | Yes
BK-0710 | 2026-07-04 | 2026-07-16 |  | 12 | MEWP | Telescopic Boom Lift 30m | MEWP-13 |  |  | YST D2 | B | Commissioning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Medium | Completed |  | Partly Cloudy | 10 | FALSE | 51 | On Time | 2 | No |  | No Conflict | Yes
BK-0711 | 2026-07-07 | 2026-07-10 |  | 3 | Forklift | Counterbalance Forklift | FLT-34 | 5 | 1.5 | YST 15 | C | Planning | Insulation Materials | Full Day | Night Shift (1900-0700) | Team Alpha | Advanced Operator | Urgent | Confirmed |  | Clear | 18 | FALSE | 59 |  | 4 | No |  | No Conflict | Yes
BK-0712 | 2026-07-01 | 2026-07-11 | 2026-07-13 | 10 | MEWP | Articulating Boom Lift 26m | MEWP-06 |  |  | YST 03 | A | Commissioning | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Rescheduled | Safety stand-down | Thunderstorm | 31 | FALSE | 69 |  | 2 | No |  | No Conflict | Yes
BK-0713 | 2026-07-17 | 2026-07-20 |  | 3 | Forklift | Counterbalance Forklift | FLT-20 | 2.5 | 2.2 | YST 18 | A | Outfitting | Insulation Materials | 7 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Pending |  | Clear | 6 | FALSE | 49 |  | 2 | No |  | No Conflict | Yes
BK-0714 | 2026-07-30 | 2026-08-07 |  | 8 | Forklift | Reach Forklift | FLT-22 | 1.5 | 1.2 | YST D2 | C | Planning | Safety Equipment | Full Day | Day Shift (0700-1900) | Team Delta | MEWP Operator | Medium | Completed |  | Thunderstorm | 35 | FALSE | 85 | Delayed | 2 | No |  | No Conflict | Yes
BK-0715 | 2026-07-19 | 2026-07-21 |  | 2 | MEWP | Articulating Boom Lift 26m | MEWP-25 |  |  | YST D1 | C | Commissioning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Medium | Rejected | Permit not approved | Partly Cloudy | 15 | TRUE | 26 |  | 2 | No |  | No Conflict | Yes
BK-0716 | 2026-07-11 | 2026-07-18 |  | 7 | MEWP | Articulating Boom Lift 26m | MEWP-26 |  |  | YST D4 | B | Planning | Personnel Access Work | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Low | Rejected | Crane under scheduled maintenance | Partly Cloudy | 7 | FALSE | 23 |  | 1 | No |  | No Conflict | Yes
BK-0717 | 2026-07-31 | 2026-08-04 |  | 4 | Crane | Tower Crane | TOW-17 | 10 | 7.4 | YST D2 | B | Planning | Turret Assembly | 3 Days | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | High | Confirmed |  | Partly Cloudy | 7 | FALSE | 44 |  | 3 | No |  | No Conflict | Yes
BK-0718 | 2026-07-23 | 2026-07-26 |  | 3 | Crane | Workshop Crane | WOR-13 | 10 | 4.2 | YST 02 | C | Fabrication | Riser Assembly | Full Day | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | Low | Completed |  | High Wind | 32 | FALSE | 42 | On Time | 1 | No |  | No Conflict | Yes
BK-0719 | 2026-07-20 | 2026-07-23 |  | 3 | Cometto | SPMT 24 Axle Lines | COM-12 |  |  | YST 18 | C | Outfitting | Jacket Structure | 7 Days | Day Shift (0700-1900) | Team Beta | MEWP Operator | Urgent | Cancelled | Material not ready | Overcast | 15 | FALSE | 37 |  | 4 | No |  | No Conflict | Yes
BK-0720 | 2026-07-27 | 2026-08-07 |  | 11 | Forklift | Reach Forklift | FLT-26 | 2.5 | 0.8 | YST 20 | F | Planning | Steel Plates | Half Day (AM) | Night Shift (1900-0700) | Team Beta | Forklift Operator | High | Completed |  | Clear | 17 | FALSE | 50 | Early | 3 | No |  | No Conflict | Yes
BK-0721 | 2026-07-09 | 2026-07-22 |  | 13 | Cometto | SPMT 24 Axle Lines | COM-05 |  |  | YST 05 | B | Planning | Jacket Structure | Full Day | Day Shift (0700-1900) | Team Alpha | Basic Operator | High | Completed |  | Overcast | 17 | FALSE | 73 | Early | 3 | No |  | No Conflict | Yes
BK-0722 | 2026-07-16 | 2026-07-22 |  | 6 | Crane | Level Luffing Crane | LLC 16A | 100 | 59.8 | YST 06 | B | Outfitting | Engine Module | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Completed |  | Overcast | 3 | FALSE | 52 | Delayed | 3 | No |  | No Conflict | Yes
BK-0723 | 2026-07-24 | 2026-07-28 | 2026-07-31 | 4 | MEWP | Boom Lift 20m | MEWP-28 |  |  | YST 11 | A | Outfitting | Personnel Access Work | 10 Days | Night Shift (1900-0700) | Team Gamma | Forklift Operator | Medium | Rescheduled | Operator reassigned | Partly Cloudy | 11 | TRUE | 32 |  | 2 | No |  | No Conflict | Yes
BK-0724 | 2026-07-22 | 2026-07-30 |  | 8 | Crane | Mobile Crane | MOB-17 | 25 | 14.3 | YST 04 | F | Planning | Construction Materials | Full Day | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | Urgent | Confirmed |  | Partly Cloudy | 2 | FALSE | 60 |  | 4 | No |  | No Conflict | Yes
BK-0725 | 2026-07-12 | 2026-07-13 |  | 1 | Forklift | Heavy Duty Forklift | FLT-37 | 10 | 3.1 | YST 13 | F | Planning | Steel Plates | Half Day (AM) | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Completed |  | Overcast | 4 | FALSE | 70 | Early | 2 | No |  | No Conflict | Yes
BK-0726 | 2026-08-13 | 2026-08-17 | 2026-08-21 | 4 | MEWP | Telescopic Boom Lift 30m | MEWP-22 |  |  | YST 08 | B | Outfitting | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Rescheduled | Higher priority job took precedence | Partly Cloudy | 13 | FALSE | 31 |  | 2 | No |  | No Conflict | Yes
BK-0727 | 2026-08-09 | 2026-08-20 | 2026-08-24 | 11 | Crane | Level Luffing Crane | LLC 02 | 100 | 45.3 | YST 10 | B | Commissioning | Structural Steel Module | 2 Days | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Urgent | Rescheduled | Safety stand-down | Partly Cloudy | 14 | FALSE | 44 |  | 4 | No |  | No Conflict | Yes
BK-0728 | 2026-08-12 | 2026-08-16 | 2026-08-18 | 4 | Cometto | Cometto Eco500 12 Axle Lines | COM-04 |  |  | YST 19 | F | Testing | Jacket Structure | Full Day | Night Shift (1900-0700) | Team Echo | Forklift Operator | Medium | Rescheduled | Material delivery delayed | Partly Cloudy | 16 | FALSE | 39 |  | 2 | No |  | No Conflict | Yes
BK-0729 | 2026-08-13 | 2026-08-16 |  | 3 | Crane | Workshop Crane | WOR-20 | 20 | 4.3 | YST 13 | D | Testing | Riser Assembly | 2 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Confirmed |  | Partly Cloudy | 16 | FALSE | 76 |  | 3 | No |  | No Conflict | Yes
BK-0730 | 2026-08-22 | 2026-08-25 | 2026-08-26 | 3 | Forklift | Heavy Duty Forklift | FLT-10 | 25 | 15.5 | YST 19 | C | Testing | Tool Containers | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Rescheduled | Original date conflicts with maintenance | High Wind | 44 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0731 | 2026-08-03 | 2026-08-04 |  | 1 | Forklift | Counterbalance Forklift | FLT-21 | 5 | 3.3 | YST D8 | A | Assembly | Safety Equipment | 7 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Completed |  | Overcast | 12 | FALSE | 70 | On Time | 2 | No |  | No Conflict | Yes
BK-0732 | 2026-08-06 | 2026-08-10 |  | 4 | Crane | Tower Crane | TOW-14 | 15 | 11.8 | YST 12 | D | Commissioning | Structural Steel Module | Half Day (PM) | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | Medium | Pending |  | High Wind | 32 | FALSE | 29 |  | 2 | No |  | No Conflict | Yes
BK-0733 | 2026-08-30 | 2026-09-04 |  | 5 | Forklift | Heavy Duty Forklift | FLT-31 | 25 | 20.9 | YST 16 | D | Testing | Consumables Pallet | Full Day | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Urgent | Completed |  | Overcast | 16 | FALSE | 82 | Delayed | 4 | No |  | No Conflict | Yes
BK-0734 | 2026-08-29 | 2026-09-02 | 2026-09-03 | 4 | Crane | Crawler Crane | CRA-20 | 50 | 18.8 | YST 03 | F | Fabrication | Structural Steel Module | Full Day | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Rescheduled | Weather delay | High Wind | 35 | FALSE | 51 |  | 2 | No |  | No Conflict | Yes
BK-0735 | 2026-08-20 | 2026-08-31 | 2026-09-07 | 11 | Crane | Goliath Gantry Crane | GC-19 | 300 | 107.4 | YST 04 | A | Commissioning | Mega Block Section | Full Day | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Medium | Rescheduled | Equipment breakdown | Clear | 11 | TRUE | 67 |  | 2 | No |  | No Conflict | Yes
BK-0736 | 2026-08-22 | 2026-08-28 | 2026-09-01 | 6 | Crane | Tower Crane | TOW-20 | 10 | 6.2 | YST 12 | D | Outfitting | Flare Tower Section | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Medium | Rescheduled | Client request | Clear | 10 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0737 | 2026-08-14 | 2026-08-22 |  | 8 | Crane | Crawler Crane | CRA-16 | 150 | 32.1 | YST D1 | F | Assembly | Mega Block Section | Full Day | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Urgent | Confirmed |  | Heavy Rain | 13 | FALSE | 88 |  | 4 | No |  | No Conflict | Yes
BK-0738 | 2026-08-04 | 2026-08-07 |  | 3 | Crane | Level Luffing Crane | LLC 08 | 40 | 23.1 | YST D3 | C | Testing | Helideck Module | 5 Days | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | High | Cancelled | Client cancelled | Clear | 16 | FALSE | 59 |  | 3 | No |  | No Conflict | Yes
BK-0739 | 2026-08-04 | 2026-08-06 |  | 2 | Crane | Workshop Crane | WOR-03 | 10 | 4.9 | YST 09 | D | Assembly | Engine Module | Half Day (AM) | Night Shift (1900-0700) | Team Beta | Basic Crane Operator | Medium | Cancelled | Material not ready | Overcast | 8 | FALSE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0740 | 2026-08-23 | 2026-08-26 | 2026-09-02 | 3 | Crane | Workshop Crane | WOR-17 | 10 | 3.1 | YST D5 | E | Fabrication | Structural Steel Module | Half Day (AM) | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Rescheduled | Operator reassigned | Overcast | 4 | TRUE | 60 |  | 2 | No |  | No Conflict | Yes
BK-0741 | 2026-08-19 | 2026-08-23 | 2026-08-28 | 4 | Crane | Workshop Crane | WOR-09 | 20 | 4.8 | YST 10 | F | Assembly | Anchor Chain | 5 Days | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | Low | Rescheduled | Equipment breakdown | Clear | 7 | FALSE | 23 |  | 1 | No |  | No Conflict | Yes
BK-0742 | 2026-08-25 | 2026-09-04 |  | 10 | Crane | Workshop Crane | WOR-03 | 20 | 9.4 | YST 01 | A | Testing | Turret Assembly | 2 Days | Night Shift (1900-0700) | Team Gamma | Heavy Lift Specialist | High | Cancelled | Material not ready | Clear | 12 | FALSE | 43 |  | 3 | No |  | No Conflict | Yes
BK-0743 | 2026-08-16 | 2026-08-20 |  | 4 | MEWP | Boom Lift 20m | MEWP-19 |  |  | YST 08 | D | Outfitting | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Completed |  | Heavy Rain | 24 | FALSE | 49 | Delayed | 2 | No |  | No Conflict | Yes
BK-0744 | 2026-08-13 | 2026-08-18 |  | 5 | Crane | Goliath Gantry Crane | GC-13 | 300 | 145 | YST 04 | B | Fabrication | Flare Tower Section | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Urgent | Confirmed |  | Clear | 14 | FALSE | 52 |  | 4 | No |  | No Conflict | Yes
BK-0745 | 2026-08-01 | 2026-08-07 |  | 6 | Crane | Tower Crane | TOW-16 | 25 | 6 | YST 14 | F | Planning | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Urgent | Confirmed |  | Partly Cloudy | 5 | FALSE | 70 |  | 4 | No |  | No Conflict | Yes
BK-0746 | 2026-08-20 | 2026-08-24 |  | 4 | Crane | Mobile Crane | MOB-01 | 50 | 25.9 | YST 07 | D | Testing | Mooring Winch | 10 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Cancelled | Duplicate booking | Clear | 6 | FALSE | 64 |  | 3 | No |  | No Conflict | Yes
BK-0747 | 2026-08-28 | 2026-08-30 |  | 2 | MEWP | Telescopic Boom Lift 30m | MEWP-01 |  |  | YST 03 | C | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Urgent | Cancelled | Budget constraint | Thunderstorm | 35 | FALSE | 41 |  | 4 | No |  | No Conflict | Yes
BK-0748 | 2026-08-19 | 2026-08-28 |  | 9 | Cometto | Cometto Eco500 12 Axle Lines | COM-04 |  |  | YST 13 | A | Assembly | Jacket Structure | 5 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | Medium | Completed |  | Partly Cloudy | 5 | FALSE | 49 | Delayed | 2 | Yes | BK-0751 | Yielded to Higher Priority | No
BK-0749 | 2026-08-03 | 2026-08-09 |  | 6 | MEWP | Articulating Boom Lift 26m | MEWP-15 |  |  | YST 03 | A | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | High | Completed |  | Clear | 2 | FALSE | 92 | Delayed | 3 | No |  | No Conflict | Yes
BK-0750 | 2026-08-18 | 2026-08-21 |  | 3 | Crane | Crawler Crane | CRA-18 | 250 | 128.5 | YST 06 | A | Assembly | Construction Materials | Full Day | Night Shift (1900-0700) | Team Beta | Heavy Lift Specialist | Urgent | Pending |  | Overcast | 8 | FALSE | 35 |  | 4 | No |  | No Conflict | Yes
BK-0751 | 2026-08-26 | 2026-08-31 |  | 5 | Cometto | Cometto MSPE 8 Axle Lines | COM-04 |  |  | YST 05 | C | Outfitting | Mega Block Section | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | High | Completed |  | Light Rain | 6 | FALSE | 64 | Delayed | 3 | Yes | BK-0748 | Priority Override | Yes
BK-0752 | 2026-08-20 | 2026-08-25 |  | 5 | Crane | Crawler Crane | CRA-20 | 250 | 71.3 | YST 05 | A | Assembly | Mega Block Section | 2 Days | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | Medium | Confirmed |  | Overcast | 13 | FALSE | 64 |  | 2 | No |  | No Conflict | Yes
BK-0753 | 2026-08-18 | 2026-08-19 |  | 1 | Crane | Crawler Crane | CRA-20 | 250 | 124.5 | YST 03 | A | Testing | Pipe Spool | 5 Days | Day Shift (0700-1900) | Team Gamma | Lifting Supervisor | Medium | Rejected | Insufficient lead time | Clear | 6 | TRUE | 53 |  | 2 | No |  | No Conflict | Yes
BK-0754 | 2026-08-06 | 2026-08-18 |  | 12 | Crane | Crawler Crane | CRA-14 | 150 | 103.3 | YST 06 | F | Outfitting | Engine Module | 2 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Pending |  | Overcast | 4 | FALSE | 27 |  | 2 | No |  | No Conflict | Yes
BK-0755 | 2026-08-25 | 2026-09-06 |  | 12 | Crane | Goliath Gantry Crane | GC-19 | 200 | 100.1 | YST 19 | B | Fabrication | Workshop Equipment | Half Day (AM) | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Confirmed |  | High Wind | 29 | FALSE | 88 |  | 2 | No |  | No Conflict | Yes
BK-0756 | 2026-08-21 | 2026-08-29 |  | 8 | Crane | Crawler Crane | CRA-14 | 250 | 137.2 | YST 01 | D | Planning | Workshop Equipment | 3 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Low | Completed |  | Partly Cloudy | 4 | FALSE | 97 | Delayed | 1 | No |  | No Conflict | Yes
BK-0757 | 2026-08-13 | 2026-08-16 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-18 |  |  | YST 09 | B | Assembly | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | High | Completed |  | Heavy Rain | 22 | FALSE | 58 | On Time | 3 | No |  | No Conflict | Yes
BK-0758 | 2026-08-15 | 2026-08-22 |  | 7 | Cometto | SPMT 24 Axle Lines | COM-02 |  |  | YST 04 | E | Commissioning | Hull Block Section | Half Day (AM) | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Urgent | Completed |  | Overcast | 8 | FALSE | 92 | On Time | 4 | No |  | No Conflict | Yes
BK-0759 | 2026-08-15 | 2026-08-17 |  | 2 | MEWP | Articulating Boom Lift 26m | MEWP-17 |  |  | YST 07 | F | Outfitting | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Beta | MEWP Operator | Urgent | Completed |  | Overcast | 16 | FALSE | 78 | Delayed | 4 | No |  | No Conflict | Yes
BK-0760 | 2026-08-30 | 2026-09-05 | 2026-09-07 | 6 | MEWP | Articulating Boom Lift 26m | MEWP-03 |  |  | YST 08 | C | Planning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Alpha | Forklift Operator | High | Rescheduled | Project timeline shifted | Partly Cloudy | 14 | TRUE | 43 |  | 3 | No |  | No Conflict | Yes
BK-0761 | 2026-08-21 | 2026-08-24 |  | 3 | Crane | Crawler Crane | CRA-01 | 50 | 36.4 | YST 05 | B | Planning | Anchor Chain | Full Day | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Medium | Completed |  | Thunderstorm | 20 | FALSE | 51 | On Time | 2 | No |  | No Conflict | Yes
BK-0762 | 2026-08-03 | 2026-08-11 |  | 8 | MEWP | Articulating Boom Lift 26m | MEWP-01 |  |  | YST 09 | D | Commissioning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | High | Completed |  | Partly Cloudy | 3 | FALSE | 93 | On Time | 3 | No |  | No Conflict | Yes
BK-0763 | 2026-08-06 | 2026-08-19 |  | 13 | MEWP | Scissor Lift 10m | MEWP-25 |  |  | YST 03 | A | Commissioning | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Rejected | Permit not approved | Clear | 8 | FALSE | 61 |  | 2 | No |  | No Conflict | Yes
BK-0764 | 2026-08-02 | 2026-08-13 |  | 11 | Forklift | Reach Forklift | FLT-04 | 3 | 2.2 | YST D6 | B | Assembly | Valve Crates | Full Day | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Completed |  | Overcast | 13 | FALSE | 60 | Delayed | 2 | No |  | No Conflict | Yes
BK-0765 | 2026-08-12 | 2026-08-17 |  | 5 | MEWP | Articulating Boom Lift 26m | MEWP-12 |  |  | YST D3 | E | Outfitting | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Completed |  | Partly Cloudy | 15 | FALSE | 56 | Early | 3 | No |  | No Conflict | Yes
BK-0766 | 2026-08-11 | 2026-08-23 |  | 12 | MEWP | Telescopic Boom Lift 30m | MEWP-29 |  |  | YST 06 | F | Commissioning | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Completed |  | Clear | 6 | FALSE | 90 | On Time | 2 | No |  | No Conflict | Yes
BK-0767 | 2026-08-23 | 2026-08-28 |  | 5 | Forklift | Counterbalance Forklift | FLT-37 | 2.5 | 0.9 | YST 17 | F | Commissioning | Insulation Materials | Half Day (AM) | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Urgent | Cancelled | Duplicate booking | Light Rain | 17 | FALSE | 55 |  | 4 | No |  | No Conflict | Yes
BK-0768 | 2026-08-30 | 2026-09-04 |  | 5 | Cometto | SPMT 24 Axle Lines | COM-06 |  |  | YST 04 | B | Commissioning | Jacket Structure | 5 Days | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Cancelled | Budget constraint | Heavy Rain | 16 | FALSE | 26 |  | 2 | No |  | No Conflict | Yes
BK-0769 | 2026-08-16 | 2026-08-19 |  | 3 | Crane | Crawler Crane | CRA-07 | 100 | 24 | YST 07 | A | Fabrication | Accommodation Module | 3 Days | Day Shift (0700-1900) | Team Beta | Advanced Crane Operator | Low | Confirmed |  | Clear | 4 | FALSE | 47 |  | 1 | No |  | No Conflict | Yes
BK-0770 | 2026-08-14 | 2026-08-26 |  | 12 | Cometto | Cometto MSPE 8 Axle Lines | COM-05 |  |  | YST 19 | D | Commissioning | Jacket Structure | 2 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Pending |  | Overcast | 3 | FALSE | 22 |  | 2 | No |  | No Conflict | Yes
BK-0771 | 2026-08-16 | 2026-08-20 |  | 4 | Crane | Workshop Crane | WOR-18 | 20 | 4.5 | YST D2 | F | Outfitting | Helideck Module | 5 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | High | Completed |  | High Wind | 37 | FALSE | 97 | On Time | 3 | No |  | No Conflict | Yes
BK-0772 | 2026-08-09 | 2026-08-16 |  | 7 | Crane | Workshop Crane | WOR-11 | 10 | 2.6 | YST D5 | F | Outfitting | Anchor Chain | Full Day | Night Shift (1900-0700) | Team Alpha | Heavy Lift Specialist | Medium | Pending |  | Clear | 15 | FALSE | 57 |  | 2 | No |  | No Conflict | Yes
BK-0773 | 2026-08-28 | 2026-09-05 |  | 8 | Crane | Tower Crane | TOW-06 | 40 | 24.8 | YST 10 | F | Planning | Transformer Unit | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Pending |  | Clear | 5 | FALSE | 48 |  | 3 | No |  | No Conflict | Yes
BK-0774 | 2026-08-10 | 2026-08-20 |  | 10 | Crane | Tower Crane | TOW-05 | 25 | 5.7 | YST D2 | F | Commissioning | Engine Module | 10 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Medium | Confirmed |  | Thunderstorm | 32 | FALSE | 61 |  | 2 | No |  | No Conflict | Yes
BK-0775 | 2026-08-28 | 2026-09-05 |  | 8 | Forklift | Heavy Duty Forklift | FLT-07 | 25 | 21 | YST D6 | C | Commissioning | Insulation Materials | Full Day | Day Shift (0700-1900) | Team Echo | Advanced Operator | High | Completed |  | Partly Cloudy | 18 | FALSE | 74 | On Time | 3 | No |  | No Conflict | Yes
BK-0776 | 2026-08-16 | 2026-08-17 |  | 1 | Crane | Workshop Crane | WOR-03 | 20 | 5 | YST 06 | B | Fabrication | Engine Module | Full Day | Night Shift (1900-0700) | Team Gamma | Basic Crane Operator | Medium | Pending |  | Clear | 7 | FALSE | 32 |  | 2 | No |  | No Conflict | Yes
BK-0777 | 2026-08-15 | 2026-08-23 |  | 8 | MEWP | Articulating Boom Lift 26m | MEWP-03 |  |  | YST D4 | B | Fabrication | Personnel Access Work | 10 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Pending |  | Clear | 6 | FALSE | 45 |  | 2 | Yes | BK-0801 | Later Request - Reassigned | No
BK-0778 | 2026-08-01 | 2026-08-06 |  | 5 | MEWP | Scissor Lift 10m | MEWP-17 |  |  | YST 04 | C | Fabrication | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Rejected | Permit not approved | Heavy Rain | 16 | FALSE | 33 |  | 2 | No |  | No Conflict | Yes
BK-0779 | 2026-08-04 | 2026-08-07 | 2026-08-11 | 3 | MEWP | Scissor Lift 10m | MEWP-22 |  |  | YST 05 | A | Testing | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Rescheduled | Equipment breakdown | Clear | 15 | FALSE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0780 | 2026-08-02 | 2026-08-11 |  | 9 | Crane | Crawler Crane | CRA-12 | 250 | 86.2 | YST 01 | E | Testing | Mega Block Section | 2 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | High | Confirmed |  | Heavy Rain | 15 | FALSE | 71 |  | 3 | No |  | No Conflict | Yes
BK-0781 | 2026-08-25 | 2026-08-27 |  | 2 | MEWP | Telescopic Boom Lift 30m | MEWP-18 |  |  | YST 03 | C | Outfitting | Personnel Access Work | Half Day (PM) | Night Shift (1900-0700) | Team Beta | Advanced Operator | High | Confirmed |  | Clear | 12 | FALSE | 74 |  | 3 | No |  | No Conflict | Yes
BK-0782 | 2026-08-20 | 2026-08-24 |  | 4 | Crane | Mobile Crane | MOB-19 | 100 | 78.5 | YST 07 | B | Outfitting | Helideck Module | 5 Days | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | High | Rejected | Safety inspection required first | Partly Cloudy | 17 | FALSE | 36 |  | 3 | No |  | No Conflict | Yes
BK-0783 | 2026-08-21 | 2026-08-25 |  | 4 | Crane | Crawler Crane | CRA-11 | 100 | 35.8 | YST 06 | C | Testing | Riser Assembly | 7 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Urgent | Confirmed |  | Overcast | 10 | FALSE | 82 |  | 4 | No |  | No Conflict | Yes
BK-0784 | 2026-08-07 | 2026-08-16 |  | 9 | Forklift | Heavy Duty Forklift | FLT-35 | 20 | 8.5 | YST 07 | F | Commissioning | Bolt Pallets | 3 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Confirmed |  | Heavy Rain | 17 | FALSE | 93 |  | 3 | No |  | No Conflict | Yes
BK-0785 | 2026-08-11 | 2026-08-14 |  | 3 | MEWP | Telescopic Boom Lift 30m | MEWP-08 |  |  | YST 12 | C | Testing | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Echo | MEWP Operator | Medium | Completed |  | Clear | 5 | FALSE | 92 | Delayed | 2 | No |  | No Conflict | Yes
BK-0786 | 2026-08-13 | 2026-08-14 |  | 1 | Crane | Crawler Crane | CRA-18 | 250 | 66.2 | YST 08 | D | Commissioning | Riser Assembly | 3 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Medium | Completed |  | High Wind | 44 | FALSE | 60 | On Time | 2 | No |  | No Conflict | Yes
BK-0787 | 2026-08-06 | 2026-08-08 | 2026-08-12 | 2 | Forklift | Counterbalance Forklift | FLT-18 | 2.5 | 0.8 | YST D8 | F | Outfitting | Safety Equipment | Half Day (PM) | Day Shift (0700-1900) | Team Beta | Advanced Operator | High | Rescheduled | Permit delay | Clear | 3 | FALSE | 38 |  | 3 | No |  | No Conflict | Yes
BK-0788 | 2026-08-08 | 2026-08-11 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-27 |  |  | YST 12 | D | Fabrication | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Completed |  | Partly Cloudy | 2 | FALSE | 45 | Delayed | 2 | No |  | No Conflict | Yes
BK-0789 | 2026-08-20 | 2026-09-02 | 2026-09-03 | 13 | Crane | Mobile Crane | MOB-14 | 25 | 11.5 | YST 02 | C | Planning | Mega Block Section | Full Day | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Urgent | Rescheduled | Material delivery delayed | Clear | 11 | FALSE | 34 |  | 4 | No |  | No Conflict | Yes
BK-0790 | 2026-08-28 | 2026-08-30 |  | 2 | Cometto | SPMT 24 Axle Lines | COM-10 |  |  | YST 03 | D | Testing | Offshore Platform Topside | 5 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Medium | Cancelled | Budget constraint | Partly Cloudy | 2 | FALSE | 44 |  | 2 | No |  | No Conflict | Yes
BK-0791 | 2026-08-27 | 2026-09-01 |  | 5 | Crane | Goliath Gantry Crane | GC-17 | 200 | 85.5 | YST 19 | B | Commissioning | Flare Tower Section | Full Day | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | Medium | Completed |  | Clear | 9 | FALSE | 41 | Delayed | 2 | No |  | No Conflict | Yes
BK-0792 | 2026-08-19 | 2026-08-22 |  | 3 | Cometto | SPMT 24 Axle Lines | COM-07 |  |  | YST 19 | D | Planning | Engine Module | 3 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Cancelled | Duplicate booking | Partly Cloudy | 13 | FALSE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0793 | 2026-08-16 | 2026-08-19 |  | 3 | Crane | Tower Crane | TOW-12 | 15 | 7.7 | YST 09 | F | Testing | Anchor Chain | Half Day (AM) | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Urgent | Confirmed |  | Clear | 4 | FALSE | 49 |  | 4 | No |  | No Conflict | Yes
BK-0794 | 2026-08-10 | 2026-08-13 |  | 3 | Crane | Goliath Gantry Crane | GC-13 | 240 | 183.7 | YST 04 | F | Fabrication | Accommodation Module | 3 Days | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | High | Pending |  | Clear | 17 | FALSE | 35 |  | 3 | No |  | No Conflict | Yes
BK-0795 | 2026-08-01 | 2026-08-11 |  | 10 | Crane | Workshop Crane | WOR-04 | 10 | 3.5 | YST 06 | C | Commissioning | Helideck Module | Full Day | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | Medium | Completed |  | Clear | 7 | FALSE | 94 | On Time | 2 | No |  | No Conflict | Yes
BK-0796 | 2026-08-09 | 2026-08-15 |  | 6 | Crane | Tower Crane | TOW-06 | 10 | 3.5 | YST D2 | C | Testing | Structural Steel Module | Half Day (AM) | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Medium | Cancelled | Client cancelled | Light Rain | 16 | FALSE | 65 |  | 2 | No |  | No Conflict | Yes
BK-0797 | 2026-08-08 | 2026-08-11 |  | 3 | MEWP | Scissor Lift 10m | MEWP-13 |  |  | YST 03 | D | Testing | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Cancelled | Material not ready | Partly Cloudy | 14 | FALSE | 61 |  | 3 | No |  | No Conflict | Yes
BK-0798 | 2026-08-31 | 2026-09-06 |  | 6 | Forklift | Reach Forklift | FLT-11 | 2.5 | 1.3 | YST 17 | C | Assembly | Scaffolding Materials | 3 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Pending |  | Clear | 15 | FALSE | 21 |  | 2 | Yes | BK-0822 | Later Request - Reassigned | No
BK-0799 | 2026-08-11 | 2026-08-17 |  | 6 | Forklift | Heavy Duty Forklift | FLT-29 | 25 | 21.1 | YST D5 | D | Fabrication | Welding Materials | 7 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Rejected | Location conflict with another operation | Clear | 9 | FALSE | 49 |  | 2 | No |  | No Conflict | Yes
BK-0800 | 2026-08-12 | 2026-08-23 |  | 11 | MEWP | Telescopic Boom Lift 30m | MEWP-08 |  |  | YST 02 | D | Outfitting | Personnel Access Work | 10 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Confirmed |  | Heavy Rain | 23 | FALSE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0801 | 2026-08-12 | 2026-08-22 | 2026-08-25 | 10 | MEWP | Scissor Lift 10m | MEWP-03 |  |  | YST D4 | B | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Medium | Rescheduled | Client request | Overcast | 10 | TRUE | 53 |  | 2 | Yes | BK-0777 | First-Come-First-Served | Yes
BK-0802 | 2026-08-01 | 2026-08-06 | 2026-08-13 | 5 | Crane | Tower Crane | TOW-11 | 40 | 24 | YST 17 | D | Outfitting | Construction Materials | Full Day | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | High | Rescheduled | Permit delay | Light Rain | 3 | FALSE | 29 |  | 3 | No |  | No Conflict | Yes
BK-0803 | 2026-08-13 | 2026-08-17 |  | 4 | Cometto | SPMT 16 Axle Lines | COM-04 |  |  | YST 03 | A | Fabrication | Hull Block Section | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Confirmed |  | Clear | 8 | FALSE | 92 |  | 2 | No |  | No Conflict | Yes
BK-0804 | 2026-08-29 | 2026-09-01 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-01 |  |  | YST 07 | A | Fabrication | Personnel Access Work | 14 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Completed |  | Partly Cloudy | 7 | FALSE | 71 | On Time | 2 | No |  | No Conflict | Yes
BK-0805 | 2026-08-22 | 2026-08-28 |  | 6 | Forklift | Telehandler Forklift | FLT-21 | 7 | 3.9 | YST 09 | E | Fabrication | Paint Drums | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Cancelled | Budget constraint | Clear | 2 | FALSE | 39 |  | 3 | No |  | No Conflict | Yes
BK-0806 | 2026-08-16 | 2026-08-29 |  | 13 | Forklift | Counterbalance Forklift | FLT-07 | 5 | 2.6 | YST D6 | B | Planning | Gasket Boxes | 5 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Urgent | Completed |  | Overcast | 18 | FALSE | 66 | Delayed | 4 | No |  | No Conflict | Yes
BK-0807 | 2026-08-10 | 2026-08-12 | 2026-08-16 | 2 | Crane | Mobile Crane | MOB-02 | 25 | 12.3 | YST 06 | C | Assembly | Riser Assembly | 2 Days | Night Shift (1900-0700) | Team Beta | Lifting Supervisor | Medium | Rescheduled | Material delivery delayed | Clear | 9 | FALSE | 45 |  | 2 | No |  | No Conflict | Yes
BK-0808 | 2026-08-28 | 2026-08-31 |  | 3 | Crane | Goliath Gantry Crane | GC-16 | 300 | 221.4 | YST 01 | A | Fabrication | Construction Materials | 3 Days | Night Shift (1900-0700) | Team Alpha | Lifting Supervisor | Low | Rejected | Insufficient lead time | Partly Cloudy | 17 | FALSE | 20 |  | 1 | No |  | No Conflict | Yes
BK-0809 | 2026-08-16 | 2026-08-19 | 2026-08-22 | 3 | Crane | Crawler Crane | CRA-03 | 150 | 101.1 | YST D3 | A | Planning | Construction Materials | Half Day (AM) | Night Shift (1900-0700) | Team Gamma | Rigging Supervisor | Low | Rescheduled | Safety stand-down | Overcast | 8 | TRUE | 57 |  | 1 | No |  | No Conflict | Yes
BK-0810 | 2026-08-20 | 2026-08-30 |  | 10 | Crane | Tower Crane | TOW-15 | 25 | 5.5 | YST 12 | D | Testing | Engine Module | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Rigging Supervisor | High | Pending |  | Clear | 11 | FALSE | 62 |  | 3 | No |  | No Conflict | Yes
BK-0811 | 2026-08-06 | 2026-08-14 |  | 8 | Forklift | Telehandler Forklift | FLT-27 | 5 | 1.7 | YST 10 | D | Fabrication | Consumables Pallet | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | High | Completed |  | Overcast | 3 | FALSE | 47 | On Time | 3 | No |  | No Conflict | Yes
BK-0812 | 2026-08-15 | 2026-08-17 |  | 2 | Cometto | SPMT 16 Axle Lines | COM-12 |  |  | YST 20 | F | Commissioning | Mega Block Section | 2 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Confirmed |  | High Wind | 42 | FALSE | 59 |  | 2 | No |  | No Conflict | Yes
BK-0813 | 2026-08-30 | 2026-09-07 |  | 8 | Forklift | Counterbalance Forklift | FLT-13 | 5 | 2.8 | YST 06 | D | Commissioning | Consumables Pallet | 2 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Rejected | Location conflict with another operation | High Wind | 35 | FALSE | 68 |  | 2 | No |  | No Conflict | Yes
BK-0814 | 2026-08-19 | 2026-08-30 |  | 11 | Crane | Goliath Gantry Crane | GC-18 | 300 | 189.7 | YST 04 | E | Outfitting | Engine Module | 7 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Urgent | Completed |  | High Wind | 31 | FALSE | 89 | On Time | 4 | No |  | No Conflict | Yes
BK-0815 | 2026-08-12 | 2026-08-20 |  | 8 | Forklift | Telehandler Forklift | FLT-31 | 5 | 3.1 | YST 01 | F | Commissioning | Insulation Materials | 5 Days | Night Shift (1900-0700) | Team Beta | MEWP Operator | Medium | Completed |  | Overcast | 10 | FALSE | 77 | Delayed | 2 | No |  | No Conflict | Yes
BK-0816 | 2026-08-20 | 2026-08-23 |  | 3 | Forklift | Counterbalance Forklift | FLT-35 | 7 | 6 | YST D4 | F | Planning | Electrical Cables | 14 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Completed |  | Partly Cloudy | 15 | FALSE | 78 | Delayed | 2 | No |  | No Conflict | Yes
BK-0817 | 2026-08-30 | 2026-09-03 |  | 4 | MEWP | Telescopic Boom Lift 30m | MEWP-10 |  |  | YST 09 | D | Assembly | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | High | Pending |  | Clear | 9 | FALSE | 48 |  | 3 | No |  | No Conflict | Yes
BK-0818 | 2026-08-08 | 2026-08-13 |  | 5 | Crane | Level Luffing Crane | LLC 18 | 50 | 39.7 | YST D2 | C | Testing | Flare Tower Section | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | High | Cancelled | Budget constraint | Overcast | 17 | FALSE | 38 |  | 3 | No |  | No Conflict | Yes
BK-0819 | 2026-08-25 | 2026-08-27 | 2026-08-29 | 2 | Crane | Mobile Crane | MOB-07 | 75 | 22.6 | YST 03 | A | Planning | Transformer Unit | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Rescheduled | Higher priority job took precedence | Clear | 10 | FALSE | 47 |  | 3 | No |  | No Conflict | Yes
BK-0820 | 2026-08-24 | 2026-08-27 | 2026-09-03 | 3 | Crane | Crawler Crane | CRA-18 | 150 | 116.9 | YST D1 | A | Fabrication | Turret Assembly | 3 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Urgent | Rescheduled | Safety stand-down | Clear | 10 | FALSE | 52 |  | 4 | No |  | No Conflict | Yes
BK-0821 | 2026-08-27 | 2026-09-05 |  | 9 | MEWP | Scissor Lift 10m | MEWP-22 |  |  | YST D4 | D | Fabrication | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Gamma | Forklift Operator | High | Completed |  | Partly Cloudy | 10 | FALSE | 98 | Early | 3 | No |  | No Conflict | Yes
BK-0822 | 2026-08-26 | 2026-09-08 | 2026-09-10 | 13 | Forklift | Counterbalance Forklift | FLT-11 | 3 | 2.3 | YST 05 | F | Assembly | Paint Drums | 3 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | Medium | Rescheduled | Client request | Clear | 14 | FALSE | 45 |  | 2 | Yes | BK-0798 | First-Come-First-Served | Yes
BK-0823 | 2026-08-06 | 2026-08-09 |  | 3 | MEWP | Scissor Lift 10m | MEWP-27 |  |  | YST 08 | C | Commissioning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Delta | Basic Operator | High | Completed |  | Partly Cloudy | 3 | FALSE | 52 | On Time | 3 | No |  | No Conflict | Yes
BK-0824 | 2026-08-12 | 2026-08-13 |  | 1 | Cometto | SPMT 16 Axle Lines | COM-07 |  |  | YST 18 | A | Testing | Mega Block Section | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Urgent | Confirmed |  | Partly Cloudy | 5 | FALSE | 70 |  | 4 | No |  | No Conflict | Yes
BK-0825 | 2026-08-16 | 2026-08-23 |  | 7 | MEWP | Articulating Boom Lift 26m | MEWP-20 |  |  | YST 04 | D | Assembly | Personnel Access Work | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Completed |  | Clear | 5 | FALSE | 59 | Delayed | 2 | No |  | No Conflict | Yes
BK-0826 | 2026-09-23 | 2026-09-27 |  | 4 | Crane | Goliath Gantry Crane | GC-17 | 300 | 119 | YST 04 | C | Outfitting | Flare Tower Section | 14 Days | Night Shift (1900-0700) | Team Gamma | Rigging Supervisor | Low | Completed |  | Clear | 11 | FALSE | 95 | On Time | 1 | No |  | No Conflict | Yes
BK-0827 | 2026-09-17 | 2026-09-24 |  | 7 | Forklift | Telehandler Forklift | FLT-22 | 3 | 2.4 | YST 04 | B | Planning | Gasket Boxes | 2 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Rejected | Safety inspection required first | Clear | 4 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0828 | 2026-09-10 | 2026-09-21 |  | 11 | Cometto | Cometto MSPE 8 Axle Lines | COM-05 |  |  | YST 14 | B | Planning | Engine Module | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Cancelled | Material not ready | Clear | 2 | FALSE | 22 |  | 2 | No |  | No Conflict | Yes
BK-0829 | 2026-09-16 | 2026-09-26 |  | 10 | Crane | Level Luffing Crane | LLC 18 | 50 | 24.1 | YST 06 | E | Commissioning | Construction Materials | 7 Days | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | Medium | Cancelled | Project postponed | Heavy Rain | 10 | FALSE | 30 |  | 2 | No |  | No Conflict | Yes
BK-0830 | 2026-09-24 | 2026-10-07 |  | 13 | Forklift | Heavy Duty Forklift | FLT-37 | 25 | 10.4 | YST 01 | D | Fabrication | Gasket Boxes | 5 Days | Night Shift (1900-0700) | Team Beta | Forklift Operator | Medium | Completed |  | Overcast | 14 | FALSE | 62 | On Time | 2 | No |  | No Conflict | Yes
BK-0831 | 2026-09-19 | 2026-09-24 |  | 5 | MEWP | Articulating Boom Lift 26m | MEWP-20 |  |  | YST 08 | A | Planning | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Cancelled | Project postponed | Partly Cloudy | 8 | FALSE | 56 |  | 2 | No |  | No Conflict | Yes
BK-0832 | 2026-09-06 | 2026-09-16 |  | 10 | MEWP | Boom Lift 20m | MEWP-23 |  |  | YST 05 | D | Fabrication | Personnel Access Work | Half Day (AM) | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Low | Confirmed |  | High Wind | 33 | FALSE | 76 |  | 1 | No |  | No Conflict | Yes
BK-0833 | 2026-09-01 | 2026-09-09 |  | 8 | Cometto | Cometto MSPE 8 Axle Lines | COM-06 |  |  | YST 14 | C | Assembly | Engine Module | Full Day | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | High | Confirmed |  | High Wind | 37 | FALSE | 83 |  | 3 | No |  | No Conflict | Yes
BK-0834 | 2026-09-09 | 2026-09-14 |  | 5 | Crane | Workshop Crane | WOR-12 | 10 | 4.6 | YST 10 | C | Outfitting | Anchor Chain | Full Day | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | Medium | Completed |  | Clear | 2 | FALSE | 90 | Early | 2 | No |  | No Conflict | Yes
BK-0835 | 2026-09-02 | 2026-09-11 |  | 9 | MEWP | Boom Lift 20m | MEWP-04 |  |  | YST D2 | D | Testing | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Medium | Rejected | Weather conditions unsafe | Clear | 16 | FALSE | 64 |  | 2 | No |  | No Conflict | Yes
BK-0836 | 2026-09-28 | 2026-10-02 |  | 4 | MEWP | Telescopic Boom Lift 30m | MEWP-06 |  |  | YST 09 | D | Outfitting | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Low | Completed |  | Clear | 18 | FALSE | 49 | On Time | 1 | No |  | No Conflict | Yes
BK-0837 | 2026-09-24 | 2026-09-29 |  | 5 | Crane | Level Luffing Crane | LLC 10 | 50 | 37.7 | YST D1 | C | Assembly | Helideck Module | 5 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Urgent | Confirmed |  | Light Rain | 18 | FALSE | 73 |  | 4 | No |  | No Conflict | Yes
BK-0838 | 2026-09-01 | 2026-09-04 |  | 3 | Crane | Workshop Crane | WOR-16 | 20 | 12 | YST 14 | F | Assembly | Hull Block Section | Full Day | Day Shift (0700-1900) | Team Gamma | Lifting Supervisor | High | Completed |  | Overcast | 14 | FALSE | 76 | Delayed | 3 | No |  | No Conflict | Yes
BK-0839 | 2026-09-04 | 2026-09-09 |  | 5 | MEWP | Boom Lift 20m | MEWP-02 |  |  | YST 11 | D | Testing | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | Medium | Completed |  | Clear | 4 | FALSE | 97 | On Time | 2 | No |  | No Conflict | Yes
BK-0840 | 2026-09-14 | 2026-09-25 |  | 11 | Crane | Mobile Crane | MOB-18 | 25 | 6.8 | YST 02 | A | Assembly | Workshop Equipment | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Medium | Completed |  | Clear | 15 | FALSE | 77 | Early | 2 | No |  | No Conflict | Yes
BK-0841 | 2026-09-29 | 2026-10-02 |  | 3 | Crane | Goliath Gantry Crane | GC-15 | 600 | 356.6 | YST 01 | D | Commissioning | Engine Module | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Rigging Supervisor | Urgent | Completed |  | Clear | 7 | FALSE | 40 | Early | 4 | No |  | No Conflict | Yes
BK-0842 | 2026-09-16 | 2026-09-26 |  | 10 | Crane | Mobile Crane | MOB-17 | 75 | 16.2 | YST 02 | C | Outfitting | Engine Module | 3 Days | Night Shift (1900-0700) | Team Gamma | Basic Crane Operator | Low | Cancelled | Budget constraint | Overcast | 7 | FALSE | 21 |  | 1 | No |  | No Conflict | Yes
BK-0843 | 2026-09-22 | 2026-09-26 |  | 4 | Crane | Goliath Gantry Crane | GC-13 | 240 | 65 | YST 19 | D | Fabrication | Hull Block Section | Full Day | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | Medium | Confirmed |  | Overcast | 3 | FALSE | 53 |  | 2 | No |  | No Conflict | Yes
BK-0844 | 2026-09-12 | 2026-09-19 |  | 7 | Forklift | Telehandler Forklift | FLT-11 | 7 | 3 | YST 05 | D | Planning | Safety Equipment | 3 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Low | Confirmed |  | Clear | 7 | FALSE | 46 |  | 1 | No |  | No Conflict | Yes
BK-0845 | 2026-09-14 | 2026-09-17 |  | 3 | Forklift | Telehandler Forklift | FLT-39 | 5 | 4.3 | YST 15 | D | Assembly | PPE Supplies | 3 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Cancelled | Client cancelled | Partly Cloudy | 8 | FALSE | 32 |  | 2 | No |  | No Conflict | Yes
BK-0846 | 2026-09-13 | 2026-09-17 | 2026-09-18 | 4 | Forklift | Reach Forklift | FLT-09 | 1.5 | 0.5 | YST D8 | E | Outfitting | Insulation Materials | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Rescheduled | Operator reassigned | Partly Cloudy | 6 | FALSE | 35 |  | 2 | No |  | No Conflict | Yes
BK-0847 | 2026-09-17 | 2026-09-27 |  | 10 | MEWP | Scissor Lift 10m | MEWP-18 |  |  | YST 08 | E | Fabrication | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Echo | Advanced Operator | Low | Completed |  | Light Rain | 3 | FALSE | 94 | Delayed | 1 | No |  | No Conflict | Yes
BK-0848 | 2026-09-05 | 2026-09-15 |  | 10 | Crane | Workshop Crane | WOR-15 | 10 | 2.2 | YST 08 | D | Fabrication | Construction Materials | Half Day (AM) | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | Low | Rejected | Crane under scheduled maintenance | Overcast | 12 | FALSE | 64 |  | 1 | No |  | No Conflict | Yes
BK-0849 | 2026-09-01 | 2026-09-12 |  | 11 | Cometto | Cometto MSPE 8 Axle Lines | COM-12 |  |  | YST 13 | A | Outfitting | Hull Block Section | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | High | Completed |  | Light Rain | 13 | FALSE | 80 | Delayed | 3 | No |  | No Conflict | Yes
BK-0850 | 2026-09-20 | 2026-09-21 |  | 1 | Crane | Crawler Crane | CRA-04 | 150 | 55.8 | YST 07 | A | Testing | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | High | Completed |  | Light Rain | 17 | FALSE | 89 | On Time | 3 | No |  | No Conflict | Yes
BK-0851 | 2026-09-06 | 2026-09-16 |  | 10 | Crane | Tower Crane | TOW-16 | 10 | 4.1 | YST 17 | F | Assembly | Anchor Chain | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Low | Confirmed |  | Heavy Rain | 22 | FALSE | 63 |  | 1 | Yes | BK-0908 | Yielded to Higher Priority | No
BK-0852 | 2026-09-24 | 2026-09-30 | 2026-10-05 | 6 | MEWP | Telescopic Boom Lift 30m | MEWP-19 |  |  | YST D1 | C | Commissioning | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Rescheduled | Permit delay | Clear | 11 | FALSE | 22 |  | 2 | No |  | No Conflict | Yes
BK-0853 | 2026-09-23 | 2026-09-24 |  | 1 | MEWP | Telescopic Boom Lift 30m | MEWP-08 |  |  | YST 07 | A | Testing | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Echo | Basic Operator | Medium | Completed |  | Light Rain | 18 | FALSE | 44 | On Time | 2 | No |  | No Conflict | Yes
BK-0854 | 2026-09-26 | 2026-09-27 |  | 1 | Crane | Mobile Crane | MOB-18 | 75 | 37.4 | YST D1 | F | Fabrication | Engine Module | 7 Days | Night Shift (1900-0700) | Team Gamma | Lifting Supervisor | High | Completed |  | Partly Cloudy | 17 | FALSE | 73 | On Time | 3 | No |  | No Conflict | Yes
BK-0855 | 2026-09-23 | 2026-10-02 |  | 9 | MEWP | Scissor Lift 10m | MEWP-09 |  |  | YST D1 | C | Commissioning | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Beta | Advanced Operator | High | Cancelled | Project postponed | Clear | 11 | FALSE | 21 |  | 3 | No |  | No Conflict | Yes
BK-0856 | 2026-09-08 | 2026-09-19 | 2026-09-21 | 11 | Forklift | Heavy Duty Forklift | FLT-14 | 20 | 10.7 | YST D4 | D | Assembly | Scaffolding Materials | Half Day (PM) | Night Shift (1900-0700) | Team Gamma | Advanced Operator | Low | Rescheduled | Equipment breakdown | High Wind | 45 | FALSE | 22 |  | 1 | No |  | No Conflict | Yes
BK-0857 | 2026-09-13 | 2026-09-22 |  | 9 | Cometto | SPMT 16 Axle Lines | COM-11 |  |  | YST 13 | D | Assembly | Jacket Structure | Full Day | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Low | Confirmed |  | Partly Cloudy | 10 | FALSE | 72 |  | 1 | No |  | No Conflict | Yes
BK-0858 | 2026-09-19 | 2026-10-02 |  | 13 | MEWP | Scissor Lift 10m | MEWP-24 |  |  | YST 08 | C | Assembly | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Medium | Confirmed |  | Overcast | 6 | FALSE | 93 |  | 2 | No |  | No Conflict | Yes
BK-0859 | 2026-09-23 | 2026-09-25 |  | 2 | Cometto | Cometto MSPE 8 Axle Lines | COM-05 |  |  | YST 05 | B | Testing | Engine Module | Full Day | Night Shift (1900-0700) | Team Beta | MEWP Operator | Urgent | Rejected | Crane already booked | Clear | 12 | FALSE | 34 |  | 4 | No |  | No Conflict | Yes
BK-0860 | 2026-09-26 | 2026-09-29 | 2026-10-03 | 3 | Crane | Level Luffing Crane | LLC 15 | 300 | 148.7 | YST 16 | B | Testing | Transformer Unit | 5 Days | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Low | Rescheduled | Equipment breakdown | Clear | 8 | FALSE | 22 |  | 1 | No |  | No Conflict | Yes
BK-0861 | 2026-09-28 | 2026-09-29 |  | 1 | Crane | Level Luffing Crane | LLC 16A | 300 | 220.5 | YST D1 | D | Testing | Mooring Winch | 10 Days | Night Shift (1900-0700) | Team Alpha | Basic Crane Operator | Medium | Pending |  | Overcast | 18 | FALSE | 31 |  | 2 | No |  | No Conflict | Yes
BK-0862 | 2026-09-07 | 2026-09-17 |  | 10 | Forklift | Counterbalance Forklift | FLT-08 | 2.5 | 1.1 | YST 11 | D | Assembly | Scaffolding Materials | 3 Days | Night Shift (1900-0700) | Team Echo | Basic Operator | Urgent | Completed |  | Partly Cloudy | 17 | FALSE | 78 | On Time | 4 | No |  | No Conflict | Yes
BK-0863 | 2026-09-24 | 2026-10-05 |  | 11 | Forklift | Heavy Duty Forklift | FLT-09 | 25 | 9.1 | YST 12 | E | Commissioning | Bolt Pallets | 7 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Low | Confirmed |  | Light Rain | 11 | FALSE | 54 |  | 1 | No |  | No Conflict | Yes
BK-0864 | 2026-09-13 | 2026-09-19 |  | 6 | Crane | Level Luffing Crane | LLC 14 | 300 | 109.5 | YST 05 | E | Fabrication | Helideck Module | Full Day | Night Shift (1900-0700) | Team Beta | Heavy Lift Specialist | Urgent | Cancelled | Client cancelled | Clear | 16 | FALSE | 25 |  | 4 | No |  | No Conflict | Yes
BK-0865 | 2026-09-09 | 2026-09-21 |  | 12 | Cometto | SPMT 16 Axle Lines | COM-09 |  |  | YST 03 | C | Fabrication | Jacket Structure | 2 Days | Night Shift (1900-0700) | Team Gamma | Advanced Operator | High | Rejected | Crane under scheduled maintenance | Partly Cloudy | 14 | FALSE | 26 |  | 3 | No |  | No Conflict | Yes
BK-0866 | 2026-09-04 | 2026-09-13 |  | 9 | Crane | Level Luffing Crane | LLC 02 | 30 | 7.3 | YST 07 | A | Outfitting | Flare Tower Section | 3 Days | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | Medium | Cancelled | Project postponed | Clear | 16 | FALSE | 26 |  | 2 | No |  | No Conflict | Yes
BK-0867 | 2026-09-06 | 2026-09-15 |  | 9 | Crane | Crawler Crane | CRA-14 | 150 | 85.9 | YST 01 | D | Outfitting | Flare Tower Section | 3 Days | Day Shift (0700-1900) | Team Echo | Lifting Supervisor | Medium | Cancelled | Duplicate booking | Light Rain | 6 | FALSE | 38 |  | 2 | No |  | No Conflict | Yes
BK-0868 | 2026-09-24 | 2026-10-07 |  | 13 | Crane | Crawler Crane | CRA-07 | 50 | 17 | YST D1 | E | Fabrication | Mooring Winch | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Urgent | Cancelled | Client cancelled | Partly Cloudy | 8 | FALSE | 23 |  | 4 | No |  | No Conflict | Yes
BK-0869 | 2026-09-04 | 2026-09-12 |  | 8 | MEWP | Scissor Lift 10m | MEWP-17 |  |  | YST 02 | E | Fabrication | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Low | Completed |  | High Wind | 39 | FALSE | 77 | Delayed | 1 | No |  | No Conflict | Yes
BK-0870 | 2026-09-13 | 2026-09-22 |  | 9 | Cometto | SPMT 24 Axle Lines | COM-10 |  |  | YST 20 | E | Testing | Jacket Structure | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Pending |  | Overcast | 16 | FALSE | 53 |  | 2 | No |  | No Conflict | Yes
BK-0871 | 2026-09-10 | 2026-09-13 |  | 3 | Forklift | Reach Forklift | FLT-37 | 2 | 0.8 | YST 05 | B | Fabrication | Paint Drums | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Forklift Operator | Urgent | Pending |  | Heavy Rain | 13 | FALSE | 34 |  | 4 | No |  | No Conflict | Yes
BK-0872 | 2026-09-10 | 2026-09-19 |  | 9 | Forklift | Reach Forklift | FLT-27 | 3 | 2.1 | YST 19 | A | Outfitting | Pipe Bundles | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Medium | Completed |  | Light Rain | 2 | FALSE | 53 | On Time | 2 | No |  | No Conflict | Yes
BK-0873 | 2026-09-24 | 2026-09-27 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-21 |  |  | YST 12 | A | Assembly | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Beta | MEWP Operator | High | Pending |  | Light Rain | 13 | FALSE | 62 |  | 3 | No |  | No Conflict | Yes
BK-0874 | 2026-09-04 | 2026-09-18 |  | 14 | Forklift | Reach Forklift | FLT-26 | 2.5 | 1.3 | YST 01 | A | Testing | Welding Materials | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Cancelled | Project postponed | Partly Cloudy | 14 | FALSE | 20 |  | 2 | No |  | No Conflict | Yes
BK-0875 | 2026-09-18 | 2026-09-24 |  | 6 | Crane | Workshop Crane | WOR-17 | 10 | 5.5 | YST 10 | C | Outfitting | Helideck Module | 2 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Medium | Confirmed |  | Partly Cloudy | 9 | FALSE | 94 |  | 2 | No |  | No Conflict | Yes
BK-0876 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 4 | Forklift | Counterbalance Forklift | FLT-01 | 3 | 2.4 | YST 16 | D | Planning | Valve Crates | Half Day (AM) | Night Shift (1900-0700) | Team Delta | Forklift Operator | High | Rescheduled | Client request | High Wind | 28 | TRUE | 25 |  | 3 | No |  | No Conflict | Yes
BK-0877 | 2026-09-07 | 2026-09-17 |  | 10 | Crane | Level Luffing Crane | LLC 17 | 30 | 19.9 | YST 03 | F | Assembly | Anchor Chain | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Medium | Cancelled | Budget constraint | Clear | 15 | FALSE | 32 |  | 2 | No |  | No Conflict | Yes
BK-0878 | 2026-09-28 | 2026-10-05 |  | 7 | Crane | Mobile Crane | MOB-12 | 50 | 31.4 | YST 01 | E | Assembly | Turret Assembly | Full Day | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Urgent | Completed |  | Partly Cloudy | 3 | FALSE | 48 | Delayed | 4 | No |  | No Conflict | Yes
BK-0879 | 2026-09-25 | 2026-10-06 |  | 11 | Cometto | Cometto Eco500 12 Axle Lines | COM-09 |  |  | YST 13 | D | Planning | Engine Module | 5 Days | Night Shift (1900-0700) | Team Delta | Forklift Operator | High | Rejected | Safety inspection required first | High Wind | 43 | TRUE | 69 |  | 3 | No |  | No Conflict | Yes
BK-0880 | 2026-09-09 | 2026-09-10 |  | 1 | Forklift | Telehandler Forklift | FLT-13 | 3 | 1.1 | YST 07 | F | Fabrication | Tool Containers | 2 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Urgent | Completed |  | Clear | 14 | FALSE | 45 | On Time | 4 | No |  | No Conflict | Yes
BK-0881 | 2026-09-07 | 2026-09-17 |  | 10 | Forklift | Heavy Duty Forklift | FLT-01 | 10 | 6.3 | YST 03 | F | Assembly | PPE Supplies | 2 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Medium | Pending |  | Clear | 17 | FALSE | 44 |  | 2 | No |  | No Conflict | Yes
BK-0882 | 2026-09-04 | 2026-09-07 |  | 3 | Crane | Workshop Crane | WOR-19 | 20 | 9.2 | YST 13 | D | Assembly | Accommodation Module | Half Day (AM) | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Medium | Confirmed |  | Partly Cloudy | 5 | FALSE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0883 | 2026-09-08 | 2026-09-14 |  | 6 | Cometto | Cometto MSPE 8 Axle Lines | COM-09 |  |  | YST 14 | E | Fabrication | Offshore Platform Topside | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Basic Operator | High | Completed |  | Thunderstorm | 22 | FALSE | 50 | Delayed | 3 | No |  | No Conflict | Yes
BK-0884 | 2026-09-29 | 2026-10-05 |  | 6 | Forklift | Heavy Duty Forklift | FLT-17 | 10 | 4.4 | YST D1 | D | Commissioning | Tool Containers | 3 Days | Night Shift (1900-0700) | Team Beta | Advanced Operator | High | Completed |  | Overcast | 16 | FALSE | 92 | On Time | 3 | No |  | No Conflict | Yes
BK-0885 | 2026-09-27 | 2026-10-04 |  | 7 | Forklift | Heavy Duty Forklift | FLT-22 | 20 | 10.8 | YST 14 | E | Testing | Steel Plates | Full Day | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Low | Rejected | Crane already booked | Overcast | 15 | FALSE | 64 |  | 1 | No |  | No Conflict | Yes
BK-0886 | 2026-09-02 | 2026-09-07 |  | 5 | Forklift | Heavy Duty Forklift | FLT-01 | 25 | 12.4 | YST 17 | B | Fabrication | Welding Materials | 2 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Medium | Cancelled | Material not ready | Clear | 13 | FALSE | 63 |  | 2 | No |  | No Conflict | Yes
BK-0887 | 2026-09-28 | 2026-10-06 |  | 8 | Crane | Crawler Crane | CRA-09 | 250 | 99.1 | YST 02 | B | Planning | Workshop Equipment | 2 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Medium | Rejected | Permit not approved | High Wind | 29 | FALSE | 22 |  | 2 | No |  | No Conflict | Yes
BK-0888 | 2026-09-18 | 2026-09-25 |  | 7 | Forklift | Telehandler Forklift | FLT-35 | 4 | 2.8 | YST 14 | C | Planning | Electrical Cables | 7 Days | Night Shift (1900-0700) | Team Beta | Forklift Operator | Urgent | Confirmed |  | High Wind | 32 | FALSE | 86 |  | 4 | No |  | No Conflict | Yes
BK-0889 | 2026-09-20 | 2026-09-28 |  | 8 | Crane | Crawler Crane | CRA-20 | 100 | 47.5 | YST 05 | A | Assembly | Riser Assembly | 2 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | High | Confirmed |  | Partly Cloudy | 18 | FALSE | 98 |  | 3 | No |  | No Conflict | Yes
BK-0890 | 2026-09-02 | 2026-09-10 | 2026-09-16 | 8 | Crane | Crawler Crane | CRA-18 | 100 | 36.5 | YST 04 | B | Planning | Riser Assembly | 2 Days | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Rescheduled | Permit delay | High Wind | 39 | TRUE | 60 |  | 2 | No |  | No Conflict | Yes
BK-0891 | 2026-09-15 | 2026-09-21 |  | 6 | MEWP | Telescopic Boom Lift 30m | MEWP-28 |  |  | YST 05 | B | Assembly | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Echo | Advanced Operator | Medium | Rejected | Crane under scheduled maintenance | Partly Cloudy | 8 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-0892 | 2026-09-11 | 2026-09-19 |  | 8 | Crane | Workshop Crane | WOR-02 | 10 | 6.1 | YST 11 | D | Outfitting | Pipe Spool | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Heavy Lift Specialist | Urgent | Completed |  | Overcast | 12 | FALSE | 41 | Delayed | 4 | No |  | No Conflict | Yes
BK-0893 | 2026-09-06 | 2026-09-10 |  | 4 | MEWP | Articulating Boom Lift 26m | MEWP-09 |  |  | YST 12 | B | Assembly | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Delta | Basic Operator | Medium | Completed |  | Light Rain | 11 | FALSE | 55 | Delayed | 2 | No |  | No Conflict | Yes
BK-0894 | 2026-09-05 | 2026-09-13 |  | 8 | Cometto | SPMT 16 Axle Lines | COM-04 |  |  | YST 20 | B | Assembly | Offshore Platform Topside | 7 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Urgent | Completed |  | Clear | 12 | FALSE | 88 | On Time | 4 | No |  | No Conflict | Yes
BK-0895 | 2026-09-30 | 2026-10-06 |  | 6 | Forklift | Telehandler Forklift | FLT-26 | 7 | 2.5 | YST 06 | F | Assembly | PPE Supplies | 10 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Pending |  | Clear | 18 | FALSE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0896 | 2026-09-12 | 2026-09-13 |  | 1 | MEWP | Articulating Boom Lift 26m | MEWP-28 |  |  | YST D1 | C | Assembly | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | High | Rejected | Safety inspection required first | Clear | 8 | TRUE | 63 |  | 3 | No |  | No Conflict | Yes
BK-0897 | 2026-09-29 | 2026-10-05 |  | 6 | MEWP | Scissor Lift 10m | MEWP-20 |  |  | YST D4 | B | Assembly | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Completed |  | Light Rain | 4 | FALSE | 53 | On Time | 3 | No |  | No Conflict | Yes
BK-0898 | 2026-09-03 | 2026-09-07 |  | 4 | MEWP | Articulating Boom Lift 26m | MEWP-07 |  |  | YST 11 | D | Outfitting | Personnel Access Work | Half Day (PM) | Night Shift (1900-0700) | Team Gamma | Basic Operator | High | Completed |  | Overcast | 18 | FALSE | 91 | On Time | 3 | No |  | No Conflict | Yes
BK-0899 | 2026-09-28 | 2026-10-02 |  | 4 | Crane | Tower Crane | TOW-04 | 25 | 15.4 | YST 12 | D | Outfitting | Turret Assembly | Full Day | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | Low | Completed |  | Overcast | 5 | FALSE | 75 | On Time | 1 | No |  | No Conflict | Yes
BK-0900 | 2026-09-24 | 2026-10-04 | 2026-10-11 | 10 | Forklift | Counterbalance Forklift | FLT-16 | 5 | 2.7 | YST 12 | C | Testing | Welding Materials | 7 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Rescheduled | Permit delay | Light Rain | 15 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0901 | 2026-09-15 | 2026-09-22 |  | 7 | Crane | Goliath Gantry Crane | GC-16 | 240 | 162.7 | YST 04 | F | Testing | Turret Assembly | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Heavy Lift Specialist | Medium | Cancelled | Budget constraint | Partly Cloudy | 13 | FALSE | 38 |  | 2 | No |  | No Conflict | Yes
BK-0902 | 2026-09-06 | 2026-09-12 |  | 6 | Crane | Tower Crane | TOW-14 | 10 | 2.4 | YST 10 | C | Assembly | Helideck Module | 14 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Urgent | Confirmed |  | Overcast | 9 | FALSE | 81 |  | 4 | No |  | No Conflict | Yes
BK-0903 | 2026-09-29 | 2026-10-09 |  | 10 | Forklift | Counterbalance Forklift | FLT-05 | 5 | 3.5 | YST D8 | F | Outfitting | Paint Drums | Full Day | Day Shift (0700-1900) | Team Delta | Basic Operator | Low | Completed |  | Overcast | 7 | FALSE | 58 | Early | 1 | No |  | No Conflict | Yes
BK-0904 | 2026-09-17 | 2026-09-24 |  | 7 | Crane | Tower Crane | TOW-08 | 40 | 16.8 | YST 12 | D | Fabrication | Mooring Winch | 2 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | High | Completed |  | Overcast | 6 | FALSE | 87 | Delayed | 3 | No |  | No Conflict | Yes
BK-0905 | 2026-09-30 | 2026-10-05 |  | 5 | Crane | Level Luffing Crane | LLC 06 | 300 | 218.2 | YST 07 | A | Fabrication | Helideck Module | 5 Days | Night Shift (1900-0700) | Team Alpha | Rigging Supervisor | High | Confirmed |  | Clear | 6 | FALSE | 80 |  | 3 | No |  | No Conflict | Yes
BK-0906 | 2026-09-10 | 2026-09-17 |  | 7 | Crane | Workshop Crane | WOR-08 | 10 | 4.4 | YST 06 | A | Testing | Transformer Unit | 2 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | High | Completed |  | Clear | 17 | FALSE | 82 | On Time | 3 | No |  | No Conflict | Yes
BK-0907 | 2026-09-26 | 2026-09-29 | 2026-10-04 | 3 | Crane | Mobile Crane | MOB-12 | 75 | 38 | YST 05 | A | Assembly | Turret Assembly | 3 Days | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Rescheduled | Safety stand-down | Clear | 4 | FALSE | 62 |  | 2 | No |  | No Conflict | Yes
BK-0908 | 2026-09-08 | 2026-09-16 |  | 8 | Crane | Tower Crane | TOW-16 | 15 | 11.6 | YST D3 | F | Fabrication | Engine Module | Full Day | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | Medium | Rejected | Load exceeds crane capacity | Thunderstorm | 25 | TRUE | 29 |  | 2 | Yes | BK-0851 | Priority Override | Yes
BK-0909 | 2026-09-19 | 2026-10-02 |  | 13 | Forklift | Heavy Duty Forklift | FLT-28 | 25 | 12.4 | YST 06 | E | Testing | Insulation Materials | 5 Days | Day Shift (0700-1900) | Team Echo | Advanced Operator | Low | Completed |  | Clear | 7 | FALSE | 55 | Delayed | 1 | No |  | No Conflict | Yes
BK-0910 | 2026-09-28 | 2026-10-09 |  | 11 | Crane | Tower Crane | TOW-04 | 25 | 13.6 | YST 16 | B | Outfitting | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | High | Completed |  | Clear | 2 | FALSE | 56 | Delayed | 3 | No |  | No Conflict | Yes
BK-0911 | 2026-09-25 | 2026-10-01 |  | 6 | Cometto | Cometto MSPE 8 Axle Lines | COM-10 |  |  | YST 03 | D | Planning | Offshore Platform Topside | 5 Days | Night Shift (1900-0700) | Team Delta | Basic Operator | Low | Pending |  | Clear | 12 | FALSE | 58 |  | 1 | No |  | No Conflict | Yes
BK-0912 | 2026-09-15 | 2026-09-24 |  | 9 | Forklift | Counterbalance Forklift | FLT-09 | 3 | 1.6 | YST 16 | F | Planning | Paint Drums | 3 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Confirmed |  | Clear | 13 | FALSE | 95 |  | 2 | No |  | No Conflict | Yes
BK-0913 | 2026-09-02 | 2026-09-09 |  | 7 | Crane | Level Luffing Crane | LLC 20 | 50 | 30.8 | YST D2 | E | Outfitting | Mooring Winch | 5 Days | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Medium | Pending |  | Partly Cloudy | 8 | FALSE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0914 | 2026-09-22 | 2026-09-28 |  | 6 | Crane | Workshop Crane | WOR-02 | 20 | 5.3 | YST 02 | A | Testing | Helideck Module | Full Day | Day Shift (0700-1900) | Team Gamma | Basic Crane Operator | Medium | Completed |  | Heavy Rain | 20 | FALSE | 93 | Early | 2 | No |  | No Conflict | Yes
BK-0915 | 2026-09-07 | 2026-09-18 |  | 11 | MEWP | Scissor Lift 10m | MEWP-25 |  |  | YST 01 | F | Planning | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Urgent | Cancelled | Budget constraint | Clear | 8 | FALSE | 32 |  | 4 | No |  | No Conflict | Yes
BK-0916 | 2026-09-02 | 2026-09-09 |  | 7 | Crane | Level Luffing Crane | LLC 03 | 300 | 80.8 | YST 15 | D | Planning | Mooring Winch | Full Day | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | High | Confirmed |  | Overcast | 6 | FALSE | 95 |  | 3 | No |  | No Conflict | Yes
BK-0917 | 2026-09-22 | 2026-10-04 |  | 12 | Forklift | Reach Forklift | FLT-04 | 3 | 1 | YST D5 | D | Planning | Welding Materials | Half Day (PM) | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Low | Confirmed |  | Clear | 7 | FALSE | 42 |  | 1 | No |  | No Conflict | Yes
BK-0918 | 2026-09-15 | 2026-09-18 |  | 3 | Crane | Workshop Crane | WOR-20 | 20 | 9.5 | YST 11 | C | Fabrication | Mega Block Section | 5 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | High | Completed |  | Partly Cloudy | 7 | FALSE | 91 | On Time | 3 | No |  | No Conflict | Yes
BK-0919 | 2026-09-17 | 2026-09-19 |  | 2 | Forklift | Telehandler Forklift | FLT-19 | 4 | 3.6 | YST 04 | C | Planning | Safety Equipment | Half Day (AM) | Day Shift (0700-1900) | Team Delta | Basic Operator | High | Confirmed |  | Overcast | 12 | FALSE | 58 |  | 3 | No |  | No Conflict | Yes
BK-0920 | 2026-09-13 | 2026-09-15 |  | 2 | Forklift | Heavy Duty Forklift | FLT-05 | 20 | 15.4 | YST 12 | F | Testing | Consumables Pallet | 5 Days | Night Shift (1900-0700) | Team Alpha | Forklift Operator | High | Completed |  | Overcast | 6 | FALSE | 92 | On Time | 3 | No |  | No Conflict | Yes
BK-0921 | 2026-09-04 | 2026-09-07 |  | 3 | MEWP | Boom Lift 20m | MEWP-07 |  |  | YST 09 | B | Fabrication | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Completed |  | Light Rain | 10 | FALSE | 96 | Delayed | 2 | No |  | No Conflict | Yes
BK-0922 | 2026-09-05 | 2026-09-06 |  | 1 | Forklift | Counterbalance Forklift | FLT-40 | 7 | 3.9 | YST 04 | E | Planning | Bolt Pallets | Full Day | Day Shift (0700-1900) | Team Delta | MEWP Operator | Medium | Confirmed |  | Partly Cloudy | 4 | FALSE | 41 |  | 2 | No |  | No Conflict | Yes
BK-0923 | 2026-09-14 | 2026-09-17 |  | 3 | Crane | Crawler Crane | CRA-09 | 50 | 17.5 | YST 06 | F | Commissioning | Pipe Spool | 10 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | High | Confirmed |  | Heavy Rain | 11 | FALSE | 79 |  | 3 | No |  | No Conflict | Yes
BK-0924 | 2026-09-12 | 2026-09-23 | 2026-09-27 | 11 | Crane | Mobile Crane | MOB-10 | 100 | 76.7 | YST 06 | C | Assembly | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | High | Rescheduled | Weather delay | Partly Cloudy | 7 | TRUE | 36 |  | 3 | No |  | No Conflict | Yes
BK-0925 | 2026-09-14 | 2026-09-15 |  | 1 | Crane | Level Luffing Crane | LLC 02 | 30 | 14.8 | YST D1 | A | Outfitting | Engine Module | Full Day | Night Shift (1900-0700) | Team Foxtrot | Advanced Crane Operator | High | Pending |  | Partly Cloudy | 4 | FALSE | 22 |  | 3 | No |  | No Conflict | Yes
BK-0926 | 2026-09-18 | 2026-09-19 |  | 1 | Crane | Workshop Crane | WOR-05 | 20 | 8.9 | YST D5 | D | Planning | Engine Module | 3 Days | Night Shift (1900-0700) | Team Alpha | Basic Crane Operator | Urgent | Cancelled | Client cancelled | Clear | 3 | FALSE | 49 |  | 4 | No |  | No Conflict | Yes
BK-0927 | 2026-09-23 | 2026-09-26 |  | 3 | Crane | Level Luffing Crane | LLC 09 | 50 | 20.5 | YST 12 | A | Planning | Transformer Unit | 3 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Cancelled | Duplicate booking | Overcast | 7 | FALSE | 48 |  | 2 | No |  | No Conflict | Yes
BK-0928 | 2026-09-14 | 2026-09-22 |  | 8 | MEWP | Telescopic Boom Lift 30m | MEWP-07 |  |  | YST 01 | B | Testing | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Beta | MEWP Operator | Urgent | Rejected | Location conflict with another operation | Partly Cloudy | 16 | FALSE | 47 |  | 4 | No |  | No Conflict | Yes
BK-0929 | 2026-09-27 | 2026-09-30 |  | 3 | Crane | Level Luffing Crane | LLC 05 | 300 | 172.8 | YST 08 | D | Outfitting | Flare Tower Section | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Low | Completed |  | Clear | 12 | FALSE | 44 | Delayed | 1 | No |  | No Conflict | Yes
BK-0930 | 2026-10-15 | 2026-10-22 | 2026-10-23 | 7 | Cometto | Cometto MSPE 8 Axle Lines | COM-01 |  |  | YST 05 | A | Commissioning | Engine Module | 5 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Rescheduled | Equipment breakdown | Overcast | 10 | TRUE | 65 |  | 2 | No |  | No Conflict | Yes
BK-0931 | 2026-10-11 | 2026-10-20 |  | 9 | Crane | Tower Crane | TOW-20 | 10 | 3.2 | YST D8 | D | Commissioning | Accommodation Module | 5 Days | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | High | Pending |  | Clear | 4 | FALSE | 63 |  | 3 | No |  | No Conflict | Yes
BK-0932 | 2026-10-04 | 2026-10-14 |  | 10 | Crane | Tower Crane | TOW-13 | 25 | 17.5 | YST 10 | D | Testing | Anchor Chain | 10 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Confirmed |  | Clear | 9 | FALSE | 67 |  | 2 | No |  | No Conflict | Yes
BK-0933 | 2026-10-06 | 2026-10-09 |  | 3 | Cometto | SPMT 16 Axle Lines | COM-02 |  |  | YST 17 | C | Fabrication | Jacket Structure | 14 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | Low | Rejected | Permit not approved | Heavy Rain | 14 | TRUE | 49 |  | 1 | No |  | No Conflict | Yes
BK-0934 | 2026-10-27 | 2026-11-07 |  | 11 | Forklift | Counterbalance Forklift | FLT-11 | 2.5 | 1.1 | YST 14 | A | Testing | Pipe Bundles | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | High | Cancelled | Budget constraint | High Wind | 27 | FALSE | 56 |  | 3 | No |  | No Conflict | Yes
BK-0935 | 2026-10-17 | 2026-10-24 |  | 7 | Forklift | Reach Forklift | FLT-29 | 2 | 1.8 | YST 04 | C | Commissioning | Safety Equipment | 10 Days | Night Shift (1900-0700) | Team Echo | MEWP Operator | Medium | Pending |  | Partly Cloudy | 4 | FALSE | 36 |  | 2 | No |  | No Conflict | Yes
BK-0936 | 2026-10-10 | 2026-10-17 |  | 7 | Crane | Level Luffing Crane | LLC 17 | 100 | 35.6 | YST 12 | A | Testing | Transformer Unit | 5 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Urgent | Completed |  | Clear | 2 | FALSE | 70 | On Time | 4 | No |  | No Conflict | Yes
BK-0937 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2 | Forklift | Heavy Duty Forklift | FLT-20 | 25 | 19.4 | YST 19 | E | Outfitting | Safety Equipment | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | High | Rescheduled | Material delivery delayed | Overcast | 10 | FALSE | 52 |  | 3 | No |  | No Conflict | Yes
BK-0938 | 2026-10-15 | 2026-10-23 |  | 8 | Crane | Workshop Crane | WOR-02 | 20 | 4.5 | YST 02 | E | Outfitting | Accommodation Module | 3 Days | Day Shift (0700-1900) | Team Alpha | Rigging Supervisor | Medium | Rejected | Weather conditions unsafe | Clear | 15 | TRUE | 38 |  | 2 | No |  | No Conflict | Yes
BK-0939 | 2026-10-22 | 2026-11-02 |  | 11 | Cometto | Cometto Eco500 12 Axle Lines | COM-06 |  |  | YST 13 | F | Commissioning | Offshore Platform Topside | Half Day (PM) | Night Shift (1900-0700) | Team Echo | Forklift Operator | High | Rejected | Safety inspection required first | Partly Cloudy | 11 | FALSE | 64 |  | 3 | No |  | No Conflict | Yes
BK-0940 | 2026-10-21 | 2026-10-25 |  | 4 | MEWP | Telescopic Boom Lift 30m | MEWP-24 |  |  | YST 08 | B | Planning | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Pending |  | Partly Cloudy | 6 | FALSE | 26 |  | 2 | No |  | No Conflict | Yes
BK-0941 | 2026-10-13 | 2026-10-16 | 2026-10-20 | 3 | Forklift | Telehandler Forklift | FLT-18 | 4 | 1.7 | YST D7 | B | Assembly | Scaffolding Materials | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Urgent | Rescheduled | Material delivery delayed | Partly Cloudy | 18 | TRUE | 36 |  | 4 | No |  | No Conflict | Yes
BK-0942 | 2026-10-16 | 2026-10-19 |  | 3 | Forklift | Reach Forklift | FLT-40 | 1.5 | 1.3 | YST 14 | E | Commissioning | Steel Plates | 5 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Rejected | Location conflict with another operation | Clear | 7 | TRUE | 33 |  | 2 | No |  | No Conflict | Yes
BK-0943 | 2026-10-16 | 2026-10-24 |  | 8 | Forklift | Telehandler Forklift | FLT-17 | 4 | 3 | YST 08 | A | Fabrication | Pipe Bundles | 2 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Rejected | Operator not available | Partly Cloudy | 10 | TRUE | 26 |  | 2 | No |  | No Conflict | Yes
BK-0944 | 2026-10-14 | 2026-10-18 |  | 4 | Crane | Goliath Gantry Crane | GC-20 | 300 | 186 | YST 04 | F | Planning | Hull Block Section | 2 Days | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | High | Completed |  | Light Rain | 6 | FALSE | 76 | Delayed | 3 | No |  | No Conflict | Yes
BK-0945 | 2026-10-21 | 2026-10-22 |  | 1 | MEWP | Scissor Lift 10m | MEWP-15 |  |  | YST D1 | E | Planning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Low | Completed |  | Light Rain | 12 | FALSE | 98 | On Time | 1 | No |  | No Conflict | Yes
BK-0946 | 2026-10-13 | 2026-10-25 |  | 12 | MEWP | Boom Lift 20m | MEWP-23 |  |  | YST D1 | A | Assembly | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Completed |  | Partly Cloudy | 10 | FALSE | 91 | Delayed | 2 | No |  | No Conflict | Yes
BK-0947 | 2026-10-04 | 2026-10-06 |  | 2 | Crane | Tower Crane | TOW-16 | 15 | 9.1 | YST 09 | A | Planning | Flare Tower Section | 14 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Urgent | Confirmed |  | Partly Cloudy | 15 | FALSE | 93 |  | 4 | No |  | No Conflict | Yes
BK-0948 | 2026-10-20 | 2026-10-27 |  | 7 | Forklift | Reach Forklift | FLT-16 | 2 | 1.2 | YST 14 | C | Assembly | Paint Drums | 2 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | Medium | Pending |  | Overcast | 14 | FALSE | 58 |  | 2 | No |  | No Conflict | Yes
BK-0949 | 2026-10-21 | 2026-10-29 |  | 8 | Crane | Goliath Gantry Crane | GC-15 | 300 | 137.6 | YST 19 | C | Commissioning | Construction Materials | Full Day | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Urgent | Cancelled | Duplicate booking | Heavy Rain | 23 | FALSE | 70 |  | 4 | No |  | No Conflict | Yes
BK-0950 | 2026-10-14 | 2026-10-18 |  | 4 | Crane | Crawler Crane | CRA-12 | 150 | 100.3 | YST 07 | C | Assembly | Flare Tower Section | 3 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Urgent | Pending |  | High Wind | 31 | FALSE | 21 |  | 4 | No |  | No Conflict | Yes
BK-0951 | 2026-10-14 | 2026-10-17 |  | 3 | Forklift | Telehandler Forklift | FLT-25 | 5 | 3.3 | YST D6 | C | Planning | Consumables Pallet | 5 Days | Night Shift (1900-0700) | Team Beta | Advanced Operator | High | Completed |  | Clear | 12 | FALSE | 43 | On Time | 3 | No |  | No Conflict | Yes
BK-0952 | 2026-10-30 | 2026-11-07 | 2026-11-08 | 8 | Crane | Goliath Gantry Crane | GC-15 | 200 | 56.1 | YST 01 | F | Commissioning | Structural Steel Module | Full Day | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | Medium | Rescheduled | Weather delay | Partly Cloudy | 14 | FALSE | 26 |  | 2 | No |  | No Conflict | Yes
BK-0953 | 2026-10-06 | 2026-10-10 | 2026-10-12 | 4 | Forklift | Counterbalance Forklift | FLT-35 | 5 | 4.4 | YST D8 | E | Planning | Gasket Boxes | 5 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Low | Rescheduled | Safety stand-down | Clear | 18 | FALSE | 28 |  | 1 | No |  | No Conflict | Yes
BK-0954 | 2026-10-28 | 2026-10-30 | 2026-11-01 | 2 | MEWP | Articulating Boom Lift 26m | MEWP-30 |  |  | YST D3 | D | Assembly | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Rescheduled | Weather delay | Heavy Rain | 23 | FALSE | 23 |  | 2 | No |  | No Conflict | Yes
BK-0955 | 2026-10-17 | 2026-10-21 |  | 4 | Cometto | SPMT 24 Axle Lines | COM-07 |  |  | YST 13 | D | Testing | Hull Block Section | 2 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Urgent | Pending |  | Partly Cloudy | 7 | FALSE | 36 |  | 4 | No |  | No Conflict | Yes
BK-0956 | 2026-10-31 | 2026-11-06 |  | 6 | Crane | Level Luffing Crane | LLC 11 | 300 | 111.3 | YST 08 | D | Assembly | Transformer Unit | 7 Days | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | Low | Cancelled | Project postponed | Partly Cloudy | 13 | FALSE | 32 |  | 1 | No |  | No Conflict | Yes
BK-0957 | 2026-10-28 | 2026-11-08 |  | 11 | Crane | Goliath Gantry Crane | GC-15 | 240 | 112.9 | YST 19 | E | Commissioning | Mooring Winch | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Lifting Supervisor | High | Completed |  | Light Rain | 4 | FALSE | 65 | Delayed | 3 | Yes | BK-1105 | First-Come-First-Served | Yes
BK-0958 | 2026-10-08 | 2026-10-16 |  | 8 | MEWP | Boom Lift 20m | MEWP-06 |  |  | YST D4 | A | Outfitting | Personnel Access Work | Half Day (AM) | Night Shift (1900-0700) | Team Echo | Forklift Operator | Medium | Cancelled | Client cancelled | Partly Cloudy | 2 | FALSE | 24 |  | 2 | No |  | No Conflict | Yes
BK-0959 | 2026-10-20 | 2026-10-29 |  | 9 | Forklift | Counterbalance Forklift | FLT-03 | 5 | 2.5 | YST 11 | B | Assembly | Tool Containers | 2 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | Medium | Pending |  | Overcast | 9 | FALSE | 39 |  | 2 | No |  | No Conflict | Yes
BK-0960 | 2026-10-01 | 2026-10-02 |  | 1 | Forklift | Counterbalance Forklift | FLT-29 | 2.5 | 1.1 | YST D3 | B | Assembly | Consumables Pallet | 3 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | High | Completed |  | Clear | 13 | FALSE | 92 | Delayed | 3 | No |  | No Conflict | Yes
BK-0961 | 2026-10-27 | 2026-11-03 |  | 7 | Crane | Level Luffing Crane | LLC 07 | 100 | 28.8 | YST D4 | F | Commissioning | Construction Materials | 2 Days | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | Low | Cancelled | Budget constraint | Partly Cloudy | 5 | FALSE | 52 |  | 1 | No |  | No Conflict | Yes
BK-0962 | 2026-10-22 | 2026-10-26 |  | 4 | MEWP | Telescopic Boom Lift 30m | MEWP-19 |  |  | YST D2 | C | Outfitting | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | High | Completed |  | Overcast | 6 | FALSE | 46 | On Time | 3 | No |  | No Conflict | Yes
BK-0963 | 2026-10-15 | 2026-10-23 |  | 8 | Crane | Goliath Gantry Crane | GC-20 | 200 | 59.5 | YST 01 | B | Testing | Flare Tower Section | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Heavy Lift Specialist | Medium | Completed |  | Overcast | 16 | FALSE | 76 | Delayed | 2 | No |  | No Conflict | Yes
BK-0964 | 2026-10-05 | 2026-10-18 |  | 13 | Forklift | Reach Forklift | FLT-37 | 1.5 | 0.5 | YST 13 | E | Fabrication | PPE Supplies | Full Day | Day Shift (0700-1900) | Team Echo | Basic Operator | Urgent | Cancelled | Project postponed | Clear | 5 | FALSE | 34 |  | 4 | No |  | No Conflict | Yes
BK-0965 | 2026-10-06 | 2026-10-17 |  | 11 | Crane | Workshop Crane | WOR-13 | 20 | 5.5 | YST D5 | E | Commissioning | Anchor Chain | Half Day (PM) | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | High | Pending |  | Partly Cloudy | 14 | FALSE | 38 |  | 3 | No |  | No Conflict | Yes
BK-0966 | 2026-10-07 | 2026-10-12 |  | 5 | Forklift | Telehandler Forklift | FLT-36 | 3 | 1.7 | YST D4 | E | Planning | Valve Crates | Full Day | Day Shift (0700-1900) | Team Beta | Forklift Operator | High | Confirmed |  | Light Rain | 10 | FALSE | 94 |  | 3 | No |  | No Conflict | Yes
BK-0967 | 2026-10-18 | 2026-10-25 |  | 7 | Crane | Crawler Crane | CRA-04 | 250 | 191.5 | YST D2 | B | Planning | Pipe Spool | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | Medium | Rejected | Safety inspection required first | Partly Cloudy | 10 | FALSE | 24 |  | 2 | No |  | No Conflict | Yes
BK-0968 | 2026-10-11 | 2026-10-12 |  | 1 | Cometto | SPMT 24 Axle Lines | COM-07 |  |  | YST 14 | A | Commissioning | Offshore Platform Topside | Full Day | Day Shift (0700-1900) | Team Foxtrot | MEWP Operator | Medium | Completed |  | Clear | 9 | FALSE | 40 | Delayed | 2 | No |  | No Conflict | Yes
BK-0969 | 2026-10-18 | 2026-10-22 |  | 4 | Crane | Tower Crane | TOW-02 | 25 | 10.7 | YST D8 | E | Fabrication | Mooring Winch | 3 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | High | Completed |  | Clear | 6 | FALSE | 76 | Delayed | 3 | No |  | No Conflict | Yes
BK-0970 | 2026-10-06 | 2026-10-11 |  | 5 | MEWP | Scissor Lift 10m | MEWP-18 |  |  | YST 08 | F | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | High | Completed |  | Overcast | 4 | FALSE | 63 | Delayed | 3 | No |  | No Conflict | Yes
BK-0971 | 2026-10-14 | 2026-10-17 | 2026-10-21 | 3 | MEWP | Scissor Lift 10m | MEWP-29 |  |  | YST D3 | B | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Beta | Advanced Operator | Medium | Rescheduled | Client request | Heavy Rain | 21 | FALSE | 31 |  | 2 | No |  | No Conflict | Yes
BK-0972 | 2026-10-01 | 2026-10-05 |  | 4 | Crane | Level Luffing Crane | LLC 05 | 300 | 187.1 | YST 12 | A | Outfitting | Riser Assembly | 10 Days | Night Shift (1900-0700) | Team Gamma | Rigging Supervisor | Medium | Completed |  | Partly Cloudy | 11 | FALSE | 48 | On Time | 2 | No |  | No Conflict | Yes
BK-0973 | 2026-10-13 | 2026-10-20 |  | 7 | Forklift | Counterbalance Forklift | FLT-39 | 3 | 1.8 | YST 09 | B | Testing | Safety Equipment | 5 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | Medium | Confirmed |  | High Wind | 35 | FALSE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0974 | 2026-10-26 | 2026-11-03 |  | 8 | Forklift | Telehandler Forklift | FLT-07 | 5 | 1.9 | YST 09 | A | Assembly | Welding Materials | 5 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Rejected | Insufficient lead time | Partly Cloudy | 18 | TRUE | 43 |  | 2 | No |  | No Conflict | Yes
BK-0975 | 2026-10-16 | 2026-10-26 |  | 10 | Cometto | Cometto MSPE 8 Axle Lines | COM-02 |  |  | YST 19 | A | Outfitting | Engine Module | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Urgent | Completed |  | Clear | 6 | FALSE | 95 | On Time | 4 | No |  | No Conflict | Yes
BK-0976 | 2026-10-06 | 2026-10-12 |  | 6 | Forklift | Telehandler Forklift | FLT-06 | 5 | 4.5 | YST 01 | F | Outfitting | Pipe Bundles | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Medium | Cancelled | Budget constraint | Clear | 6 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-0977 | 2026-10-25 | 2026-10-30 |  | 5 | MEWP | Scissor Lift 10m | MEWP-18 |  |  | YST 12 | A | Testing | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Low | Pending |  | Clear | 16 | FALSE | 26 |  | 1 | No |  | No Conflict | Yes
BK-0978 | 2026-10-27 | 2026-11-04 |  | 8 | Crane | Mobile Crane | MOB-12 | 25 | 17.1 | YST 01 | B | Planning | Turret Assembly | Full Day | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | Low | Pending |  | Clear | 4 | FALSE | 63 |  | 1 | No |  | No Conflict | Yes
BK-0979 | 2026-10-01 | 2026-10-02 |  | 1 | MEWP | Scissor Lift 10m | MEWP-18 |  |  | YST 10 | E | Testing | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Beta | MEWP Operator | High | Confirmed |  | Partly Cloudy | 8 | FALSE | 66 |  | 3 | No |  | No Conflict | Yes
BK-0980 | 2026-10-12 | 2026-10-15 | 2026-10-16 | 3 | Crane | Mobile Crane | MOB-03 | 25 | 8.2 | YST 07 | B | Assembly | Flare Tower Section | 10 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | Urgent | Rescheduled | Weather delay | Light Rain | 4 | TRUE | 41 |  | 4 | No |  | No Conflict | Yes
BK-0981 | 2026-10-05 | 2026-10-10 | 2026-10-14 | 5 | MEWP | Telescopic Boom Lift 30m | MEWP-22 |  |  | YST 08 | F | Assembly | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Rescheduled | Operator reassigned | Partly Cloudy | 18 | FALSE | 29 |  | 2 | No |  | No Conflict | Yes
BK-0982 | 2026-10-17 | 2026-10-19 | 2026-10-26 | 2 | Forklift | Reach Forklift | FLT-29 | 1.5 | 1.3 | YST D4 | E | Testing | Scaffolding Materials | Full Day | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Urgent | Rescheduled | Operator reassigned | Clear | 11 | FALSE | 60 |  | 4 | No |  | No Conflict | Yes
BK-0983 | 2026-10-10 | 2026-10-15 |  | 5 | Crane | Level Luffing Crane | LLC 15 | 50 | 38.8 | YST 11 | E | Assembly | Hull Block Section | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Crane Operator | Low | Completed |  | Partly Cloudy | 13 | FALSE | 76 | On Time | 1 | No |  | No Conflict | Yes
BK-0984 | 2026-10-27 | 2026-10-28 |  | 1 | Crane | Crawler Crane | CRA-16 | 150 | 71.6 | YST 02 | B | Planning | Hull Block Section | 3 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | High | Cancelled | Material not ready | High Wind | 28 | FALSE | 26 |  | 3 | No |  | No Conflict | Yes
BK-0985 | 2026-10-20 | 2026-11-03 |  | 14 | Crane | Crawler Crane | CRA-13 | 150 | 103.6 | YST D4 | E | Assembly | Mooring Winch | Half Day (AM) | Night Shift (1900-0700) | Team Beta | Lifting Supervisor | High | Completed |  | Thunderstorm | 30 | FALSE | 84 | Early | 3 | No |  | No Conflict | Yes
BK-0986 | 2026-10-22 | 2026-10-25 |  | 3 | Crane | Level Luffing Crane | LLC 11 | 40 | 9.9 | YST 06 | B | Outfitting | Mooring Winch | 5 Days | Night Shift (1900-0700) | Team Gamma | Basic Crane Operator | Urgent | Confirmed |  | Light Rain | 3 | FALSE | 53 |  | 4 | No |  | No Conflict | Yes
BK-0987 | 2026-10-28 | 2026-11-05 |  | 8 | Crane | Crawler Crane | CRA-20 | 150 | 71.7 | YST 08 | D | Commissioning | Workshop Equipment | 2 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Urgent | Completed |  | Clear | 6 | FALSE | 62 | Delayed | 4 | No |  | No Conflict | Yes
BK-0988 | 2026-10-19 | 2026-10-27 | 2026-10-29 | 8 | MEWP | Boom Lift 20m | MEWP-02 |  |  | YST 03 | F | Planning | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Rescheduled | Equipment breakdown | Clear | 5 | TRUE | 22 |  | 3 | No |  | No Conflict | Yes
BK-0989 | 2026-10-14 | 2026-10-15 | 2026-10-17 | 1 | MEWP | Articulating Boom Lift 26m | MEWP-03 |  |  | YST 03 | C | Testing | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Urgent | Rescheduled | Equipment breakdown | Overcast | 7 | FALSE | 68 |  | 4 | No |  | No Conflict | Yes
BK-0990 | 2026-10-30 | 2026-11-04 |  | 5 | MEWP | Boom Lift 20m | MEWP-12 |  |  | YST 02 | E | Planning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Urgent | Pending |  | Overcast | 14 | FALSE | 55 |  | 4 | No |  | No Conflict | Yes
BK-0991 | 2026-10-02 | 2026-10-04 |  | 2 | Crane | Mobile Crane | MOB-08 | 100 | 38.4 | YST 05 | B | Commissioning | Hull Block Section | 14 Days | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | High | Cancelled | Duplicate booking | Clear | 11 | FALSE | 34 |  | 3 | No |  | No Conflict | Yes
BK-0992 | 2026-10-01 | 2026-10-02 |  | 1 | MEWP | Telescopic Boom Lift 30m | MEWP-11 |  |  | YST 06 | D | Fabrication | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Confirmed |  | High Wind | 35 | FALSE | 97 |  | 2 | No |  | No Conflict | Yes
BK-0993 | 2026-10-13 | 2026-10-16 |  | 3 | Crane | Tower Crane | TOW-02 | 25 | 6 | YST 12 | B | Assembly | Construction Materials | 3 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | High | Confirmed |  | Partly Cloudy | 5 | FALSE | 42 |  | 3 | No |  | No Conflict | Yes
BK-0994 | 2026-10-19 | 2026-10-20 |  | 1 | Forklift | Reach Forklift | FLT-01 | 1.5 | 0.5 | YST 12 | B | Planning | Valve Crates | 3 Days | Night Shift (1900-0700) | Team Echo | Advanced Operator | Urgent | Pending |  | Clear | 5 | FALSE | 34 |  | 4 | No |  | No Conflict | Yes
BK-0995 | 2026-10-26 | 2026-10-29 |  | 3 | Forklift | Telehandler Forklift | FLT-37 | 5 | 2.4 | YST 15 | B | Planning | Paint Drums | 3 Days | Night Shift (1900-0700) | Team Delta | Advanced Operator | Medium | Pending |  | Clear | 15 | FALSE | 34 |  | 2 | No |  | No Conflict | Yes
BK-0996 | 2026-10-31 | 2026-11-10 | 2026-11-16 | 10 | Crane | Goliath Gantry Crane | GC-18 | 200 | 148.9 | YST 19 | A | Commissioning | Structural Steel Module | 2 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Medium | Rescheduled | Equipment breakdown | Overcast | 2 | FALSE | 34 |  | 2 | No |  | No Conflict | Yes
BK-0997 | 2026-10-25 | 2026-11-01 |  | 7 | Crane | Mobile Crane | MOB-20 | 50 | 31.7 | YST 02 | A | Testing | Workshop Equipment | 5 Days | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | Urgent | Pending |  | Overcast | 17 | FALSE | 56 |  | 4 | No |  | No Conflict | Yes
BK-0998 | 2026-10-04 | 2026-10-09 |  | 5 | Forklift | Reach Forklift | FLT-22 | 2 | 1.4 | YST 18 | D | Commissioning | Bolt Pallets | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Urgent | Pending |  | High Wind | 30 | FALSE | 55 |  | 4 | No |  | No Conflict | Yes
BK-0999 | 2026-10-17 | 2026-10-18 |  | 1 | Crane | Crawler Crane | CRA-20 | 100 | 39.9 | YST 08 | E | Outfitting | Transformer Unit | 7 Days | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | High | Confirmed |  | Heavy Rain | 18 | FALSE | 95 |  | 3 | No |  | No Conflict | Yes
BK-1000 | 2026-10-02 | 2026-10-10 |  | 8 | Forklift | Heavy Duty Forklift | FLT-11 | 15 | 5 | YST D4 | F | Fabrication | Small Fittings Pallet | Half Day (AM) | Day Shift (0700-1900) | Team Beta | Basic Operator | High | Pending |  | Clear | 6 | FALSE | 37 |  | 3 | No |  | No Conflict | Yes
BK-1001 | 2026-10-16 | 2026-10-30 |  | 14 | Cometto | Cometto Eco500 12 Axle Lines | COM-12 |  |  | YST 19 | F | Planning | Jacket Structure | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Basic Operator | High | Cancelled | Project postponed | Overcast | 2 | FALSE | 23 |  | 3 | No |  | No Conflict | Yes
BK-1002 | 2026-10-09 | 2026-10-21 |  | 12 | Cometto | Cometto Eco500 12 Axle Lines | COM-12 |  |  | YST 03 | C | Commissioning | Hull Block Section | 2 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | High | Confirmed |  | Clear | 6 | FALSE | 66 |  | 3 | No |  | No Conflict | Yes
BK-1003 | 2026-10-11 | 2026-10-22 |  | 11 | Crane | Mobile Crane | MOB-02 | 50 | 28.3 | YST 01 | D | Assembly | Workshop Equipment | 2 Days | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | Urgent | Completed |  | Partly Cloudy | 5 | FALSE | 89 | On Time | 4 | No |  | No Conflict | Yes
BK-1004 | 2026-10-01 | 2026-10-09 |  | 8 | Forklift | Counterbalance Forklift | FLT-31 | 7 | 3.2 | YST D2 | F | Testing | Safety Equipment | Full Day | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Urgent | Confirmed |  | Clear | 2 | FALSE | 87 |  | 4 | No |  | No Conflict | Yes
BK-1005 | 2026-10-18 | 2026-10-28 |  | 10 | Crane | Mobile Crane | MOB-19 | 100 | 78.1 | YST 03 | A | Assembly | Structural Steel Module | Half Day (PM) | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | Medium | Confirmed |  | Partly Cloudy | 13 | FALSE | 98 |  | 2 | No |  | No Conflict | Yes
BK-1006 | 2026-10-13 | 2026-10-19 |  | 6 | Forklift | Counterbalance Forklift | FLT-10 | 7 | 3.4 | YST 08 | E | Assembly | Consumables Pallet | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Basic Operator | Medium | Confirmed |  | Light Rain | 10 | FALSE | 67 |  | 2 | No |  | No Conflict | Yes
BK-1007 | 2026-10-13 | 2026-10-26 |  | 13 | Cometto | Cometto Eco500 12 Axle Lines | COM-10 |  |  | YST 19 | B | Fabrication | Hull Block Section | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | High | Confirmed |  | Light Rain | 14 | FALSE | 96 |  | 3 | No |  | No Conflict | Yes
BK-1008 | 2026-10-27 | 2026-10-29 |  | 2 | Crane | Goliath Gantry Crane | GC-17 | 300 | 78.3 | YST 01 | F | Assembly | Helideck Module | 5 Days | Night Shift (1900-0700) | Team Foxtrot | Heavy Lift Specialist | Medium | Cancelled | Budget constraint | Clear | 6 | FALSE | 60 |  | 2 | No |  | No Conflict | Yes
BK-1009 | 2026-10-29 | 2026-11-11 |  | 13 | MEWP | Telescopic Boom Lift 30m | MEWP-24 |  |  | YST 04 | F | Planning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Completed |  | Overcast | 14 | FALSE | 52 | Delayed | 2 | No |  | No Conflict | Yes
BK-1010 | 2026-10-26 | 2026-10-29 |  | 3 | Crane | Crawler Crane | CRA-12 | 250 | 61.6 | YST 03 | B | Planning | Riser Assembly | 5 Days | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Completed |  | Light Rain | 9 | FALSE | 63 | Delayed | 2 | No |  | No Conflict | Yes
BK-1011 | 2026-10-17 | 2026-10-23 |  | 6 | Crane | Workshop Crane | WOR-15 | 20 | 12.7 | YST 15 | C | Outfitting | Flare Tower Section | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Lifting Supervisor | High | Completed |  | Partly Cloudy | 10 | FALSE | 98 | Delayed | 3 | No |  | No Conflict | Yes
BK-1012 | 2026-10-31 | 2026-11-03 |  | 3 | Forklift | Reach Forklift | FLT-18 | 2.5 | 0.9 | YST 19 | A | Outfitting | Small Fittings Pallet | 2 Days | Night Shift (1900-0700) | Team Echo | Basic Operator | High | Completed |  | Clear | 10 | FALSE | 58 | On Time | 3 | No |  | No Conflict | Yes
BK-1013 | 2026-10-18 | 2026-10-26 | 2026-10-28 | 8 | Crane | Crawler Crane | CRA-11 | 150 | 46.4 | YST D1 | E | Outfitting | Engine Module | Full Day | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Rescheduled | Operator reassigned | Partly Cloudy | 16 | TRUE | 37 |  | 2 | No |  | No Conflict | Yes
BK-1014 | 2026-10-08 | 2026-10-13 | 2026-10-16 | 5 | Cometto | Cometto MSPE 8 Axle Lines | COM-07 |  |  | YST 05 | F | Testing | Hull Block Section | Half Day (PM) | Night Shift (1900-0700) | Team Alpha | Forklift Operator | Urgent | Rescheduled | Project timeline shifted | Overcast | 9 | FALSE | 27 |  | 4 | No |  | No Conflict | Yes
BK-1015 | 2026-10-25 | 2026-10-29 | 2026-10-30 | 4 | Crane | Workshop Crane | WOR-14 | 10 | 5 | YST D5 | A | Planning | Construction Materials | Full Day | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | Medium | Rescheduled | Equipment breakdown | Partly Cloudy | 5 | FALSE | 29 |  | 2 | No |  | No Conflict | Yes
BK-1016 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 5 | MEWP | Scissor Lift 10m | MEWP-11 |  |  | YST 09 | D | Testing | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Basic Operator | Medium | Rescheduled | Safety stand-down | Light Rain | 10 | TRUE | 51 |  | 2 | No |  | No Conflict | Yes
BK-1017 | 2026-10-21 | 2026-11-03 |  | 13 | Forklift | Counterbalance Forklift | FLT-10 | 7 | 4.1 | YST D6 | F | Assembly | Paint Drums | Full Day | Day Shift (0700-1900) | Team Delta | Basic Operator | Medium | Completed |  | Partly Cloudy | 8 | FALSE | 98 | On Time | 2 | No |  | No Conflict | Yes
BK-1018 | 2026-10-27 | 2026-10-28 |  | 1 | Forklift | Telehandler Forklift | FLT-35 | 4 | 2.4 | YST D7 | A | Planning | Timber Dunnage | Half Day (AM) | Night Shift (1900-0700) | Team Gamma | Forklift Operator | Medium | Pending |  | Clear | 6 | FALSE | 66 |  | 2 | No |  | No Conflict | Yes
BK-1019 | 2026-10-05 | 2026-10-07 |  | 2 | Crane | Mobile Crane | MOB-01 | 50 | 24.8 | YST 02 | B | Outfitting | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | High | Confirmed |  | Partly Cloudy | 4 | FALSE | 42 |  | 3 | No |  | No Conflict | Yes
BK-1020 | 2026-10-07 | 2026-10-09 |  | 2 | Crane | Crawler Crane | CRA-17 | 150 | 100.6 | YST D4 | E | Commissioning | Structural Steel Module | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Low | Cancelled | Duplicate booking | Overcast | 17 | FALSE | 59 |  | 1 | No |  | No Conflict | Yes
BK-1021 | 2026-10-12 | 2026-10-22 |  | 10 | Forklift | Heavy Duty Forklift | FLT-10 | 15 | 7.1 | YST 05 | E | Testing | PPE Supplies | 3 Days | Night Shift (1900-0700) | Team Delta | MEWP Operator | Medium | Cancelled | Project postponed | Overcast | 2 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-1022 | 2026-10-12 | 2026-10-15 |  | 3 | Crane | Mobile Crane | MOB-02 | 25 | 16.8 | YST D1 | E | Fabrication | Pipe Spool | 3 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | High | Completed |  | Partly Cloudy | 17 | FALSE | 72 | Delayed | 3 | No |  | No Conflict | Yes
BK-1023 | 2026-10-27 | 2026-11-06 | 2026-11-10 | 10 | Crane | Level Luffing Crane | LLC 05 | 30 | 18.7 | YST 17 | F | Testing | Engine Module | 2 Days | Day Shift (0700-1900) | Team Echo | Lifting Supervisor | Medium | Rescheduled | Safety stand-down | Overcast | 7 | FALSE | 60 |  | 2 | No |  | No Conflict | Yes
BK-1024 | 2026-10-30 | 2026-11-07 | 2026-11-14 | 8 | Crane | Crawler Crane | CRA-11 | 250 | 192.8 | YST 08 | B | Commissioning | Mega Block Section | 2 Days | Day Shift (0700-1900) | Team Beta | Lifting Supervisor | Medium | Rescheduled | Client request | High Wind | 29 | TRUE | 26 |  | 2 | No |  | No Conflict | Yes
BK-1025 | 2026-10-20 | 2026-10-24 |  | 4 | Forklift | Telehandler Forklift | FLT-12 | 4 | 3.4 | YST D3 | E | Assembly | PPE Supplies | 5 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Rejected | Permit not approved | Clear | 3 | FALSE | 35 |  | 2 | No |  | No Conflict | Yes
BK-1026 | 2026-10-03 | 2026-10-13 |  | 10 | Crane | Level Luffing Crane | LLC 16 | 50 | 14.5 | YST 13 | E | Assembly | Workshop Equipment | Full Day | Night Shift (1900-0700) | Team Alpha | Rigging Supervisor | Medium | Completed |  | Light Rain | 12 | FALSE | 44 | On Time | 2 | No |  | No Conflict | Yes
BK-1027 | 2026-10-13 | 2026-10-16 |  | 3 | Cometto | SPMT 16 Axle Lines | COM-04 |  |  | YST 18 | F | Assembly | Offshore Platform Topside | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Operator | Medium | Confirmed |  | Light Rain | 3 | FALSE | 56 |  | 2 | No |  | No Conflict | Yes
BK-1028 | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2 | Crane | Workshop Crane | WOR-14 | 10 | 5.4 | YST 15 | C | Assembly | Engine Module | 10 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | High | Rescheduled | Permit delay | Partly Cloudy | 2 | FALSE | 57 |  | 3 | No |  | No Conflict | Yes
BK-1029 | 2026-10-19 | 2026-10-23 |  | 4 | MEWP | Articulating Boom Lift 26m | MEWP-02 |  |  | YST 06 | B | Commissioning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | Low | Confirmed |  | Clear | 17 | FALSE | 86 |  | 1 | No |  | No Conflict | Yes
BK-1030 | 2026-10-22 | 2026-10-24 |  | 2 | Crane | Goliath Gantry Crane | GC-17 | 600 | 290.8 | YST 01 | D | Planning | Helideck Module | 7 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Cancelled | Material not ready | Overcast | 18 | FALSE | 51 |  | 2 | No |  | No Conflict | Yes
BK-1031 | 2026-11-08 | 2026-11-10 |  | 2 | MEWP | Boom Lift 20m | MEWP-15 |  |  | YST 05 | E | Testing | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Completed |  | Partly Cloudy | 17 | FALSE | 66 | On Time | 2 | No |  | No Conflict | Yes
BK-1032 | 2026-11-27 | 2026-12-04 |  | 7 | Crane | Workshop Crane | WOR-20 | 20 | 6.2 | YST 10 | E | Commissioning | Engine Module | Half Day (PM) | Night Shift (1900-0700) | Team Gamma | Basic Crane Operator | Medium | Confirmed |  | Overcast | 12 | FALSE | 42 |  | 2 | No |  | No Conflict | Yes
BK-1033 | 2026-11-06 | 2026-11-08 | 2026-11-13 | 2 | Crane | Level Luffing Crane | LLC 13 | 50 | 14.2 | YST 17 | D | Planning | Helideck Module | Full Day | Day Shift (0700-1900) | Team Foxtrot | Lifting Supervisor | Medium | Rescheduled | Safety stand-down | Overcast | 2 | FALSE | 39 |  | 2 | No |  | No Conflict | Yes
BK-1034 | 2026-11-22 | 2026-12-01 |  | 9 | MEWP | Articulating Boom Lift 26m | MEWP-19 |  |  | YST D3 | C | Outfitting | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Completed |  | Overcast | 3 | FALSE | 61 | On Time | 2 | No |  | No Conflict | Yes
BK-1035 | 2026-11-14 | 2026-11-17 |  | 3 | Crane | Goliath Gantry Crane | GC-20 | 400 | 113 | YST 01 | D | Outfitting | Hull Block Section | 5 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | Medium | Confirmed |  | Clear | 13 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-1036 | 2026-11-11 | 2026-11-14 |  | 3 | Cometto | SPMT 24 Axle Lines | COM-03 |  |  | YST 19 | B | Outfitting | Engine Module | 2 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | Medium | Completed |  | Clear | 4 | FALSE | 79 | On Time | 2 | Yes | BK-1140 | Yielded to Higher Priority | No
BK-1037 | 2026-11-17 | 2026-11-24 | 2026-11-29 | 7 | MEWP | Articulating Boom Lift 26m | MEWP-12 |  |  | YST D1 | C | Assembly | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Rescheduled | Weather delay | Overcast | 11 | FALSE | 39 |  | 2 | Yes | BK-1089 | Later Request - Reassigned | No
BK-1038 | 2026-11-04 | 2026-11-09 | 2026-11-14 | 5 | Forklift | Heavy Duty Forklift | FLT-18 | 15 | 5.8 | YST D7 | C | Planning | Gasket Boxes | 3 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Urgent | Rescheduled | Equipment breakdown | Partly Cloudy | 7 | FALSE | 28 |  | 4 | No |  | No Conflict | Yes
BK-1039 | 2026-11-24 | 2026-11-30 |  | 6 | Forklift | Telehandler Forklift | FLT-07 | 3 | 1.8 | YST 08 | B | Planning | PPE Supplies | 10 Days | Night Shift (1900-0700) | Team Echo | Advanced Operator | Medium | Confirmed |  | Heavy Rain | 11 | FALSE | 94 |  | 2 | No |  | No Conflict | Yes
BK-1040 | 2026-11-17 | 2026-11-21 |  | 4 | Crane | Workshop Crane | WOR-16 | 20 | 8.6 | YST 15 | C | Assembly | Pipe Spool | 5 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Low | Confirmed |  | Overcast | 11 | FALSE | 86 |  | 1 | Yes | BK-1065 | Yielded to Higher Priority | No
BK-1041 | 2026-11-20 | 2026-11-23 |  | 3 | Crane | Level Luffing Crane | LLC 05 | 40 | 12.6 | YST 12 | C | Testing | Engine Module | 5 Days | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | Medium | Completed |  | Overcast | 14 | FALSE | 80 | Delayed | 2 | No |  | No Conflict | Yes
BK-1042 | 2026-11-16 | 2026-11-29 |  | 13 | MEWP | Telescopic Boom Lift 30m | MEWP-30 |  |  | YST 03 | C | Fabrication | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Completed |  | Clear | 12 | FALSE | 54 | On Time | 2 | No |  | No Conflict | Yes
BK-1043 | 2026-11-08 | 2026-11-20 |  | 12 | MEWP | Scissor Lift 10m | MEWP-10 |  |  | YST 07 | B | Planning | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Cancelled | Duplicate booking | Heavy Rain | 16 | FALSE | 31 |  | 2 | No |  | No Conflict | Yes
BK-1044 | 2026-11-09 | 2026-11-14 |  | 5 | Cometto | Cometto MSPE 8 Axle Lines | COM-11 |  |  | YST 05 | F | Outfitting | Hull Block Section | 2 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Cancelled | Duplicate booking | Light Rain | 2 | FALSE | 65 |  | 3 | No |  | No Conflict | Yes
BK-1045 | 2026-11-23 | 2026-12-04 |  | 11 | MEWP | Articulating Boom Lift 26m | MEWP-25 |  |  | YST D1 | D | Outfitting | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Low | Cancelled | Project postponed | Heavy Rain | 12 | FALSE | 22 |  | 1 | No |  | No Conflict | Yes
BK-1046 | 2026-11-10 | 2026-11-13 |  | 3 | Crane | Goliath Gantry Crane | GC-16 | 240 | 153.1 | YST 19 | D | Assembly | Helideck Module | 10 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | High | Completed |  | Clear | 12 | FALSE | 88 | On Time | 3 | Yes | BK-1082 | Priority Override | Yes
BK-1047 | 2026-11-07 | 2026-11-10 | 2026-11-17 | 3 | Forklift | Heavy Duty Forklift | FLT-09 | 10 | 5.4 | YST 05 | B | Planning | Steel Plates | 2 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Rescheduled | Weather delay | Clear | 10 | FALSE | 47 |  | 2 | No |  | No Conflict | Yes
BK-1048 | 2026-11-15 | 2026-11-20 |  | 5 | Forklift | Reach Forklift | FLT-40 | 3 | 1 | YST 05 | B | Assembly | Small Fittings Pallet | 3 Days | Night Shift (1900-0700) | Team Gamma | MEWP Operator | Medium | Cancelled | Project postponed | Overcast | 8 | FALSE | 34 |  | 2 | No |  | No Conflict | Yes
BK-1049 | 2026-11-24 | 2026-12-01 |  | 7 | Forklift | Reach Forklift | FLT-14 | 2 | 1.6 | YST 08 | D | Planning | Steel Plates | Full Day | Night Shift (1900-0700) | Team Beta | Forklift Operator | Low | Pending |  | High Wind | 43 | FALSE | 69 |  | 1 | No |  | No Conflict | Yes
BK-1050 | 2026-11-01 | 2026-11-03 |  | 2 | Cometto | Cometto Eco500 12 Axle Lines | COM-05 |  |  | YST 18 | C | Commissioning | Hull Block Section | Half Day (AM) | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Cancelled | Client cancelled | Heavy Rain | 24 | FALSE | 50 |  | 3 | No |  | No Conflict | Yes
BK-1051 | 2026-11-21 | 2026-11-28 |  | 7 | MEWP | Articulating Boom Lift 26m | MEWP-04 |  |  | YST D2 | C | Commissioning | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | Urgent | Confirmed |  | Partly Cloudy | 16 | FALSE | 83 |  | 4 | No |  | No Conflict | Yes
BK-1052 | 2026-11-16 | 2026-11-23 |  | 7 | Crane | Level Luffing Crane | LLC 20 | 40 | 25.4 | YST 05 | E | Assembly | Pipe Spool | Half Day (AM) | Night Shift (1900-0700) | Team Foxtrot | Basic Crane Operator | Medium | Completed |  | Overcast | 18 | FALSE | 55 | On Time | 2 | No |  | No Conflict | Yes
BK-1053 | 2026-11-21 | 2026-11-24 |  | 3 | MEWP | Scissor Lift 10m | MEWP-04 |  |  | YST 06 | E | Planning | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Completed |  | Clear | 13 | FALSE | 69 | Early | 2 | No |  | No Conflict | Yes
BK-1054 | 2026-11-28 | 2026-12-08 |  | 10 | Crane | Level Luffing Crane | LLC 12 | 40 | 19.9 | YST D4 | E | Assembly | Structural Steel Module | Half Day (PM) | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | Medium | Completed |  | Overcast | 5 | FALSE | 49 | Early | 2 | No |  | No Conflict | Yes
BK-1055 | 2026-11-13 | 2026-11-22 |  | 9 | Crane | Tower Crane | TOW-01 | 40 | 22.2 | YST 12 | F | Assembly | Structural Steel Module | 2 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | Medium | Confirmed |  | Overcast | 10 | FALSE | 94 |  | 2 | No |  | No Conflict | Yes
BK-1056 | 2026-11-07 | 2026-11-18 | 2026-11-19 | 11 | Cometto | Cometto MSPE 8 Axle Lines | COM-04 |  |  | YST 19 | A | Assembly | Jacket Structure | Full Day | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Medium | Rescheduled | Permit delay | Partly Cloudy | 18 | FALSE | 41 |  | 2 | No |  | No Conflict | Yes
BK-1057 | 2026-11-09 | 2026-11-15 |  | 6 | Forklift | Counterbalance Forklift | FLT-33 | 5 | 2.7 | YST 20 | D | Assembly | Consumables Pallet | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Cancelled | Project postponed | Overcast | 7 | FALSE | 30 |  | 2 | No |  | No Conflict | Yes
BK-1058 | 2026-11-29 | 2026-12-06 |  | 7 | Crane | Goliath Gantry Crane | GC-18 | 300 | 122.9 | YST 01 | A | Outfitting | Mooring Winch | 3 Days | Night Shift (1900-0700) | Team Beta | Advanced Crane Operator | Urgent | Pending |  | Clear | 14 | FALSE | 58 |  | 4 | No |  | No Conflict | Yes
BK-1059 | 2026-11-05 | 2026-11-06 |  | 1 | Crane | Workshop Crane | WOR-10 | 10 | 3.4 | YST 08 | C | Assembly | Construction Materials | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Confirmed |  | Light Rain | 14 | FALSE | 82 |  | 2 | No |  | No Conflict | Yes
BK-1060 | 2026-11-24 | 2026-12-04 |  | 10 | MEWP | Boom Lift 20m | MEWP-22 |  |  | YST 10 | C | Testing | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | Medium | Completed |  | Partly Cloudy | 12 | FALSE | 53 | Delayed | 2 | No |  | No Conflict | Yes
BK-1061 | 2026-11-08 | 2026-11-16 |  | 8 | Forklift | Counterbalance Forklift | FLT-11 | 2.5 | 1.5 | YST 09 | B | Planning | Valve Crates | Half Day (AM) | Day Shift (0700-1900) | Team Beta | MEWP Operator | Urgent | Confirmed |  | Partly Cloudy | 11 | FALSE | 47 |  | 4 | No |  | No Conflict | Yes
BK-1062 | 2026-11-23 | 2026-11-28 |  | 5 | Crane | Mobile Crane | MOB-13 | 100 | 79.3 | YST D1 | E | Testing | Mooring Winch | Full Day | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Medium | Completed |  | Clear | 11 | FALSE | 93 | Delayed | 2 | No |  | No Conflict | Yes
BK-1063 | 2026-11-01 | 2026-11-02 |  | 1 | Crane | Tower Crane | TOW-17 | 40 | 26 | YST D3 | D | Commissioning | Workshop Equipment | 3 Days | Night Shift (1900-0700) | Team Echo | Rigging Supervisor | Medium | Cancelled | Client cancelled | Partly Cloudy | 14 | FALSE | 58 |  | 2 | No |  | No Conflict | Yes
BK-1064 | 2026-11-14 | 2026-11-22 |  | 8 | Crane | Workshop Crane | WOR-05 | 10 | 3.7 | YST 07 | A | Assembly | Construction Materials | 5 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | Medium | Confirmed |  | Overcast | 3 | FALSE | 74 |  | 2 | No |  | No Conflict | Yes
BK-1065 | 2026-11-07 | 2026-11-16 |  | 9 | Crane | Workshop Crane | WOR-16 | 20 | 5.2 | YST 07 | E | Assembly | Engine Module | 7 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | High | Pending |  | Overcast | 18 | FALSE | 64 |  | 3 | Yes | BK-1040 | Priority Override | Yes
BK-1066 | 2026-11-07 | 2026-11-09 |  | 2 | MEWP | Scissor Lift 10m | MEWP-29 |  |  | YST 08 | A | Planning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | High | Confirmed |  | Clear | 8 | FALSE | 74 |  | 3 | No |  | No Conflict | Yes
BK-1067 | 2026-11-11 | 2026-11-14 | 2026-11-16 | 3 | Crane | Level Luffing Crane | LLC 02 | 30 | 16 | YST 11 | E | Commissioning | Workshop Equipment | 2 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Urgent | Rescheduled | Material delivery delayed | Clear | 13 | FALSE | 59 |  | 4 | No |  | No Conflict | Yes
BK-1068 | 2026-11-22 | 2026-12-01 | 2026-12-03 | 9 | Forklift | Counterbalance Forklift | FLT-35 | 2.5 | 2.1 | YST 15 | B | Fabrication | Consumables Pallet | 5 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Rescheduled | Material delivery delayed | Light Rain | 8 | FALSE | 33 |  | 3 | No |  | No Conflict | Yes
BK-1069 | 2026-11-27 | 2026-12-03 |  | 6 | Forklift | Counterbalance Forklift | FLT-35 | 5 | 1.5 | YST D1 | B | Outfitting | Insulation Materials | 7 Days | Night Shift (1900-0700) | Team Delta | Basic Operator | Medium | Completed |  | Overcast | 5 | FALSE | 49 | Delayed | 2 | Yes | BK-1120 | First-Come-First-Served | Yes
BK-1070 | 2026-11-26 | 2026-11-29 |  | 3 | Forklift | Heavy Duty Forklift | FLT-23 | 10 | 5.4 | YST D2 | D | Assembly | Valve Crates | 7 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Confirmed |  | Overcast | 2 | FALSE | 71 |  | 3 | No |  | No Conflict | Yes
BK-1071 | 2026-11-13 | 2026-11-15 |  | 2 | Crane | Workshop Crane | WOR-18 | 20 | 5.4 | YST 09 | B | Outfitting | Hull Block Section | 3 Days | Night Shift (1900-0700) | Team Gamma | Lifting Supervisor | Medium | Confirmed |  | Overcast | 15 | FALSE | 84 |  | 2 | No |  | No Conflict | Yes
BK-1072 | 2026-11-04 | 2026-11-09 |  | 5 | MEWP | Boom Lift 20m | MEWP-12 |  |  | YST 10 | F | Fabrication | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Low | Cancelled | Material not ready | Overcast | 14 | FALSE | 54 |  | 1 | No |  | No Conflict | Yes
BK-1073 | 2026-11-13 | 2026-11-22 |  | 9 | MEWP | Articulating Boom Lift 26m | MEWP-05 |  |  | YST 04 | B | Assembly | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Pending |  | Partly Cloudy | 10 | FALSE | 60 |  | 2 | No |  | No Conflict | Yes
BK-1074 | 2026-11-21 | 2026-11-22 |  | 1 | Crane | Crawler Crane | CRA-20 | 100 | 23.8 | YST D2 | D | Testing | Flare Tower Section | Half Day (AM) | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Cancelled | Budget constraint | High Wind | 34 | FALSE | 45 |  | 2 | No |  | No Conflict | Yes
BK-1075 | 2026-11-16 | 2026-11-17 |  | 1 | Crane | Tower Crane | TOW-16 | 40 | 27.3 | YST 16 | C | Planning | Workshop Equipment | Full Day | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Urgent | Completed |  | High Wind | 31 | FALSE | 94 | On Time | 4 | No |  | No Conflict | Yes
BK-1076 | 2026-11-14 | 2026-11-20 |  | 6 | Crane | Mobile Crane | MOB-19 | 75 | 50.7 | YST 04 | A | Assembly | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Medium | Pending |  | Clear | 2 | FALSE | 60 |  | 2 | No |  | No Conflict | Yes
BK-1077 | 2026-11-17 | 2026-11-27 |  | 10 | Forklift | Telehandler Forklift | FLT-11 | 4 | 1.8 | YST 04 | E | Planning | Pipe Bundles | 2 Days | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Medium | Completed |  | Clear | 7 | FALSE | 62 | Delayed | 2 | No |  | No Conflict | Yes
BK-1078 | 2026-11-25 | 2026-11-28 |  | 3 | MEWP | Boom Lift 20m | MEWP-11 |  |  | YST 02 | F | Outfitting | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | High | Cancelled | Material not ready | Clear | 5 | FALSE | 35 |  | 3 | No |  | No Conflict | Yes
BK-1079 | 2026-11-01 | 2026-11-04 |  | 3 | Forklift | Telehandler Forklift | FLT-14 | 3 | 0.9 | YST 02 | E | Testing | Steel Plates | Half Day (AM) | Day Shift (0700-1900) | Team Delta | MEWP Operator | High | Completed |  | Partly Cloudy | 8 | FALSE | 62 | On Time | 3 | No |  | No Conflict | Yes
BK-1080 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 7 | Forklift | Heavy Duty Forklift | FLT-28 | 25 | 13.7 | YST 18 | F | Planning | Electrical Cables | 2 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Urgent | Rescheduled | Original date conflicts with maintenance | Partly Cloudy | 7 | TRUE | 60 |  | 4 | No |  | No Conflict | Yes
BK-1081 | 2026-11-07 | 2026-11-12 | 2026-11-14 | 5 | Forklift | Counterbalance Forklift | FLT-19 | 2.5 | 2.2 | YST 08 | D | Outfitting | Gasket Boxes | Full Day | Night Shift (1900-0700) | Team Beta | Forklift Operator | High | Rescheduled | Material delivery delayed | Clear | 12 | FALSE | 43 |  | 3 | No |  | No Conflict | Yes
BK-1082 | 2026-11-10 | 2026-11-22 | 2026-11-28 | 12 | Crane | Goliath Gantry Crane | GC-16 | 200 | 55 | YST 04 | B | Fabrication | Riser Assembly | 3 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Medium | Rescheduled | Operator reassigned | High Wind | 30 | TRUE | 60 |  | 2 | Yes | BK-1046 | Yielded to Higher Priority | No
BK-1083 | 2026-11-22 | 2026-11-26 |  | 4 | Forklift | Telehandler Forklift | FLT-25 | 7 | 4.3 | YST 10 | D | Assembly | Small Fittings Pallet | Full Day | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Medium | Completed |  | Clear | 9 | FALSE | 71 | Delayed | 2 | No |  | No Conflict | Yes
BK-1084 | 2026-11-05 | 2026-11-09 |  | 4 | Cometto | Cometto Eco500 12 Axle Lines | COM-12 |  |  | YST 02 | B | Commissioning | Hull Block Section | 5 Days | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Low | Completed |  | Clear | 4 | FALSE | 44 | Early | 1 | No |  | No Conflict | Yes
BK-1085 | 2026-11-25 | 2026-12-01 |  | 6 | Forklift | Heavy Duty Forklift | FLT-28 | 25 | 15.8 | YST 16 | E | Assembly | PPE Supplies | 5 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Cancelled | Budget constraint | Overcast | 12 | FALSE | 62 |  | 3 | No |  | No Conflict | Yes
BK-1086 | 2026-11-10 | 2026-11-13 |  | 3 | Forklift | Heavy Duty Forklift | FLT-08 | 20 | 10.4 | YST 04 | A | Assembly | Consumables Pallet | 10 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | High | Completed |  | Thunderstorm | 21 | FALSE | 56 | On Time | 3 | No |  | No Conflict | Yes
BK-1087 | 2026-11-10 | 2026-11-14 |  | 4 | Crane | Crawler Crane | CRA-05 | 100 | 62.1 | YST 06 | A | Outfitting | Helideck Module | Full Day | Night Shift (1900-0700) | Team Foxtrot | Lifting Supervisor | High | Cancelled | Material not ready | Clear | 11 | FALSE | 32 |  | 3 | No |  | No Conflict | Yes
BK-1088 | 2026-11-09 | 2026-11-13 |  | 4 | Forklift | Heavy Duty Forklift | FLT-32 | 10 | 8 | YST 11 | A | Planning | Valve Crates | 3 Days | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Completed |  | Overcast | 9 | FALSE | 78 | Early | 2 | No |  | No Conflict | Yes
BK-1089 | 2026-11-14 | 2026-11-26 |  | 12 | MEWP | Boom Lift 20m | MEWP-12 |  |  | YST 03 | E | Outfitting | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Completed |  | Clear | 4 | FALSE | 47 | On Time | 2 | Yes | BK-1037 | First-Come-First-Served | Yes
BK-1090 | 2026-11-10 | 2026-11-15 |  | 5 | Forklift | Heavy Duty Forklift | FLT-31 | 20 | 8.3 | YST D4 | A | Assembly | Valve Crates | 5 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Pending |  | Partly Cloudy | 17 | FALSE | 44 |  | 2 | No |  | No Conflict | Yes
BK-1091 | 2026-11-16 | 2026-11-18 |  | 2 | MEWP | Telescopic Boom Lift 30m | MEWP-19 |  |  | YST 06 | D | Fabrication | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Urgent | Completed |  | Overcast | 10 | FALSE | 80 | Delayed | 4 | No |  | No Conflict | Yes
BK-1092 | 2026-11-09 | 2026-11-22 |  | 13 | Crane | Tower Crane | TOW-02 | 10 | 2.6 | YST 09 | B | Commissioning | Engine Module | 3 Days | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | Medium | Confirmed |  | Overcast | 7 | FALSE | 78 |  | 2 | No |  | No Conflict | Yes
BK-1093 | 2026-11-14 | 2026-11-22 |  | 8 | Crane | Crawler Crane | CRA-13 | 100 | 46.3 | YST D3 | F | Testing | Accommodation Module | Full Day | Night Shift (1900-0700) | Team Echo | Heavy Lift Specialist | Medium | Rejected | Load exceeds crane capacity | Overcast | 13 | FALSE | 51 |  | 2 | No |  | No Conflict | Yes
BK-1094 | 2026-11-11 | 2026-11-18 |  | 7 | MEWP | Boom Lift 20m | MEWP-27 |  |  | YST 04 | F | Testing | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Pending |  | Overcast | 4 | FALSE | 39 |  | 2 | No |  | No Conflict | Yes
BK-1095 | 2026-11-17 | 2026-11-24 | 2026-12-01 | 7 | MEWP | Telescopic Boom Lift 30m | MEWP-15 |  |  | YST 03 | C | Assembly | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Rescheduled | Operator reassigned | Light Rain | 10 | FALSE | 68 |  | 2 | No |  | No Conflict | Yes
BK-1096 | 2026-11-06 | 2026-11-12 |  | 6 | Crane | Tower Crane | TOW-07 | 10 | 5.7 | YST 10 | E | Planning | Structural Steel Module | 3 Days | Day Shift (0700-1900) | Team Echo | Lifting Supervisor | Medium | Completed |  | Light Rain | 9 | FALSE | 93 | Delayed | 2 | No |  | No Conflict | Yes
BK-1097 | 2026-11-09 | 2026-11-21 |  | 12 | Crane | Level Luffing Crane | LLC 15A | 30 | 22.6 | YST D4 | C | Assembly | Workshop Equipment | 3 Days | Night Shift (1900-0700) | Team Alpha | Heavy Lift Specialist | Medium | Pending |  | Clear | 15 | FALSE | 34 |  | 2 | No |  | No Conflict | Yes
BK-1098 | 2026-11-27 | 2026-12-06 |  | 9 | Crane | Workshop Crane | WOR-15 | 20 | 5.5 | YST 01 | D | Planning | Helideck Module | 10 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Medium | Confirmed |  | Overcast | 5 | FALSE | 77 |  | 2 | No |  | No Conflict | Yes
BK-1099 | 2026-11-03 | 2026-11-04 |  | 1 | Forklift | Heavy Duty Forklift | FLT-21 | 25 | 20.3 | YST 10 | E | Assembly | Welding Materials | 2 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Low | Confirmed |  | Light Rain | 5 | FALSE | 42 |  | 1 | No |  | No Conflict | Yes
BK-1100 | 2026-11-10 | 2026-11-14 |  | 4 | Forklift | Telehandler Forklift | FLT-14 | 4 | 3.4 | YST D3 | B | Outfitting | Timber Dunnage | 2 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | High | Pending |  | Light Rain | 6 | FALSE | 64 |  | 3 | No |  | No Conflict | Yes
BK-1101 | 2026-11-12 | 2026-11-18 |  | 6 | MEWP | Boom Lift 20m | MEWP-12 |  |  | YST 07 | C | Outfitting | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Low | Completed |  | Clear | 11 | FALSE | 55 | On Time | 1 | No |  | No Conflict | Yes
BK-1102 | 2026-11-11 | 2026-11-22 |  | 11 | Forklift | Heavy Duty Forklift | FLT-23 | 25 | 20.1 | YST 19 | F | Testing | PPE Supplies | 2 Days | Night Shift (1900-0700) | Team Alpha | MEWP Operator | Medium | Completed |  | Clear | 6 | FALSE | 70 | On Time | 2 | No |  | No Conflict | Yes
BK-1103 | 2026-11-15 | 2026-11-16 |  | 1 | Crane | Tower Crane | TOW-01 | 40 | 9.8 | YST D2 | C | Assembly | Anchor Chain | 2 Days | Day Shift (0700-1900) | Team Beta | Rigging Supervisor | Medium | Completed |  | Clear | 15 | FALSE | 79 | Early | 2 | No |  | No Conflict | Yes
BK-1104 | 2026-11-15 | 2026-11-28 |  | 13 | Crane | Goliath Gantry Crane | GC-15 | 300 | 148.3 | YST 19 | F | Testing | Flare Tower Section | 2 Days | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | Urgent | Confirmed |  | Partly Cloudy | 6 | FALSE | 56 |  | 4 | No |  | No Conflict | Yes
BK-1105 | 2026-11-05 | 2026-11-11 |  | 6 | Crane | Goliath Gantry Crane | GC-15 | 600 | 327 | YST 01 | C | Fabrication | Accommodation Module | 5 Days | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | High | Completed |  | Thunderstorm | 33 | FALSE | 71 | On Time | 3 | Yes | BK-0957 | Later Request - Reassigned | No
BK-1106 | 2026-11-23 | 2026-12-02 |  | 9 | Forklift | Counterbalance Forklift | FLT-40 | 3 | 1.9 | YST 06 | F | Fabrication | Gasket Boxes | 3 Days | Night Shift (1900-0700) | Team Gamma | MEWP Operator | High | Completed |  | Light Rain | 12 | FALSE | 48 | Delayed | 3 | No |  | No Conflict | Yes
BK-1107 | 2026-11-04 | 2026-11-10 |  | 6 | Forklift | Counterbalance Forklift | FLT-07 | 7 | 4.6 | YST D6 | A | Fabrication | Insulation Materials | 5 Days | Night Shift (1900-0700) | Team Gamma | Forklift Operator | High | Rejected | Crane already booked | Partly Cloudy | 8 | FALSE | 33 |  | 3 | No |  | No Conflict | Yes
BK-1108 | 2026-11-18 | 2026-11-24 |  | 6 | Cometto | SPMT 16 Axle Lines | COM-12 |  |  | YST 16 | A | Fabrication | Hull Block Section | Full Day | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Rejected | Crane already booked | Overcast | 2 | FALSE | 42 |  | 2 | No |  | No Conflict | Yes
BK-1109 | 2026-11-07 | 2026-11-13 |  | 6 | MEWP | Telescopic Boom Lift 30m | MEWP-06 |  |  | YST 01 | A | Assembly | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Confirmed |  | Clear | 7 | FALSE | 54 |  | 2 | No |  | No Conflict | Yes
BK-1110 | 2026-11-29 | 2026-12-01 |  | 2 | Crane | Workshop Crane | WOR-05 | 20 | 5.2 | YST D5 | D | Commissioning | Mooring Winch | Half Day (AM) | Night Shift (1900-0700) | Team Alpha | Advanced Crane Operator | Low | Cancelled | Duplicate booking | Overcast | 10 | FALSE | 43 |  | 1 | No |  | No Conflict | Yes
BK-1111 | 2026-11-25 | 2026-11-28 | 2026-12-02 | 3 | MEWP | Scissor Lift 10m | MEWP-20 |  |  | YST 02 | B | Assembly | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | Urgent | Rescheduled | Client request | Partly Cloudy | 16 | FALSE | 67 |  | 4 | No |  | No Conflict | Yes
BK-1112 | 2026-11-09 | 2026-11-20 |  | 11 | MEWP | Boom Lift 20m | MEWP-06 |  |  | YST 06 | A | Assembly | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | High | Confirmed |  | Light Rain | 8 | FALSE | 46 |  | 3 | No |  | No Conflict | Yes
BK-1113 | 2026-11-04 | 2026-11-11 |  | 7 | MEWP | Scissor Lift 10m | MEWP-10 |  |  | YST 07 | A | Fabrication | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | Medium | Confirmed |  | Partly Cloudy | 16 | FALSE | 50 |  | 2 | No |  | No Conflict | Yes
BK-1114 | 2026-11-02 | 2026-11-14 |  | 12 | Crane | Level Luffing Crane | LLC 16A | 30 | 6.2 | YST D4 | C | Fabrication | Pipe Spool | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Confirmed |  | Partly Cloudy | 2 | FALSE | 78 |  | 3 | No |  | No Conflict | Yes
BK-1115 | 2026-11-11 | 2026-11-12 |  | 1 | Crane | Goliath Gantry Crane | GC-20 | 240 | 71.1 | YST 04 | B | Planning | Helideck Module | 10 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | Medium | Completed |  | Overcast | 7 | FALSE | 74 | Delayed | 2 | No |  | No Conflict | Yes
BK-1116 | 2026-11-19 | 2026-11-20 | 2026-11-27 | 1 | MEWP | Scissor Lift 10m | MEWP-16 |  |  | YST D1 | C | Commissioning | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Medium | Rescheduled | Weather delay | Partly Cloudy | 5 | FALSE | 55 |  | 2 | No |  | No Conflict | Yes
BK-1117 | 2026-11-03 | 2026-11-09 |  | 6 | Crane | Crawler Crane | CRA-02 | 150 | 88.3 | YST 04 | B | Fabrication | Anchor Chain | 14 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | High | Completed |  | Partly Cloudy | 4 | FALSE | 61 | On Time | 3 | No |  | No Conflict | Yes
BK-1118 | 2026-11-30 | 2026-12-07 |  | 7 | Forklift | Heavy Duty Forklift | FLT-20 | 10 | 6.8 | YST 19 | A | Fabrication | Gasket Boxes | 5 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Urgent | Completed |  | Overcast | 15 | FALSE | 46 | On Time | 4 | No |  | No Conflict | Yes
BK-1119 | 2026-11-05 | 2026-11-11 |  | 6 | Crane | Mobile Crane | MOB-05 | 75 | 19.8 | YST D1 | A | Outfitting | Hull Block Section | Full Day | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Pending |  | Clear | 5 | FALSE | 40 |  | 2 | No |  | No Conflict | Yes
BK-1120 | 2026-11-30 | 2026-12-07 |  | 7 | Forklift | Counterbalance Forklift | FLT-35 | 3 | 2.3 | YST D6 | E | Outfitting | Scaffolding Materials | 7 Days | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | Medium | Cancelled | Budget constraint | Clear | 15 | FALSE | 63 |  | 2 | Yes | BK-1069 | Later Request - Reassigned | No
BK-1121 | 2026-11-14 | 2026-11-16 |  | 2 | MEWP | Scissor Lift 10m | MEWP-17 |  |  | YST 01 | D | Commissioning | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Low | Cancelled | Client cancelled | Overcast | 4 | FALSE | 56 |  | 1 | No |  | No Conflict | Yes
BK-1122 | 2026-11-02 | 2026-11-08 |  | 6 | MEWP | Boom Lift 20m | MEWP-14 |  |  | YST 03 | B | Outfitting | Personnel Access Work | Full Day | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Rejected | Load exceeds crane capacity | Overcast | 6 | FALSE | 37 |  | 3 | No |  | No Conflict | Yes
BK-1123 | 2026-11-18 | 2026-11-22 |  | 4 | Crane | Mobile Crane | MOB-04 | 25 | 6 | YST D1 | B | Commissioning | Structural Steel Module | Full Day | Night Shift (1900-0700) | Team Delta | Basic Crane Operator | Medium | Completed |  | Heavy Rain | 15 | FALSE | 87 | Delayed | 2 | No |  | No Conflict | Yes
BK-1124 | 2026-11-22 | 2026-12-04 |  | 12 | Crane | Level Luffing Crane | LLC 07 | 50 | 23.6 | YST 11 | B | Assembly | Hull Block Section | 5 Days | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | Low | Pending |  | Overcast | 14 | FALSE | 59 |  | 1 | No |  | No Conflict | Yes
BK-1125 | 2026-11-01 | 2026-11-02 | 2026-11-06 | 1 | MEWP | Scissor Lift 10m | MEWP-09 |  |  | YST 04 | A | Outfitting | Personnel Access Work | Half Day (PM) | Night Shift (1900-0700) | Team Alpha | MEWP Operator | High | Rescheduled | Project timeline shifted | Overcast | 6 | FALSE | 32 |  | 3 | No |  | No Conflict | Yes
BK-1126 | 2026-11-24 | 2026-12-04 |  | 10 | Cometto | SPMT 24 Axle Lines | COM-01 |  |  | YST 19 | A | Testing | Jacket Structure | 2 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Medium | Pending |  | Partly Cloudy | 10 | FALSE | 22 |  | 2 | No |  | No Conflict | Yes
BK-1127 | 2026-11-02 | 2026-11-03 | 2026-11-09 | 1 | MEWP | Articulating Boom Lift 26m | MEWP-08 |  |  | YST 08 | A | Planning | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Operator | High | Rescheduled | Permit delay | Partly Cloudy | 4 | FALSE | 43 |  | 3 | No |  | No Conflict | Yes
BK-1128 | 2026-11-09 | 2026-11-13 |  | 4 | Crane | Tower Crane | TOW-07 | 25 | 5.4 | YST 12 | C | Fabrication | Hull Block Section | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Crane Operator | Low | Completed |  | Clear | 15 | FALSE | 76 | Delayed | 1 | No |  | No Conflict | Yes
BK-1129 | 2026-11-09 | 2026-11-13 | 2026-11-17 | 4 | Forklift | Telehandler Forklift | FLT-10 | 7 | 5 | YST 14 | F | Planning | Timber Dunnage | 5 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Medium | Rescheduled | Project timeline shifted | Light Rain | 4 | FALSE | 52 |  | 2 | No |  | No Conflict | Yes
BK-1130 | 2026-11-20 | 2026-12-02 |  | 12 | Crane | Level Luffing Crane | LLC 02 | 40 | 23.3 | YST 13 | B | Outfitting | Structural Steel Module | 3 Days | Day Shift (0700-1900) | Team Alpha | Basic Crane Operator | Medium | Cancelled | Duplicate booking | Clear | 13 | FALSE | 30 |  | 2 | Yes | BK-1132 | Priority Override | Yes
BK-1131 | 2026-11-30 | 2026-12-03 |  | 3 | Forklift | Counterbalance Forklift | FLT-11 | 2.5 | 2.2 | YST 10 | C | Planning | Safety Equipment | 3 Days | Night Shift (1900-0700) | Team Echo | Forklift Operator | Urgent | Pending |  | Partly Cloudy | 15 | FALSE | 70 |  | 4 | No |  | No Conflict | Yes
BK-1132 | 2026-11-21 | 2026-12-04 |  | 13 | Crane | Level Luffing Crane | LLC 02 | 50 | 25.7 | YST 13 | A | Planning | Engine Module | Half Day (AM) | Day Shift (0700-1900) | Team Beta | Advanced Crane Operator | Low | Completed |  | Clear | 9 | FALSE | 41 | On Time | 1 | Yes | BK-1130 | Yielded to Higher Priority | No
BK-1133 | 2026-11-29 | 2026-12-08 |  | 9 | Crane | Goliath Gantry Crane | GC-17 | 600 | 384.8 | YST 19 | E | Commissioning | Riser Assembly | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | Heavy Lift Specialist | High | Completed |  | Partly Cloudy | 17 | FALSE | 60 | On Time | 3 | No |  | No Conflict | Yes
BK-1134 | 2026-11-27 | 2026-12-06 |  | 9 | Cometto | SPMT 16 Axle Lines | COM-12 |  |  | YST 05 | D | Outfitting | Offshore Platform Topside | Half Day (AM) | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Confirmed |  | High Wind | 45 | FALSE | 92 |  | 2 | No |  | No Conflict | Yes
BK-1135 | 2026-11-01 | 2026-11-03 |  | 2 | Crane | Goliath Gantry Crane | GC-14 | 200 | 104.2 | YST 04 | D | Planning | Mooring Winch | 10 Days | Day Shift (0700-1900) | Team Beta | Advanced Crane Operator | Medium | Completed |  | Partly Cloudy | 15 | FALSE | 60 | Delayed | 2 | No |  | No Conflict | Yes
BK-1136 | 2026-11-24 | 2026-12-02 | 2026-12-09 | 8 | Forklift | Heavy Duty Forklift | FLT-33 | 25 | 22.3 | YST 15 | D | Fabrication | Steel Plates | 2 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Urgent | Rescheduled | Permit delay | Heavy Rain | 18 | FALSE | 46 |  | 4 | No |  | No Conflict | Yes
BK-1137 | 2026-11-18 | 2026-11-23 |  | 5 | Forklift | Telehandler Forklift | FLT-06 | 5 | 3 | YST 16 | D | Planning | Timber Dunnage | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Advanced Operator | Medium | Confirmed |  | Light Rain | 11 | FALSE | 59 |  | 2 | No |  | No Conflict | Yes
BK-1138 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2 | Crane | Crawler Crane | CRA-10 | 100 | 70.6 | YST 05 | B | Planning | Hull Block Section | 5 Days | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | Medium | Rescheduled | Equipment breakdown | Partly Cloudy | 15 | TRUE | 36 |  | 2 | No |  | No Conflict | Yes
BK-1139 | 2026-11-26 | 2026-11-29 |  | 3 | Forklift | Telehandler Forklift | FLT-08 | 5 | 1.5 | YST D1 | A | Testing | Safety Equipment | Half Day (PM) | Night Shift (1900-0700) | Team Delta | Forklift Operator | High | Pending |  | Clear | 9 | FALSE | 34 |  | 3 | No |  | No Conflict | Yes
BK-1140 | 2026-11-10 | 2026-11-13 |  | 3 | Cometto | SPMT 16 Axle Lines | COM-03 |  |  | YST 16 | A | Outfitting | Jacket Structure | 5 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | High | Completed |  | Partly Cloudy | 2 | FALSE | 46 | Delayed | 3 | Yes | BK-1036 | Priority Override | Yes
BK-1141 | 2026-11-02 | 2026-11-05 |  | 3 | Crane | Crawler Crane | CRA-09 | 150 | 68.1 | YST 04 | D | Planning | Workshop Equipment | Half Day (PM) | Night Shift (1900-0700) | Team Beta | Rigging Supervisor | Urgent | Confirmed |  | Partly Cloudy | 18 | FALSE | 55 |  | 4 | No |  | No Conflict | Yes
BK-1142 | 2026-11-16 | 2026-11-19 |  | 3 | Cometto | SPMT 24 Axle Lines | COM-04 |  |  | YST 01 | E | Testing | Engine Module | Full Day | Night Shift (1900-0700) | Team Beta | Basic Operator | Medium | Completed |  | Overcast | 3 | FALSE | 91 | On Time | 2 | No |  | No Conflict | Yes
BK-1143 | 2026-11-01 | 2026-11-04 |  | 3 | Forklift | Reach Forklift | FLT-32 | 1.5 | 1.2 | YST 08 | A | Commissioning | Insulation Materials | 5 Days | Day Shift (0700-1900) | Team Delta | Basic Operator | High | Pending |  | Clear | 14 | FALSE | 42 |  | 3 | No |  | No Conflict | Yes
BK-1144 | 2026-11-22 | 2026-11-30 |  | 8 | Forklift | Counterbalance Forklift | FLT-30 | 5 | 2.2 | YST 04 | A | Fabrication | Electrical Cables | 5 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Urgent | Cancelled | Client cancelled | High Wind | 35 | FALSE | 21 |  | 4 | No |  | No Conflict | Yes
BK-1145 | 2026-11-16 | 2026-11-28 |  | 12 | MEWP | Telescopic Boom Lift 30m | MEWP-16 |  |  | YST 01 | D | Planning | Personnel Access Work | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Basic Operator | High | Completed |  | Partly Cloudy | 18 | FALSE | 79 | On Time | 3 | No |  | No Conflict | Yes
BK-1146 | 2026-12-05 | 2026-12-16 |  | 11 | Cometto | SPMT 24 Axle Lines | COM-08 |  |  | YST 05 | D | Outfitting | Offshore Platform Topside | 5 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Medium | Completed |  | Overcast | 5 | FALSE | 40 | On Time | 2 | Yes | BK-1147 | First-Come-First-Served | Yes
BK-1147 | 2026-12-10 | 2026-12-17 |  | 7 | Cometto | SPMT 16 Axle Lines | COM-08 |  |  | YST 20 | C | Fabrication | Mega Block Section | 7 Days | Day Shift (0700-1900) | Team Alpha | Basic Operator | Medium | Completed |  | Light Rain | 6 | FALSE | 65 | Early | 2 | Yes | BK-1146 | Later Request - Reassigned | No
BK-1148 | 2026-12-06 | 2026-12-19 |  | 13 | Crane | Tower Crane | TOW-13 | 10 | 2.4 | YST D2 | D | Outfitting | Construction Materials | 3 Days | Night Shift (1900-0700) | Team Gamma | Heavy Lift Specialist | Medium | Completed |  | Overcast | 13 | FALSE | 47 | On Time | 2 | No |  | No Conflict | Yes
BK-1149 | 2026-12-28 | 2027-01-11 |  | 14 | Forklift | Heavy Duty Forklift | FLT-08 | 10 | 8.9 | YST 11 | A | Fabrication | Pipe Bundles | 5 Days | Night Shift (1900-0700) | Team Beta | MEWP Operator | Medium | Confirmed |  | Clear | 3 | FALSE | 81 |  | 2 | No |  | No Conflict | Yes
BK-1150 | 2026-12-17 | 2026-12-26 |  | 9 | Forklift | Heavy Duty Forklift | FLT-08 | 20 | 6.1 | YST D8 | C | Testing | Tool Containers | 3 Days | Night Shift (1900-0700) | Team Echo | MEWP Operator | Medium | Pending |  | Clear | 2 | FALSE | 67 |  | 2 | No |  | No Conflict | Yes
BK-1151 | 2026-12-14 | 2026-12-21 |  | 7 | Forklift | Counterbalance Forklift | FLT-03 | 5 | 2.7 | YST D8 | F | Testing | Valve Crates | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Forklift Operator | Medium | Cancelled | Project postponed | High Wind | 34 | FALSE | 62 |  | 2 | No |  | No Conflict | Yes
BK-1152 | 2026-12-28 | 2027-01-09 |  | 12 | Forklift | Heavy Duty Forklift | FLT-06 | 20 | 11.9 | YST 18 | D | Outfitting | Safety Equipment | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Urgent | Completed |  | Clear | 6 | FALSE | 77 | Delayed | 4 | No |  | No Conflict | Yes
BK-1153 | 2026-12-28 | 2027-01-10 |  | 13 | Crane | Goliath Gantry Crane | GC-10 | 600 | 395.4 | YST 04 | A | Fabrication | Pipe Spool | Half Day (PM) | Night Shift (1900-0700) | Team Delta | Heavy Lift Specialist | Urgent | Completed |  | Clear | 13 | FALSE | 46 | On Time | 4 | No |  | No Conflict | Yes
BK-1154 | 2026-12-09 | 2026-12-12 |  | 3 | Forklift | Counterbalance Forklift | FLT-25 | 7 | 4.1 | YST 06 | C | Assembly | Valve Crates | Half Day (AM) | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Cancelled | Client cancelled | Partly Cloudy | 16 | FALSE | 48 |  | 2 | No |  | No Conflict | Yes
BK-1155 | 2026-12-04 | 2026-12-05 |  | 1 | Crane | Tower Crane | TOW-13 | 40 | 13.2 | YST 10 | B | Outfitting | Pipe Spool | 5 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Medium | Cancelled | Duplicate booking | Overcast | 3 | FALSE | 34 |  | 2 | No |  | No Conflict | Yes
BK-1156 | 2026-12-17 | 2026-12-18 |  | 1 | Crane | Mobile Crane | MOB-10 | 75 | 49.7 | YST 02 | B | Testing | Flare Tower Section | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Crane Operator | High | Completed |  | Clear | 10 | FALSE | 73 | On Time | 3 | No |  | No Conflict | Yes
BK-1157 | 2026-12-05 | 2026-12-16 |  | 11 | Crane | Tower Crane | TOW-14 | 25 | 17.9 | YST 09 | B | Fabrication | Mooring Winch | 2 Days | Day Shift (0700-1900) | Team Delta | Heavy Lift Specialist | High | Completed |  | Partly Cloudy | 4 | FALSE | 61 | On Time | 3 | No |  | No Conflict | Yes
BK-1158 | 2026-12-18 | 2026-12-31 |  | 13 | Crane | Mobile Crane | MOB-05 | 50 | 33.9 | YST 06 | A | Outfitting | Construction Materials | Full Day | Day Shift (0700-1900) | Team Foxtrot | Advanced Crane Operator | Medium | Completed |  | Heavy Rain | 10 | FALSE | 73 | Early | 2 | No |  | No Conflict | Yes
BK-1159 | 2026-12-19 | 2026-12-27 | 2026-12-31 | 8 | Crane | Workshop Crane | WOR-08 | 20 | 12.9 | YST 15 | E | Fabrication | Helideck Module | Full Day | Day Shift (0700-1900) | Team Alpha | Lifting Supervisor | High | Rescheduled | Equipment breakdown | Partly Cloudy | 15 | FALSE | 48 |  | 3 | No |  | No Conflict | Yes
BK-1160 | 2026-12-31 | 2027-01-04 |  | 4 | Crane | Goliath Gantry Crane | GC-01 | 300 | 165.6 | YST 04 | C | Fabrication | Mooring Winch | 5 Days | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | Medium | Completed |  | Partly Cloudy | 4 | FALSE | 55 | Delayed | 2 | No |  | No Conflict | Yes
BK-1161 | 2026-12-17 | 2026-12-21 |  | 4 | Forklift | Reach Forklift | FLT-09 | 2 | 1.5 | YST D8 | F | Fabrication | Consumables Pallet | 2 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | High | Confirmed |  | Partly Cloudy | 5 | FALSE | 93 |  | 3 | No |  | No Conflict | Yes
BK-1162 | 2026-12-12 | 2026-12-20 | 2026-12-21 | 8 | MEWP | Scissor Lift 10m | MEWP-04 |  |  | YST D4 | C | Planning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Gamma | Forklift Operator | Medium | Rescheduled | Operator reassigned | Clear | 14 | TRUE | 31 |  | 2 | No |  | No Conflict | Yes
BK-1163 | 2026-12-27 | 2027-01-01 | 2027-01-02 | 5 | MEWP | Boom Lift 20m | MEWP-06 |  |  | YST 06 | E | Planning | Personnel Access Work | Half Day (AM) | Day Shift (0700-1900) | Team Delta | Basic Operator | Urgent | Rescheduled | Material delivery delayed | Clear | 10 | TRUE | 24 |  | 4 | No |  | No Conflict | Yes
BK-1164 | 2026-12-14 | 2026-12-21 |  | 7 | Forklift | Reach Forklift | FLT-14 | 3 | 1.4 | YST D5 | C | Commissioning | Steel Plates | 5 Days | Day Shift (0700-1900) | Team Beta | Basic Operator | Medium | Rejected | Insufficient lead time | Clear | 3 | FALSE | 49 |  | 2 | No |  | No Conflict | Yes
BK-1165 | 2026-12-06 | 2026-12-10 |  | 4 | Crane | Tower Crane | TOW-15 | 15 | 9.7 | YST 10 | E | Planning | Flare Tower Section | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Rigging Supervisor | Medium | Completed |  | Partly Cloudy | 3 | FALSE | 60 | On Time | 2 | No |  | No Conflict | Yes
BK-1166 | 2026-12-06 | 2026-12-17 |  | 11 | MEWP | Articulating Boom Lift 26m | MEWP-23 |  |  | YST 04 | D | Fabrication | Personnel Access Work | 3 Days | Night Shift (1900-0700) | Team Beta | Basic Operator | Medium | Cancelled | Budget constraint | Partly Cloudy | 4 | FALSE | 27 |  | 2 | No |  | No Conflict | Yes
BK-1167 | 2026-12-27 | 2027-01-01 |  | 5 | Crane | Level Luffing Crane | LLC 14 | 50 | 26.6 | YST D3 | C | Fabrication | Flare Tower Section | Half Day (AM) | Night Shift (1900-0700) | Team Foxtrot | Advanced Crane Operator | Medium | Completed |  | Partly Cloudy | 7 | FALSE | 53 | Delayed | 2 | No |  | No Conflict | Yes
BK-1168 | 2026-12-09 | 2026-12-16 |  | 7 | MEWP | Articulating Boom Lift 26m | MEWP-15 |  |  | YST 01 | D | Commissioning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Echo | Forklift Operator | Medium | Rejected | Crane under scheduled maintenance | Partly Cloudy | 13 | TRUE | 54 |  | 2 | No |  | No Conflict | Yes
BK-1169 | 2026-12-01 | 2026-12-09 |  | 8 | Forklift | Heavy Duty Forklift | FLT-05 | 10 | 6.5 | YST 06 | A | Assembly | PPE Supplies | 7 Days | Night Shift (1900-0700) | Team Gamma | Basic Operator | Urgent | Completed |  | Clear | 3 | FALSE | 50 | On Time | 4 | No |  | No Conflict | Yes
BK-1170 | 2026-12-07 | 2026-12-10 |  | 3 | Crane | Goliath Gantry Crane | GC-01 | 240 | 190.5 | YST 04 | A | Planning | Engine Module | Half Day (PM) | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | High | Completed |  | Overcast | 9 | FALSE | 90 | Delayed | 3 | No |  | No Conflict | Yes
BK-1171 | 2026-12-29 | 2026-12-30 |  | 1 | Forklift | Telehandler Forklift | FLT-16 | 4 | 2 | YST 20 | D | Fabrication | Tool Containers | Full Day | Day Shift (0700-1900) | Team Beta | Forklift Operator | Medium | Confirmed |  | Clear | 2 | FALSE | 74 |  | 2 | No |  | No Conflict | Yes
BK-1172 | 2026-12-21 | 2026-12-24 | 2026-12-28 | 3 | Crane | Crawler Crane | CRA-19 | 150 | 40.6 | YST 02 | E | Testing | Structural Steel Module | Half Day (AM) | Night Shift (1900-0700) | Team Echo | Advanced Crane Operator | Medium | Rescheduled | Safety stand-down | Overcast | 3 | FALSE | 24 |  | 2 | No |  | No Conflict | Yes
BK-1173 | 2026-12-15 | 2026-12-19 |  | 4 | Crane | Goliath Gantry Crane | GC-13 | 200 | 110.3 | YST 01 | D | Assembly | Anchor Chain | 3 Days | Night Shift (1900-0700) | Team Foxtrot | Advanced Crane Operator | Low | Completed |  | Overcast | 5 | FALSE | 68 | On Time | 1 | No |  | No Conflict | Yes
BK-1174 | 2026-12-08 | 2026-12-10 |  | 2 | Crane | Workshop Crane | WOR-09 | 20 | 12.4 | YST 08 | D | Planning | Anchor Chain | 3 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | High | Completed |  | Heavy Rain | 14 | FALSE | 67 | On Time | 3 | No |  | No Conflict | Yes
BK-1175 | 2026-12-26 | 2027-01-04 |  | 9 | Crane | Tower Crane | TOW-09 | 15 | 6.2 | YST D5 | A | Assembly | Riser Assembly | 2 Days | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Medium | Cancelled | Duplicate booking | Overcast | 12 | FALSE | 33 |  | 2 | No |  | No Conflict | Yes
BK-1176 | 2026-12-24 | 2027-01-02 |  | 9 | Crane | Workshop Crane | WOR-02 | 10 | 6.2 | YST 13 | D | Testing | Mega Block Section | 3 Days | Day Shift (0700-1900) | Team Echo | Advanced Crane Operator | Medium | Confirmed |  | High Wind | 36 | FALSE | 48 |  | 2 | No |  | No Conflict | Yes
BK-1177 | 2026-12-05 | 2026-12-18 |  | 13 | MEWP | Boom Lift 20m | MEWP-21 |  |  | YST 09 | F | Planning | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Echo | Advanced Operator | High | Pending |  | Partly Cloudy | 17 | FALSE | 47 |  | 3 | No |  | No Conflict | Yes
BK-1178 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 7 | Forklift | Heavy Duty Forklift | FLT-38 | 15 | 13.1 | YST 08 | A | Fabrication | PPE Supplies | 3 Days | Day Shift (0700-1900) | Team Gamma | Basic Operator | Low | Rescheduled | Client request | Partly Cloudy | 11 | FALSE | 52 |  | 1 | No |  | No Conflict | Yes
BK-1179 | 2026-12-26 | 2026-12-31 |  | 5 | MEWP | Boom Lift 20m | MEWP-25 |  |  | YST 06 | A | Commissioning | Personnel Access Work | 2 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Rejected | Safety inspection required first | Partly Cloudy | 14 | FALSE | 43 |  | 2 | No |  | No Conflict | Yes
BK-1180 | 2026-12-10 | 2026-12-22 |  | 12 | Forklift | Telehandler Forklift | FLT-11 | 5 | 2 | YST 03 | B | Assembly | Consumables Pallet | 3 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Low | Confirmed |  | Overcast | 14 | FALSE | 59 |  | 1 | No |  | No Conflict | Yes
BK-1181 | 2026-12-15 | 2026-12-18 |  | 3 | Crane | Tower Crane | TOW-01 | 25 | 16.8 | YST 12 | C | Testing | Workshop Equipment | Half Day (PM) | Night Shift (1900-0700) | Team Beta | Heavy Lift Specialist | Medium | Completed |  | Overcast | 2 | FALSE | 81 | On Time | 2 | No |  | No Conflict | Yes
BK-1182 | 2026-12-06 | 2026-12-16 |  | 10 | Crane | Goliath Gantry Crane | GC-15 | 400 | 235.3 | YST 04 | B | Fabrication | Hull Block Section | 7 Days | Night Shift (1900-0700) | Team Alpha | Basic Crane Operator | Urgent | Completed |  | Clear | 11 | FALSE | 54 | Delayed | 4 | No |  | No Conflict | Yes
BK-1183 | 2026-12-02 | 2026-12-11 |  | 9 | Crane | Goliath Gantry Crane | GC-14 | 240 | 148.1 | YST 04 | A | Testing | Helideck Module | 3 Days | Day Shift (0700-1900) | Team Beta | Heavy Lift Specialist | Medium | Completed |  | Clear | 2 | FALSE | 41 | Early | 2 | No |  | No Conflict | Yes
BK-1184 | 2026-12-05 | 2026-12-11 |  | 6 | Cometto | SPMT 16 Axle Lines | COM-07 |  |  | YST 14 | D | Fabrication | Mega Block Section | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Forklift Operator | High | Confirmed |  | Partly Cloudy | 8 | FALSE | 85 |  | 3 | No |  | No Conflict | Yes
BK-1185 | 2026-12-31 | 2027-01-05 | 2027-01-06 | 5 | Crane | Crawler Crane | CRA-07 | 100 | 67.2 | YST 08 | F | Planning | Structural Steel Module | Full Day | Day Shift (0700-1900) | Team Delta | Basic Crane Operator | High | Rescheduled | Permit delay | Clear | 8 | TRUE | 65 |  | 3 | No |  | No Conflict | Yes
BK-1186 | 2026-12-31 | 2027-01-05 |  | 5 | Crane | Goliath Gantry Crane | GC-15 | 200 | 97.2 | YST 04 | D | Commissioning | Pipe Spool | 7 Days | Day Shift (0700-1900) | Team Foxtrot | Heavy Lift Specialist | Medium | Confirmed |  | Heavy Rain | 21 | FALSE | 98 |  | 2 | No |  | No Conflict | Yes
BK-1187 | 2026-12-25 | 2026-12-26 |  | 1 | Forklift | Heavy Duty Forklift | FLT-12 | 20 | 12.1 | YST 20 | D | Assembly | Electrical Cables | 3 Days | Day Shift (0700-1900) | Team Gamma | Advanced Operator | Urgent | Rejected | Crane already booked | Heavy Rain | 13 | FALSE | 51 |  | 4 | No |  | No Conflict | Yes
BK-1188 | 2026-12-20 | 2026-12-27 |  | 7 | Crane | Crawler Crane | CRA-06 | 100 | 45.7 | YST 01 | D | Fabrication | Riser Assembly | Full Day | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Medium | Completed |  | Clear | 13 | FALSE | 52 | Delayed | 2 | No |  | No Conflict | Yes
BK-1189 | 2026-12-13 | 2026-12-20 |  | 7 | Crane | Level Luffing Crane | LLC 10 | 40 | 24.5 | YST 12 | D | Testing | Flare Tower Section | 5 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Medium | Rejected | Project schedule changed | Overcast | 10 | FALSE | 65 |  | 2 | No |  | No Conflict | Yes
BK-1190 | 2026-12-09 | 2026-12-11 | 2026-12-16 | 2 | Crane | Level Luffing Crane | LLC 17 | 300 | 102.2 | YST 11 | B | Planning | Mega Block Section | 7 Days | Day Shift (0700-1900) | Team Gamma | Rigging Supervisor | Medium | Rescheduled | Permit delay | Partly Cloudy | 10 | TRUE | 22 |  | 2 | No |  | No Conflict | Yes
BK-1191 | 2026-12-25 | 2026-12-28 |  | 3 | MEWP | Articulating Boom Lift 26m | MEWP-02 |  |  | YST D2 | B | Outfitting | Personnel Access Work | Full Day | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Medium | Confirmed |  | Partly Cloudy | 18 | FALSE | 53 |  | 2 | No |  | No Conflict | Yes
BK-1192 | 2026-12-15 | 2026-12-17 |  | 2 | Cometto | Cometto MSPE 8 Axle Lines | COM-11 |  |  | YST 16 | D | Fabrication | Offshore Platform Topside | 10 Days | Day Shift (0700-1900) | Team Delta | Forklift Operator | Medium | Completed |  | Overcast | 14 | FALSE | 65 | Delayed | 2 | No |  | No Conflict | Yes
BK-1193 | 2026-12-26 | 2027-01-06 | 2027-01-12 | 11 | Forklift | Telehandler Forklift | FLT-34 | 5 | 3.2 | YST D3 | B | Outfitting | Safety Equipment | 2 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | High | Rescheduled | Client request | Partly Cloudy | 7 | FALSE | 22 |  | 3 | No |  | No Conflict | Yes
BK-1194 | 2026-12-15 | 2026-12-22 |  | 7 | Forklift | Reach Forklift | FLT-24 | 1.5 | 1 | YST 10 | F | Fabrication | Valve Crates | 2 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Confirmed |  | Partly Cloudy | 15 | FALSE | 41 |  | 2 | No |  | No Conflict | Yes
BK-1195 | 2026-12-13 | 2026-12-19 |  | 6 | Crane | Goliath Gantry Crane | GC-10 | 200 | 113.7 | YST 04 | D | Testing | Mooring Winch | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Rigging Supervisor | Medium | Completed |  | Overcast | 4 | FALSE | 68 | Delayed | 2 | No |  | No Conflict | Yes
BK-1196 | 2026-12-17 | 2026-12-22 |  | 5 | Crane | Crawler Crane | CRA-07 | 50 | 39.6 | YST 07 | F | Testing | Mooring Winch | 3 Days | Day Shift (0700-1900) | Team Foxtrot | Basic Crane Operator | High | Cancelled | Duplicate booking | Heavy Rain | 25 | FALSE | 60 |  | 3 | No |  | No Conflict | Yes
BK-1197 | 2026-12-11 | 2026-12-21 |  | 10 | Forklift | Telehandler Forklift | FLT-30 | 4 | 1.3 | YST 05 | A | Testing | Insulation Materials | Half Day (AM) | Day Shift (0700-1900) | Team Echo | Advanced Operator | Medium | Cancelled | Project postponed | Heavy Rain | 24 | FALSE | 23 |  | 2 | No |  | No Conflict | Yes
BK-1198 | 2026-12-25 | 2026-12-27 | 2026-12-31 | 2 | Forklift | Counterbalance Forklift | FLT-33 | 7 | 5.1 | YST 07 | D | Planning | PPE Supplies | 5 Days | Day Shift (0700-1900) | Team Echo | MEWP Operator | High | Rescheduled | Operator reassigned | Overcast | 15 | FALSE | 34 |  | 3 | No |  | No Conflict | Yes
BK-1199 | 2026-12-03 | 2026-12-09 |  | 6 | Forklift | Counterbalance Forklift | FLT-40 | 7 | 6.2 | YST D7 | F | Testing | Electrical Cables | Full Day | Day Shift (0700-1900) | Team Gamma | Basic Operator | Medium | Completed |  | Partly Cloudy | 9 | FALSE | 89 | On Time | 2 | No |  | No Conflict | Yes
BK-1200 | 2026-12-11 | 2026-12-15 |  | 4 | Forklift | Counterbalance Forklift | FLT-37 | 2.5 | 1 | YST 10 | A | Testing | Bolt Pallets | 3 Days | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Urgent | Pending |  | Partly Cloudy | 16 | FALSE | 58 |  | 4 | No |  | No Conflict | Yes
BK-1201 | 2026-12-17 | 2026-12-20 |  | 3 | Forklift | Heavy Duty Forklift | FLT-04 | 20 | 11.7 | YST D2 | D | Commissioning | Valve Crates | 5 Days | Night Shift (1900-0700) | Team Foxtrot | MEWP Operator | High | Cancelled | Client cancelled | Partly Cloudy | 15 | FALSE | 44 |  | 3 | No |  | No Conflict | Yes
BK-1202 | 2026-12-21 | 2026-12-26 |  | 5 | MEWP | Boom Lift 20m | MEWP-11 |  |  | YST 04 | C | Testing | Personnel Access Work | 7 Days | Day Shift (0700-1900) | Team Alpha | MEWP Operator | Medium | Cancelled | Budget constraint | Thunderstorm | 24 | FALSE | 25 |  | 2 | No |  | No Conflict | Yes
BK-1203 | 2026-12-11 | 2026-12-12 | 2026-12-14 | 1 | Forklift | Counterbalance Forklift | FLT-39 | 2.5 | 1.5 | YST 16 | B | Planning | Pipe Bundles | 10 Days | Day Shift (0700-1900) | Team Gamma | MEWP Operator | Low | Rescheduled | Weather delay | Partly Cloudy | 3 | FALSE | 45 |  | 1 | No |  | No Conflict | Yes
BK-1204 | 2026-12-17 | 2026-12-20 |  | 3 | Forklift | Heavy Duty Forklift | FLT-34 | 20 | 17.4 | YST D7 | E | Testing | Electrical Cables | 2 Days | Night Shift (1900-0700) | Team Foxtrot | Basic Operator | Urgent | Completed |  | Overcast | 12 | FALSE | 81 | On Time | 4 | No |  | No Conflict | Yes
BK-1205 | 2026-12-09 | 2026-12-11 |  | 2 | Crane | Level Luffing Crane | LLC 04 | 100 | 53.4 | YST D3 | D | Outfitting | Workshop Equipment | 5 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Urgent | Confirmed |  | Partly Cloudy | 2 | FALSE | 93 |  | 4 | No |  | No Conflict | Yes
BK-1206 | 2026-12-01 | 2026-12-04 |  | 3 | Crane | Level Luffing Crane | LLC 22 | 40 | 16 | YST 15 | D | Commissioning | Mega Block Section | 7 Days | Day Shift (0700-1900) | Team Gamma | Advanced Crane Operator | Medium | Rejected | Permit not approved | Overcast | 10 | FALSE | 25 |  | 2 | No |  | No Conflict | Yes
BK-1207 | 2026-12-06 | 2026-12-07 |  | 1 | Cometto | Cometto Eco500 12 Axle Lines | COM-11 |  |  | YST 05 | B | Fabrication | Hull Block Section | 7 Days | Day Shift (0700-1900) | Team Echo | Basic Operator | Low | Confirmed |  | Partly Cloudy | 9 | FALSE | 75 |  | 1 | No |  | No Conflict | Yes
BK-1208 | 2026-12-30 | 2027-01-03 |  | 4 | MEWP | Scissor Lift 10m | MEWP-20 |  |  | YST 08 | B | Outfitting | Personnel Access Work | 2 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | Medium | Rejected | Load exceeds crane capacity | Partly Cloudy | 11 | TRUE | 68 |  | 2 | No |  | No Conflict | Yes
BK-1209 | 2026-12-14 | 2026-12-18 | 2026-12-21 | 4 | Forklift | Reach Forklift | FLT-02 | 2.5 | 2.1 | YST D5 | E | Testing | Gasket Boxes | 10 Days | Night Shift (1900-0700) | Team Foxtrot | Forklift Operator | Medium | Rescheduled | Safety stand-down | Clear | 13 | TRUE | 43 |  | 2 | No |  | No Conflict | Yes
BK-1210 | 2026-12-31 | 2027-01-08 | 2027-01-10 | 8 | Crane | Goliath Gantry Crane | GC-01 | 240 | 101.7 | YST 01 | D | Assembly | Anchor Chain | 2 Days | Night Shift (1900-0700) | Team Echo | Heavy Lift Specialist | High | Rescheduled | Safety stand-down | Overcast | 6 | FALSE | 62 |  | 3 | No |  | No Conflict | Yes
BK-1211 | 2026-12-05 | 2026-12-14 |  | 9 | Forklift | Heavy Duty Forklift | FLT-27 | 25 | 10.3 | YST 06 | D | Testing | PPE Supplies | 3 Days | Day Shift (0700-1900) | Team Delta | Advanced Operator | Medium | Confirmed |  | Overcast | 7 | FALSE | 79 |  | 2 | No |  | No Conflict | Yes
BK-1212 | 2026-12-19 | 2026-12-30 |  | 11 | Forklift | Heavy Duty Forklift | FLT-36 | 15 | 12.7 | YST 07 | D | Outfitting | Paint Drums | 5 Days | Night Shift (1900-0700) | Team Delta | Advanced Operator | High | Completed |  | Overcast | 13 | FALSE | 59 | On Time | 3 | No |  | No Conflict | Yes
BK-1213 | 2026-12-09 | 2026-12-15 | 2026-12-22 | 6 | Crane | Crawler Crane | CRA-07 | 100 | 37.4 | YST 02 | D | Planning | Pipe Spool | 3 Days | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | Low | Rescheduled | Safety stand-down | Clear | 4 | FALSE | 29 |  | 1 | No |  | No Conflict | Yes
BK-1214 | 2026-12-20 | 2026-12-28 |  | 8 | Forklift | Telehandler Forklift | FLT-19 | 4 | 3.4 | YST D8 | E | Testing | Pipe Bundles | 5 Days | Day Shift (0700-1900) | Team Beta | MEWP Operator | Medium | Confirmed |  | Partly Cloudy | 6 | FALSE | 70 |  | 2 | No |  | No Conflict | Yes
BK-1215 | 2026-12-05 | 2026-12-06 | 2026-12-08 | 1 | MEWP | Telescopic Boom Lift 30m | MEWP-27 |  |  | YST 11 | B | Assembly | Personnel Access Work | 5 Days | Day Shift (0700-1900) | Team Foxtrot | Forklift Operator | High | Rescheduled | Project timeline shifted | Thunderstorm | 30 | TRUE | 31 |  | 3 | No |  | No Conflict | Yes
BK-1216 | 2026-12-11 | 2026-12-21 | 2026-12-22 | 10 | Crane | Mobile Crane | MOB-04 | 100 | 58.9 | YST 07 | E | Testing | Construction Materials | 3 Days | Day Shift (0700-1900) | Team Echo | Rigging Supervisor | Medium | Rescheduled | Material delivery delayed | Thunderstorm | 21 | FALSE | 20 |  | 2 | No |  | No Conflict | Yes
BK-1217 | 2026-12-16 | 2026-12-24 |  | 8 | Crane | Level Luffing Crane | LLC 14 | 100 | 71 | YST D4 | F | Commissioning | Anchor Chain | Half Day (PM) | Day Shift (0700-1900) | Team Echo | Basic Crane Operator | Medium | Completed |  | Overcast | 11 | FALSE | 55 | Delayed | 2 | No |  | No Conflict | Yes
BK-1218 | 2026-12-10 | 2026-12-16 |  | 6 | Crane | Goliath Gantry Crane | GC-14 | 300 | 73.2 | YST 01 | D | Outfitting | Engine Module | 3 Days | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | Low | Confirmed |  | Clear | 7 | FALSE | 62 |  | 1 | No |  | No Conflict | Yes
BK-1219 | 2026-12-02 | 2026-12-05 |  | 3 | Crane | Tower Crane | TOW-11 | 15 | 7.1 | YST 09 | B | Testing | Structural Steel Module | 5 Days | Night Shift (1900-0700) | Team Echo | Basic Crane Operator | High | Confirmed |  | Partly Cloudy | 8 | FALSE | 86 |  | 3 | No |  | No Conflict | Yes
BK-1220 | 2026-01-12 | 2026-01-15 | 2026-01-19 | 3 | Crane | Workshop Crane | WOR-18 | 20 | 4.6 | YST 06 | A | Fabrication | Turret Assembly | Full Day | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | High | Rescheduled | Original date conflicts with maintenance | Thunderstorm | 32 | FALSE | 22 |  | 3 | No |  | No Conflict | Yes
BK-1221 | 2026-07-08 | 2026-07-13 |  | 5 | Crane | Level Luffing Crane | LLC 21 | 40 | 22.1 | YST D1 | E | Planning | Riser Assembly | Half Day (PM) | Day Shift (0700-1900) | Team Gamma | Heavy Lift Specialist | High | Cancelled | Project postponed | Clear | 8 | FALSE | 23 |  | 3 | No |  | No Conflict | Yes
BK-1222 | 2026-12-08 | 2026-12-15 |  | 7 | Crane | Goliath Gantry Crane | GC-16 | 200 | 108.9 | YST 19 | F | Testing | Accommodation Module | Half Day (PM) | Day Shift (0700-1900) | Team Delta | Lifting Supervisor | High | Pending |  | Partly Cloudy | 5 | FALSE | 45 |  | 3 | No |  | No Conflict | Yes
BK-1223 | 2026-01-02 | 2026-01-09 |  | 7 | MEWP | Scissor Lift 10m | MEWP-28 |  |  | YST 05 | C | Assembly | Personnel Access Work | 10 Days | Day Shift (0700-1900) | Team Delta | MEWP Operator | Urgent | Cancelled | Client cancelled | High Wind | 43 | FALSE | 40 |  | 4 | No |  | No Conflict | Yes
BK-1224 | 2026-05-24 | 2026-05-31 |  | 7 | MEWP | Articulating Boom Lift 26m | MEWP-08 |  |  | YST 11 | E | Testing | Personnel Access Work | 3 Days | Day Shift (0700-1900) | Team Alpha | Forklift Operator | High | Confirmed |  | Partly Cloudy | 13 | FALSE | 58 |  | 3 | No |  | No Conflict | Yes
BK-1225 | 2026-05-25 | 2026-05-29 |  | 4 | Forklift | Heavy Duty Forklift | FLT-10 | 15 | 5.4 | YST 20 | A | Fabrication | Bolt Pallets | Half Day (PM) | Day Shift (0700-1900) | Team Alpha | Advanced Operator | Medium | Completed |  | High Wind | 38 | FALSE | 48 | On Time | 2 | No |  | No Conflict | Yes
BK-1226 | 2026-07-01 | 2026-07-06 |  | 5 | Crane | Workshop Crane | WOR-13 | 10 | 2.4 | YST D3 | A | Assembly | Riser Assembly | Half Day (AM) | Day Shift (0700-1900) | Team Alpha | Advanced Crane Operator | Medium | Completed |  | High Wind | 25 | FALSE | 86 | Delayed | 2 | No |  | No Conflict | Yes
BK-1227 | 2026-02-14 | 2026-02-20 |  | 6 | Crane | Mobile Crane | MOB-15 | 25 | 13.5 | YST 06 | B | Testing | Transformer Unit | 3 Days | Day Shift (0700-1900) | Team Beta | Basic Crane Operator | Medium | Confirmed |  | Partly Cloudy | 16 | FALSE | 64 |  | 2 | No |  | No Conflict | Yes
BK-1228 | 2026-05-24 | 2026-06-02 |  | 9 | Crane | Workshop Crane | WOR-02 | 20 | 9.2 | YST D5 | F | Testing | Construction Materials | 2 Days | Day Shift (0700-1900) | Team Echo | Heavy Lift Specialist | Urgent | Confirmed |  | Overcast | 14 | FALSE | 59 |  | 4 | No |  | No Conflict | Yes
BK-1229 | 2026-12-13 | 2026-12-20 |  | 7 | Crane | Mobile Crane | MOB-07 | 25 | 10.6 | YST D1 | D | Outfitting | Mega Block Section | 7 Days | Night Shift (1900-0700) | Team Delta | Advanced Crane Operator | Medium | Cancelled | Project postponed | Partly Cloudy | 2 | FALSE | 35 |  | 2 | No |  | No Conflict | Yes
BK-1230 | 2026-12-23 | 2026-12-29 |  | 6 | MEWP | Scissor Lift 10m | MEWP-08 |  |  | YST 09 | E | Assembly | Personnel Access Work | 7 Days | Night Shift (1900-0700) | Team Alpha | Basic Operator | High | Confirmed |  | Partly Cloudy | 9 | FALSE | 94 |  | 3 | No |  | No Conflict | Yes